## Active Project Tracking (hidden)
Name | Developer | Jurisdiction | State | Type | Size | Hearing / Target Date | ACE Engagement | Crop Engagement | Status post milestone | Remarks | Impressions | Advocacy | Links
Fayette Solar | Silicon Ranch | Fayette County (Lexington) | KY | Solar |  | 2024-09-26 | No | Yes | Commission rejected proposal for utility-scale solar expansion. Commission’s recommendation will be taken to the Lexington Fayette Urban County Government’s city council, which will have the final say on its implementation. |  | 641k (via CROP) | CROP Social + EN Petition - Ads campaign $11.5k spent | https://www.kentucky.com/news/local/counties/fayette-county/article293034494.html | Opinion piece by developer - post rejection https://www.kentucky.com/opinion/op-ed/article293593879.html | https://www.weku.org/lexington-richmond/2024-09-28/lexingtons-urban-county-planning-commission-rejects-proposal-that-would-allow-development-of-large-scale-solar-on-agricultural-zones
Dawn Harvest Solar Project | Invenergy | State - Public Service Commission (PSC) | WI | Solar | 150 MW | 2024-10-04 | Yes | Yes | Currently in administrative back and forth between PSC & developer. Next public meeting is Jan 17. Unclear if this will include public comment. PSC Project review chedule published through Feb 2025 |  |  |  | https://www.wpr.org/energy/wisconsin-utilities-propose-billions-renewable-energy-projects | https://psc.wi.gov/Pages/CommissionActions/CasePages/DawnHarvestSolar.aspx
Hope Ridge Wind Project | Enel Green Power | Dickinson County | KS | Wind | 334 MW | 2024-10-10 | Yes | Yes | After public comment period closed, County will decide whether to a) approve the project with conditions or b) reject the project and implement a 2 year moratorium |  |  |  | https://www.kwch.com/2024/10/11/proposed-wind-farm-project-prompts-massive-turnout-dickinson-county-meeting/
Birch Coulee Solar Project |  | Renville County | MN | Solar | 125 MW | 2024-10-09 | Miasia and team attending hearing | Potential for engagement with comment submission through Oct 25 https://mn.gov/commerce/energyfacilities/#comment Note: comments can be submitted via email - Comment Period Written comments will be accepted through October 25, 2024, by 4:30 p.m. Please include the docket number in all communications. Comments received after the close of the comment period may or may not be considered by the Commission. Topics for Comment  What potential human and environmental impacts of the proposed project should be considered in the environmental assessment?  Are there any methods to minimize, mitigate, or avoid potential impacts of the proposed project that should be considered in the environmental assessment?  Are there any unique characteristics of the proposed project that should be considered in the EA? Docket Number: IP7119/GS-23-477 Submit Comments Online: https://mn.gov/commerce/energyfacilities/#comment Email: Lauren.Agnew@state.mn.us U.S. Mail: Lauren Agnew Minnesota Department of Commerce 85 7th Place East, Suite 280 St. Paul, MN 55101
TBD | Opdenergy | Coweta County | GA | Solar | 476 MW | 2024-11-05 | Planned go live pre Oct 25 | Planned go live pre Oct 25
Paddlefish Solar | EDF Renewables | Huntington County & Wells County | IN | Solar | 350 MW | 2025-02-01 | Yes | Yes |  | Researching OOH opportunities
Pinal County | Sawtooth Dev Company / Operator is Copia Power | Pinal County | AZ | Solar | 1462 MW | 2024-10-30 | Yes - ads go live by Oct 18. Email and SMS to ACE network as well. | Yes - ads completed
Jackson County Wind Ordinance | N/A | Jackson County | IA | RE Ordinance | - | 2024-11-18 | Email + SMS to network | Yes - ads completed
Halifax County Solar Ordinance | N/A | Halifax Counrty | VA | RE Ordinance | - | 2024-11-19 | Email + SMS to network | Yes - ads completed
Cass County Solar Project | NextEra | Cass County | NE | Solar | 265 MW | 2024-12-02 | Email + SMS to network | Yes, first round of ads completed, running a second round 11/26-12/2 |  |  |  |  | https://www.nexteraenergyresources.com/cass-county-solar.html
Hope Hull Solar | Silicon Ranch | Montgomery (City) | AL | Solar | 80 MW | 2024-11-21 | Email + P2P paid calls+SMS to network | Yes - ads live on ASM socials Nov 15, paused on Nov 18
Bright Leaf & Swift Creek Solar + BESS | Clenera | Edgecombe County | NC | Solar + BESS | 192 MW | 2024-12-02 | Email + SMS to network | Yes - ads live on ASM socials Nov 27 - Dec 1
Rancho Viejo Solar | AES | Santa Fe County | NM | Solar + BESS | 144 MW | 2024-12-02 | Email + SMS to network | Yes - ads live on ASM socials Nov 27 - Dec 1
Yellow Barn Solar | CS Energy | Tompkins County

## Projects Supported Tracker (TD) (hidden)
Project | Developer | Type | Jurisdiction | Current Status | City | County FIPS Code | State | Lead Origin | Milestone | Milestone Type | Project Size MW | Project Size GW (formula) | Status Notes and Links | Original Hearing Date | Latest Hearing Date | Hearing Date Notes | Level of Outreach | ACE activation | CROP/AEJ/ASM activation | Which stage? | Status last updated | Total Impressions | Total Reach | Total Emails Sent | Total SMS Messages Sent | Total Calls | Totals Clicks (to page) | Total Comment Submissions (ETT page) | Total RSVPs (Petition page) | Total Attendees | Total RSVPs and Attendees (formula) | Links | Remarks | Report back from Partner | Docket #
Frasier Solar | Open Roads | Solar | Knox County | Win |  | 39083 | OH | ACE | Project | Project Hearing | 120 | 0.12 | Link | 2024-04-04 |  | TBD | Digital ads only | TRUE | TRUE | 4 local hearings done | 2025-04-01 | 2057706 | 624330 | 25442 | 2044 | 0 | 2400 | 327 | 33 |  | 33 | https://floodlightnews.org/fossil-fuel-interests-solar-ohio/
Mesa County Solar Moratorium | Moratorium | Solar | Mesa County | Win |  | 8077 | CO | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-04-23 |  | NA | Digi + P2P | FALSE | TRUE | Moratorium Reversed | 2025-04-01 | 404829 | 186478 | 0 | 7241 | 27 | 700 | 0 | 0 |  | 0
Yavapai County Solar Moratorium | Moratorium | Solar | Yavapai County | Loss |  | 4025 | AZ | Greenlight | Moratorium | Solar Moratorium | 0 | 0 |  | 2024-08-08 | 2024-09-06 |  | Digi + P2P | FALSE | TRUE | 3rd meeting on Nov 6th | 2025-04-01 | 243569 | 56958 | 0 | 235 | 55 | 577 | 0 | 2 |  | 2 | https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/News/Solar-Facilities-Zoning-Ordinance https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/Planning-Unit/Planning-Zoning-Cases/Solar-Facilities-Zoning-Ordinance-Amendment | 1 or 2 sign ups | Not hearing good news - so GL not going ahead with supporting
Mohave County Solar Moratorium | Moratorium | Solar | Mohave County | Loss |  | 4015 | AZ | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-06-03 |  |  | Digi + P2P | FALSE | TRUE | Ongoing with lot of gas lobbying | 2025-04-01 | 156574 | 29446 | 0 | 241 | 37 |  | 0 | 29 |  | 29 |  | Handful of RSVPs but no turn out | Passed a restrictive ordinance
Propel Transmission | New York Transco and NYPA | Offshore Wind | Nassau County | Pending |  | 36059 | NY | Greenlight | Project | Volunteer Open House | 432 | 0.432 | No hearing yet |  |  | TBD | Peer to Peer only | TRUE | FALSE | Early | 2025-04-01 | 0 | 0 | 0 | 1287 | 124 | 0 | 0 | 2 | 0 | 2 | PROPEL Open House Script | Southampton 9dot is related - looking across the island
Clear Mountain | Savion | Solar | Clermont County | Win |  | 39025 | OH | ACE | Project | Public Hearing | 100 | 0.1 | Link | 2024-08-01 | 2024-09-10 |  | Digi + P2P | FALSE | TRUE | 2 Local hearings done | 2025-04-01 | 807968 | 207851 | 0 | 566 | 0 | 5860 | 0 | 1 | 0 | 1
Ochoa Energy BESS | Vesper | BESS | Waller County | Loss | Katy | 48473 | TX | Greenlight | Project | Planning Meeting | 500 | 0.5 | Link | 2024-09-10 |  |  | Peer to Peer only | FALSE | FALSE | Initial planning | 2025-04-01 | 0 | 0 | 0 | 3619 | 0 | 0 | 20 | 0 |  | 0 | https://katytimes.com/stories/chamber-hosts-energy-experts,88922 | Update: Katy City Council denies project: https://www.chron.com/news/houston-texas/article/katy-battery-storage-facility-council-19863234.php . Earlier update: 10 people overall (Not just ACE)
Lexington Solar | Silicon Ranch | Solar | Fayette County | Pending |  | 21067 | KY | ACE | Project | Solar Zoning | 0 | 0 | Rejected by Commission. Council to review end of Q1 2025 | 2024-09-26 | 2024-09-26 |  | Digital ads only | FALSE | TRUE | Commission rejected proposal for utility-scale solar expansion. Commission’s recommendation will be taken to the Lexington Fayette Urban County Government’s city council, which will have the final say on its implementation. | 2025-04-02 | 1120432 | 210391 | 0 | 0 | 0 | 16867 | 0 | 4 |  | 4 | https://www.kentucky.com/news/local/counties/fayette-county/article293034494.html | Commission rejected, company seems to be looking to continue, wrote new op-ed since hearing in local paper
Prospect and Janus Solar Project |  | Solar | Weld County | Win |  | 8123 | CO | Greenlight | Project | Planning Meeting | 179 | 0.179 |  | 2024-10-01 | 2024-10-23 |  | Peer to Peer only | TRUE | FALSE | Joint hearings - Commission reviewed projects on 10/1, voting to approve on 10/23 | 2025-04-02 |  |  | 0 | 1281 | 0 |  |  | 1 | 1 | 2 |  | Vote on 22nd Oct
Town of Babylon BESS Moratorium | Moratorium | BESS | Suffolk County | Pending | Town of Babylon | 36103 | NY | Greenlight | Moratorium | BESS Moratorium | 0 | 0 | Moratorium Ending |  |  |  | Peer to Peer only | FALSE | TRUE | Moratorium currently in place thru 6 months post effective date of 6/5/24 - 12/5/24 | 2025-04-02 |  |  | 0 | 525 | 0 |  |  | 17 | 1 | 18 | https://www.townofbabylon.com/DocumentCenter/View/9791/0605---Adopt-of-LL-11-Moratorium
Dawn Harvest Solar | Invenergy | Solar | Rock County | Win |  | 55105 | WI | ACE | Project | Public Comment Period | 150 | 0.15 |  | 2024-06-01 | 2025-01-21 |  | Digital ads only | TRUE | TRUE | New public comment period in Dec/Jan. Public Comment completed, WI Public Service Commission to decide | 2025-04-02 | 1027208 | 505240 | 23886 | 13530 | 0 | 39162 | 146 | 7 |  | 7 | https://www.wpr.org/energy/wisconsin-utilities-propose-billions-renewable-energy-projects potentially part of larger deal with state of WI | 2nd Comment period open with the PCSW thru 1/23/25
Hope Ridge Wind | Enel | Onshore Wind | Dickinson County | Win |  | 20041 | KS | ACE | Project | Public Comment Period | 334 | 0.334 |  | 2024-10-10 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | Project Approved (11/21). Commissioners overrode the Planning Commission recommendation to deny the project. Public Comment is open through 11/19. Sending ACE list members SMS/Email to submit comment. | 2025-04-02 | 341944 | 27260 | 92 | 25 | 0 | 6054 | 1 | 18 |  | 18 | https://kclyradio.com/business/dickinson-county-planning-and-zoning-board-votes-to-deny-cup-for-wind-farm/ https://www.kwch.com/2024/10/11/proposed-wind-farm-project-prompts-massive-turnout-dickinson-county-meeting/ | Hearing completed | https://www.kwch.com/2024/10/17/planning-commission-votes-favor-2-year-moratorium-proposed-wind-farm-dickinson-county/
Southampton BESS Moratorium | Nine Dot | BESS | Suffolk County | Loss |  | 36103 | NY | Greenlight | Moratorium | BESS Moratorium | 0 | 0 |  | 2024-10-22 |  |  | Peer to Peer only | TRUE | FALSE | Early - ground softening | 2025-04-02 | 0 | 0 | 0 | 135 | 0 | 0 | 8 | 0 |  | 0
Birch Coulee | AES | Solar | Renville County | Pending |  | 27129 | MN | ACE | Project | Public Hearing | 125 | 0.125 |  | 2024-10-09 | 2024-10-09 |  | Organizing only | TRUE | FALSE | Hearing completed, comment period open until 10/25 - next steps in remarks | 2025-04-02 | 0 | 0 | 12690 | 0 | 5 | 26 | 14 | 0 | 4 | 4 | https://www.nujournal.com/news/communities/2024/10/11/245-million-solar-project-proposed-in-franklin/ https://efiling.web.commerce.state.mn.us/documents/%7BC06CE992-0000-C612-B70B-840CAA215451%7D/download?contentSequence=0&rowIndex=5 | An environmental assessment is forecast to be issued in February 2025. Following a March 2025 public hearing, an administrative law judge will file a report in May 2025. The Mn PUC will consider a site permit in June 2025. // Miasia and team attended hearing and will have a report back
Coweta County Solar | Opdenergy | Solar | Coweta County | Loss |  | 13077 | GA | ACE | Project | Public Hearing | 476 | 0.476 |  | 2024-09-12 | 2025-01-25 |  | Digital ads only | TRUE | TRUE | first hearing done, work session 10/24, final hearing 11/5. Commissioners extended hearing until January 2025. At January hearing, they passed an ordinance with a 500 acre cap for solar, killing the Opdenergy proposal | 2025-04-02 | 217744 | 12264 | 212 | 78 |  | 2640 | 0 | 5 |  | 5 | https://www.times-herald.com/news/county-continues-to-revise-proposed-solar-ordinance/article_e14a6b7c-7157-11ef-8f68-9fc45fcc9ffc.html https://www.times-herald.com/news/commissioners-say-solar-energy-systems-should-be-no-more-than-500-acres/article_c4563780-930d-11ef-8366-67c060426d39.html#:~:text=in%20Coweta%20County.-,The%20Coweta%20County%20Commissioners%20advised%20county%20staff%20to%20not%20allow,is%20the%20House%20of%20Pickleball. | Hearing day of election, moving forward with ACE & CROP ads. Commission has advised staff to add a 500 acre cap on projects, per community feedback. They added it and voted to approve restrictive ordinance in Jan 2025
Pinal County Solar | Multiple Developers | Solar | Pinal County | Pending |  | 4021 | AZ | Greenlight | Project | Public Hearing | 1462 | 1.462 | Link |  | 2024-10-30 |  | Digi + P2P | FALSE | TRUE | Comp Plan Zoning Changes approved for solar project sites | 2025-04-02 | 490801 | 35966 | 0 | 948 | 86 | 2476 | 0 | 11 |  | 11 | Ore Town: https://copperarea.com/proposed-solar-farm-near-san-manuel-has-residents-asking-questions/ // Many projects in the area up for approval: https://www.pinalcentral.com/maricopa_monitor/news/solar-applications-bombard-pinal-county/article_548cb27e-5a8e-11ef-8df2-cbef43f2ee37.html?utm_campaign=blox&utm_source=facebook&utm_medium=social&fbclid=IwY2xjawF7gNVleHRuA2FlbQIxMQABHWhjkBDsnw1Wn3W-c5OcwL-tR7Ggy1lBppW9Nwh_aFXpUJsIsTc0Uj6wlw_aem_bOVh2rKUdvrOrHXC42CINA | Helping GL with turnout - CROP & AEJ ads
Jackson County Wind | Ordinance | Onshore Wind | Jackson County | Pending |  | 19097 | IA | ACE | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-18 | 2024-11-18 |  | Digi + P2P | TRUE | TRUE | Awaiting results of hearing on 11/18. | 2025-04-02 | 11535 | 1361 | 20 | 16 | 0 | 2923 | 0 | 0 |  | 0
Halifax County Solar | Ordinance | Solar | Halifax County | Loss |  | 51083 | VA | ACE | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County passed a very restrictive solar ordinance and lowered density cap from 5% to 3%. Landscape is tough for utility-scale development moving forward | 2025-04-02 | 9881 | 1137 | 30 | 20 | 0 | 2756 | 0 | 0 |  | 0
Cass County Solar | NextEra Energy | Solar | Cass County | Loss |  | 31025 | NE | ACE | Project | Public Hearing | 265 | 0.265 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County DENIED permit on Feb 14 | 2025-04-02 | 28331 | 3521 | 24 | 12 | 0 | 3027 | 0 | 0 | 0 | 0 |  | https://rivercountry.newschannelnebraska.com/story/52367495/county-rejects-cass-county-solar
Bright Leaf & Swift Creek Solar + BESS | Multiple Developers | Solar + BESS | Edgecombe County | Loss |  | 37065 | NC | ACE | Project | Public Comment Period | 192 | 0.192 |  | 2024-12-02 | 2024-12-02 |  | Digi + P2P | TRUE | TRUE | Special use permits DENIED at meeting on 12/2. Connect with devs on any next steps when the current moratorium period is over. | 2025-04-02 | 31098 | 3437 | 62 | 0 | 0 | 1358 | 12 |  |  | 0
Surry County BESS | Clenera | BESS | Surry County | Win |  | 51181 | VA | ACE | Ordinance | Public Hearing | 400 | 0.4 |  | 2024-12-16 | 2025-01-27 | Cont. from Dec hearing | Digi + P2P | FALSE | TRUE | Running second rnd of ads for the continued hearing on 1/27 | 2025-04-02 | 316782 | 24825 | 0 | 0 | 0 | 4850 | 6 | 0 | 0 | 0 | https://www.smithfieldtimes.com/2025/05/14/developer-surry-battery-site-would-see-less-traffic-than-solar-farms/ | Ordinance approved April 2 by Commissioners. Clanera now moving forward with application for BESS project
Paddlefish Solar | EDF Renewables | Solar | Huntington County | Potential |  | 18069 | IN | ACE | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
Paddlefish Solar | EDF Renewables | Solar | Wells County | Potential |  | 18179 | IN | ACE | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
Hope Hull Solar | Silicon Ranch | Solar | Montgomery | Win | Montgomery | 1101 | AL | ACE | Project | Public Hearing | 80 | 0.08 |  | 2024-11-21 | 2025-01-16 |  | Digi + P2P | TRUE | TRUE | Final approval granted by Montgomery County Board of Adjustment on 1/16! | 2025-04-02 | 43527 | 6967 | 526 | 7031 | 525 | 1140 | 27 | 77 | 1 | 78
Eastern Cottontail Solar | EDF Renewables | Solar | Fairfield County | Pending |  | 39045 | OH | Greenlight | Project | Public Hearing | 220 | 0.22 | Scripts | 2025-01-27 | 2025-01-27 |  | Digi + P2P | FALSE | TRUE |  | 2025-04-07 | 166275 | 23556 | 0 | 382 | 0 | 74 | 3 | 0 | 0 | 0
Schnebly Coulee Solar | Invenergy | Solar | Kittitas County | Pending |  | 53037 | WA | Greenlight | Project | Volunteer Open House | 90 | 0.09 | Toolkit | 2024-12-18 |  |  | Peer to Peer only | FALSE | TRUE | A second round of text and phonebanking support provided in Feb 2025 | 2025-04-07 | 0 | 0 | 2 | 102 | 26 | 0 |  | 2 | 1 | 3 |  | One of our YAN members attended the second hearing and spoke as well
Sussex County Offshore Wind Project | Overall | Offshore Wind | Sussex County | Potential |  | 10005 | DE | Greenlight | Project | Public Hearing | 0 | 0 |  | 2024-12-10 |  |  | Peer to Peer only | TRUE | FALSE |  | 2025-04-07 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0
Santa Fe Planning Commission voted (6-1) to APPROVE the Conditional Use Permit yesterday. Parties have 30 days to appeal the Planning Commission’s decision to the County Commission. Appealed to County Commissioners - Hearing is 8/11 | AES | Solar + BESS | Santa Fe County | Pending |  | 35049 | NM | Greenlight | Project | Public Hearing | 144 | 0.144 | GL Campaign | 2024-02-05 | 2025-02-03 | Next Hearing 8/11 | Digi + P2P | TRUE | TRUE | Santa Fe Planning Commission voted (6-1) to APPROVE the Conditional Use Permit yesterday. Parties have 30 days to appeal the Planning Commission’s decision to the County Commission. Opposition groups say they will appeal. | 2025-06-26 | 18226 | 2338 | 4779 | 2310 | 380 | 1836 | 31 | 55 | 1 | 56
Hesperus Solar | Primergy | Solar + BESS | La Plata County | Withdrawn |  | 8067 | CO | Longitudinal | Project | Project Hearing | 155 | 0.155 | News Article |  | 2024-10-29 |  |  | FALSE | FALSE | The application for a 1,900-acre solar project has been deemed withdrawn by county planners, although the developer has stated an intent to resubmit the application. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prairie Power Solar Farm | Prairie Power Inc | Solar | Sangamon County | Pending |  | 17167 | IL | Longitudinal | Project | Pre Application | 200 | 0.2 |  |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Soul City Solar Project | Apex Clean Energy | Solar | Hinds County | Win |  | 28049 | MS | Longitudinal | Project | Project Approved | 396 | 0.396 | News Article |  | 2024-06-18 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Libra Solar Project | Arevia Power | Solar + BESS | Mineral County | Win |  | 32021 | NV | Longitudinal | Project | Project Approved | 700 | 0.7 | News Article | 2024-09-09 | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Greenlink West Transmission Project | NV Energy | Transmission |  | Win |  |  | NV | Longitudinal | Project | Project Approved | 0 | 0 | News Article |  | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dry Lake East Energy Center | NextEra | Solar + BESS | Clark County | Win |  | 32003 | NV | Longitudinal | Project | Project Approved | 800 | 0.8 | News Article |  | 2024-08-30 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blue Ridge Solar | Recurrent Energy | Solar | Pittsylvania County | Win |  | 51143 | VA | Longitudinal | Project | Project Approved | 150 | 0.15 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michaux Solar | Dominion Energy | Solar | Henry County | Win |  | 51089 | VA | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michaux Solar | Dominion Energy | Solar | Pittsylvania County | Win |  | 51089 | VA | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Junction Solar | Alliant Energy | Solar + BESS | Greene County | Win |  | 19073 | IA | Longitudinal | Project | Project Approved | 150 | 0.15 | News |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Split Rail Solar | Ameren | Solar | Warren County | Win |  | 29219 | MO | Longitudinal | Project | Project Approved | 300 | 0.3 | News Article |  | 2024-03-22 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Badger Hollow Wind | Invenergy | Onshore Wind | Iowa County | Active |  | 55049 | WI | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-06-24 |  | Digi + P2P | FALSE | TRUE | Public hearings scheduled for June 24, 2pm & 6pm sessions (per WI siting table) | 2025-06-06 | 150650.5 | 28243.5 | 23864 | 11314.5 | 0 | 7622 | 58 | 0 | 0 | 0 |  |  |  | 9827-CE-100
Badger Hollow Wind | Invenergy | Onshore Wind | Grant County | Active |  | 55043 | WI | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-06-24 |  | Digi + P2P | FALSE | TRUE | Public hearings scheduled for June 24, 2pm & 6pm sessions (per WI siting table) | 2025-06-06 | 150650.5 | 28243.5 | 23864 | 11314.5 | 0 | 7622 | 59 | 0 | 0 | 0 |  |  |  | 9827-CE-100
Uplands Wind | Pattern Energy | Onshore Wind | Lafayette County | Pending |  | 55065 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Uplands Wind | Pattern Energy | Onshore Wind | Iowa County | Pending |  | 55049 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Uplands Wind | Pattern Energy | Onshore Wind | Grant County | Pending |  | 55043 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Mount Vernon BESS | NextEra | BESS | Skagit County | Win |  | 53057 | WA | ACE | Project | Public Hearing | 200 | 0.2 | Hearing Announcement | 2024-12-20 |  |  | Digi + P2P | FALSE | TRUE | Comment period open ahead of public meeting on 12/20. Decision expected ~2 weeks post-meeting | 2025-04-22 | 39408 | 5093 | 107 | 64 |  | 1983 | 6 | 0 | 0 | 0
Gabriel Solar | Gabriel Energy / Energix US | Solar + BESS | Prince Edward County | Loss |  | 51147 | VA | ACE | Project | Public Hearing | 200 | 0.2 | Hearing Documents | 2024-12-17 | 2025-02-11 |  | Digi + P2P | FALSE | TRUE | Public hearing of county commissioners on 2/11 | 2025-01-13 | 226826 | 37131 | 32 | 9 |  | 3838 | 6 | 0 | 3 | 3
Keystone Wind | RWE | Onshore Wind | Pawnee County | Active |  | 40117 | OK | RWE | Project |  | TBD | [5 empty] | Digital ads only | FALSE | TRUE | Early stages of planning, signing landowners | 2025-05-12 | 607009 | 202844 |  | 0 | 0 | 0 | 0 |  |  | 0
Prairie Wolf Wind | RWE | Onshore Wind | Hughes County | Active |  | 40063 | OK | RWE | Project | Planning Meeting | 119.5 | 0.1195 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-02-11 | 171151.5 | 56013 |  | 0 | 0 | 0 | 0 | 17 |  | 17
Prairie Wolf Wind | RWE | Onshore Wind | Okfuskee County | Active |  | 40107 | OK | RWE | Project | Planning Meeting | 119 | 0.119 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-02-11 | 171151.5 | 56013 |  | 0 | 0 | 0 | 0 | 17 |  | 17
Iron Pine Solar | Swift Current Energy | Solar | Pine County | Win |  | 27115 | MN | ACE | Project | Project Hearing | 325 | 0.32 |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | Awaiting MN PUC decision | 2025-02-26 | 57786 | 14393 | 7259 | 7284 | 884 | 1112 | 86 | 30 | 11 | 41 |  |  |  | IP7114/GS-23-414 (Site Permit) and IP7114/TL-23-415 (Route Permit) OAH Docket Number: 22-2500-40198
Westfield Battery Ordinance | Jupiter Power | BESS | Hampden County | Pending |  | 25013 | MA | ACE | Ordinance | Public Comment Period |  |  |  |  | 2025-02-06 |  | Digi + P2P | TRUE | TRUE | City council considering strict rules to stifle BESS construction. Council appears united in opposition of BESS and is intervening in Jupiter's application for state approval. | 2025-02-07 | 36565 | 8134 |  |  |  | 523 | 0 |  |  | 0
Bolivar Onshore Wind Ordinance | Steelhead/Vestas | Onshore Wind | Bolivar County | Potential |  | 28011 | MS | ACE | Ordinance | Public Hearing |  |  |  |  | 2025-02-17 |  |  | TRUE | TRUE |  | 2025-04-07 | [5 empty] | 0 | 0 |  |  | 0
Goshen Onshore Wind Ordinance |  | Onshore Wind | Goshen County | Pending |  | 56015 | WY | ACE | Ordinance | Public Hearing |  |  |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | Commissioners considering appendix on wind permitting to set guidelines | 2025-02-07 | 815 | 178 |  |  |  | 346 | 0 |  |  | 0
Lee Onshore Wind & Solar Ordinance |  | Onshore Wind & Solar | Lee County | Potential |  | 19111 | IA | ACE | Ordinance | [7 empty] | Organizing only | TRUE | TRUE | Board of Commissioners has been drafting new wind and solar regulations. Likely target date of April 2025~ | 2025-04-07
New York Rapid Act |  | Onshore Wind & Solar | New York State | Potential |  |  | NY | ACE | Legislation | Public Hearing |  |  | Hearing Details | 2025-02-19 |  |  | Organizing only | TRUE | FALSE | The NY Department of Public Service is holding a public hearing regarding the RAPID act which gives the state broader control to review projects. | 2025-04-07
Daviess Solar Ordinance |  | Solar | Daviess County | Potential |  | 21059 | KY | Laurie | Ordinance | Public Hearing |  |  |  | 2025-02-20 |  |  | Digi + P2P | TRUE | TRUE | HOLD: Fiscal Court enacted a 12 month moratorium on rewewables at their first reading of the potential new ordinance. Enacted ordinance for 1000 ft setback. | 2025-04-07
Surprise BESS Ordinance |  | BESS | Surprise | Potential | Surprise | 4013 | AZ | AZ Siting Table | Ordinance | Public Comment Period | [6 empty] | Digi + P2P | TRUE | TRUE | The city is likely to schedule a public hearing soon. It is a good time for BESS support messages ahead of the hearings. HOLD UNTIL NEXT STEPS FROM LEGAL | 2025-04-07
Livingston Energy Storage | Vesper Energy | BESS | Otsego County | Potential |  | 26137 | MI | ACE | Project | Pre Application | 300 | 0.3 |  |  |  |  | Digital ads only | FALSE | TRUE | Ground softening ads. A nice way to break in with a new developer. The developer just hosted the first of a series of community meetings. No application has been submitted yet. | 2025-04-07
Hanover BESS | Northland Power | BESS | Town of Hanover | Potential | Hanover | 36013 | NY | ACE | Project | Pre Application | 250 | 0.25 |  | 2025-02-24 |  |  | Digi + P2P | TRUE | TRUE | Town Board public hearing to gauge public input regarding the presence of such a facility in the town. | 2025-04-07
Yellow Barn Solar | CS Energy | Solar | Tompkins County | Win |  | 36109 | NY | ACE | Project | Public Comment Period | 160 | 0.16 |  |  | 2025-02-20 |  | Peer to Peer only | TRUE | TRUE | Public hearing for Yellow Barn Solar. The state has issued a draft permit for the project in December. One of the last remaining hurdles is local input, though approval is ultimately with the state. It is important to show local support for a project like this so the state sees it is not just opposition. | 2025-04-07 | 0 | 0 | 228 | 64 |  |  | 81 |  |  |  | Article citing approval
Grass Lake Solar | NextEra | Solar | Grass Lake Township | Potential | Grass Lake Township | 26075 | MI | ACE | Ordinance | Public Hearing | 100 | 0.1 |  |  |  |  | Digi + P2P | TRUE | TRUE | Town supervisor/trustees to hold public hearing by end of month of Feb - Decision to come by early March on mutually agreed upon ordinance with NextEra | 2025-04-07 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
New Frontiers Solar Park | EDPR | Solar | Breckinridge County | Win |  | 21027 | KY | Laurie | Project | Public Comment Period | 100 | 0.1 |  |  | 2025-03-20 |  | Digital ads only | FALSE | TRUE | The project is in front of the PSC for approval now and accepting comment. | 2025-03-24 | 61116 | 11570 | 8704 | 8760 |  |  | 110
Darden Energy Center | Intersect Power | Solar + BESS | Fresno County | Potential |  | 6019 | CA | ACE | Project | Public Comment Period | 6100 | 6.1 |  |  | 2025-04-21 |  |  | FALSE | FALSE | This is the first project to move this far in CA’s new “opt-in” regulatory process for largescale renewable projects which dramatically speeds up reviews and approvals for large scale projects. Project must receive a final determination within 270 days from application deemed complete. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blue Lake BESS | Power Transitions | BESS | Blue Lake | Potential | Blue Lake | 6023 | CA | ACE | Project | Public Hearing | 20 | 0.02 | Blue Lake, CA - BESS Project - Planning Doc | 2025-02-25 | 2025-03-25 |  | Digi + P2P | TRUE | TRUE | This hearing is regarding whether to move forward with an agreement to sell 2 acres to the developer. It is NOT for a project permit. City will take lead on permitting if/when the project is ready to submit for a CUP | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allen County Solar Ordinance |  | Solar | Allen County | Active |  | 18003 | IN | Solar United Neighbors Indiana | Ordinance | Public Hearing |  |  |  |  | March/April 2025 |  |  | FALSE | FALSE | Public hearings around a solar ordinance in March/April of 2025 | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Valley Farms Energy Storage | NextEra | BESS | Pinal County | Potential |  | 4021 | AZ | AZCE | Project | Public Hearing | 400 | 0.4 |  |  | Late March 2025 |  |  | FALSE | FALSE | Project was just recommended for denial last week by the planning commission (5-2 vote). In 4-6 weeks it will be heard by the Board of Supervisors. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ironwood Transmission Line | Energy West (NextEra) | Transmission | Yuma County | Potential |  | 4027 | AZ |  | Project | Developer Community Meeting | 3000 | 3 |  |  | 2025-04-01 |  | Digi + P2P | TRUE | TRUE | Pre-application, upcoming intervention point. Developer community meeting held by Energy West upcoming. Multi-state project that may traverse BLM land, number of regulatory approvals needed as this will requre permits from both state and federal agencies including CEQA and NEPA approvals. Expected to take 4 years to get all regulatory approvals. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Flickertail Solar | Savion | Solar | Richland County | Pending |  | 38077 | ND | ACE | Project | Public Hearing | 300 | 0.3 | Richland County, ND - Flickertail Solar - Planning Doc | 2025-03-25 |  |  | Digi + P2P | TRUE | TRUE | The project is up for approval on a state level, as it is over 50MW in size. March 25th is the date of the ND PSC’s public hearing to determine approval of the siting permit required to move forward with the project. | 2025-05-07 | 103822 | 7153 | 0 | 0 | 680 | 0 | 0 | 1 | 0 | 1
Gibson Solar | Open Road Renewables | Solar | King George County | Pending |  | 51099 | VA | Curate | Project | Public Hearing | 134 | 0.134 | King George County, VA - Gibson Solar Project - Planning Doc | 2025-04-01 |  |  | Digi + P2P | TRUE | TRUE | The approval for this project lies with the county, with 2 steps remaining: 1.) Planning Commission Recommendation and 2.) Board of Supervisors next hearing for this project will be held on April 15th by the Board of Supervisors. | 2025-04-07 | 4866 | 706 | 19 | 9 | 2324 | 0 | 0 | 11 | 0
Midwater Energy Storage | Spearmint Energy | BESS | Freeborn County | Active |  | 27047 | MN | ACE | Project | Public Comment Period | 150 | 0.15 | Freeborn County MN - Midwater Energy Storage BESS - Planning Doc | 2025-04-07 | 2025-04-21 |  | Digi + P2P | TRUE | TRUE | In the first stage in the Minnesota state review process. Open comment period is accepting comments regarding suggestions for the Environmental Assessment (EA). After the EA is complete, there will be public hearings and another comment period to accept general support/opposition comments on the project. | 2025-05-07 | 70714 | 20442 | 0 | 0 | 0 | 2544 | 102 | 0 | 0 | 0
Antlers Road Solar | RWE | Solar | Mecklenburg County | Active |  | 51117 | VA | ACE | Project | Public Hearing | 90 | 0.09 |  |  |  |  | Organizing only | TRUE | FALSE |  | 2025-05-07 | 0 | 0 | 28 | 22 | 2372 | 0 | 0 | 5 | 0 | 5
Little Prairie Hybrid | BayWa r.e. | Solar + BESS | Champaign County | Win |  | 17019 | IL | Greenlight | Project | Public Hearing | 270 | 0.27 | https://us.baywa-re.com/en/americas-cases/little-prairie | 2025-04-10 |  | https://citizenportal.ai/articles/2977427/Champaign-County/Illinois/Champaign-County-considers-zoning-approval-for-Little-Prairie-Solar-Project | Peer to Peer only | TRUE | FALSE | 5-1 vote by the Board APPROVED conditional use permit. | 2025-05-07 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0
Yellow Rosebush | Savion | Solar + BESS | Wasco County | Active |  | 41065 | OR | Greenlight | Project | Public Hearing | 800 | 0.8 | https://www.oregon.gov/energy/facilities-safety/facilities/Pages/YRB.aspx | TBD |  |  | Peer to Peer only | TRUE | FALSE | No set milestones currently, we are estimating there will be some in April. - GL | 2025-05-07 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
Fort Watt BESS | Cypress Creek | BESS | Tarrant County | Active | Kennedale | 48439 | TX | Greenlight | Project | Public Hearing | 255 | 0.255 |  | 2025-04-24 | 2025-05-20 |  | Peer to Peer only | TRUE | FALSE | Planning & Zoning meeting on 4/24/25, City Council on 5/20/25 | 2025-05-07 | 0 | 0 | 0 | 170 | 178 | 0 | 0 | 0 | 0 |  |  | From GL: We had an interim victory in Tarrant County TX this week - the 201.4 MW Fort Watt BESS project being developed by Cypress Creek - with a unanimous victory (all 3 members present voted yes) at the planning and zoning commission.
Purple Sage BESS | RWE | BESS | Collin County | Active | Weston | 48085 | TX | ACE | Project |  | 300 | 0.3 |  |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-06-06 | [11 empty] | Working with RWE
San Luis Obispo OSW | CET | Offshore Wind | San Luis Obispo County | Active |  | 68154 | CA | Greenlight | Project | Project Hearing |  |  |  | 2025-03-25 |  |  | Peer to Peer only | TRUE | FALSE |  | 2025-06-06 | 0 | 0 | 0 |  | 757 | 20 |  | 9
Buffalo Burr Solar + BESS |  | Solar + BESS | Pueblo County | Potential |  | 8101 | CO | Greenlight | Project

## Combined - Projects Tracker
Project | Developer | Type | County | Current Status | City | County FIPS Code | State | Primary Jurisdiction | Secondary Jurisdiction | Jurisdiction Note | Lead Origin | Milestone | Milestone Type | Project Size MW | Project Size GW | Status Notes and Links | Original Hearing Date | Latest Hearing Date | Hearing Date Notes | Level of Outreach | ACE activation | CROP/AEJ/ASM activation | Which stage? | Status last updated | Total Impressions | Total Reach | Total Engagement | Total Link Clicks | Total Emails Sent | Total SMS Sent | Total SMS Delivered | Total SMS Replies | Total Calls | Total Answered Calls | Totals Clicks (to page) | Total Page Submissions | Total RSVPs | Total Attendees | Total RSVPs and Attendees | Links | Remarks | Report back from Partner | Docket #
Frasier Solar | Open Roads | Solar | Knox County | Win |  | 39083 | OH | Ohio Power Siting Board |  |  | GoodPower | Project | Project Hearing | 120 | 0.12 | Link | 2024-04-04 |  | TBD | Digital ads only | TRUE | TRUE | 4 local hearings done | 2025-07-15 | 2057706 | 624330 | 630179 | 7610 | 23 | 2044 | 0 | 0 | 0 | 0 | 0 | 327 | 33 | 0 | 33 | https://floodlightnews.org/fossil-fuel-interests-solar-ohio/
Mesa County Solar Moratorium | Moratorium | Solar | Mesa County | Win |  | 8077 | CO | Mesa County Board of Commissioners |  |  | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-04-23 |  | NA | Digi + P2P | FALSE | TRUE | Moratorium Reversed | 2024-10-08 | 404829 | 84400 | 186478 | 980 | 0 | 7241 | 0 | 0 | 229 | 27 | 0 | 0 | 3 | 0 | 3
Yavapai County Solar Moratorium | Moratorium | Solar | Yavapai County | Loss |  | 4025 | AZ | Yavapai County Board of Commissioners |  |  | Greenlight | Moratorium | Solar Moratorium | 0 | 0 |  | 2024-08-08 | 2024-09-06 |  | Digi + P2P | FALSE | TRUE | 3rd meeting on Nov 6th | 2024-10-08 | 243569 | 56958 | 142633 | 836 | 0 | 235 | 0 | 570 | 485 | 21 | 0 | 0 | 37 | 15 | 52 | https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/News/Solar-Facilities-Zoning-Ordinance https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/Planning-Unit/Planning-Zoning-Cases/Solar-Facilities-Zoning-Ordinance-Amendment | 1 or 2 sign ups | Not hearing good news - so GL not going ahead with supporting
Mohave County Solar Moratorium | Moratorium | Solar | Mohave County | Loss |  | 4015 | AZ | Mohave County Board of Commissioners |  |  | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-06-03 |  |  | Digi + P2P | FALSE | TRUE | Ongoing with lot of gas lobbying | 2024-10-08 | 156574 | 29446 | 134948 | 226 | 0 | 241 | 0 | 0 | 244 | 37 | 0 | 52 | 9 | 0 | 9 |  | Handful of RSVPs but no turn out | Passed a restrictive ordinance
Propel Transmission | New York Transco and NYPA | Offshore Wind | Nassau County | Pending |  | 36059 | NY | New York State Public Service Commission / Office of Renewable Energy Siting (ORES) |  | At time of application, filed with NY PSC. SInce filing, NY State's RAPID act, created the ORES which oversees projects like Propel | Greenlight | Project | Volunteer Open House | 432 | 0.432 | No hearing yet |  |  | TBD | Peer to Peer only | TRUE | FALSE | Working with GL on a second stage of P2P outreach (April 2025) | 2025-04-21 | 0 | 0 | 0 | 0 | 0 | 1287 | 0 | 0 | 457 | 64 | 0 | 0 | 2 | 0 | 2 | PROPEL Open House Script | Southampton 9dot is related - looking across the island
Clear Mountain | Savion | Solar | Clermont County | Win |  | 39025 | OH | Ohio Power Siting Board |  |  | GoodPower | Project | Public Hearing | 100 | 0.1 | Link | 2024-08-01 | 2024-09-10 |  | Digi + P2P | FALSE | TRUE | 2 Local hearings done | 2024-10-08 | 807968 | 207851 | 474095 | 3718 | 0 | 566 | 0 | 0 | 0 | 0 | 0 | 35 | 1 | 0 | 1
Ochoa Energy BESS | Vesper | BESS | Waller County | Loss | Katy | 48473 | TX | City of Katy (City Council) |  |  | Greenlight | Project | Planning Meeting | 500 | 0.5 | Link | 2024-09-10 |  |  | Peer to Peer only | FALSE | FALSE | Initial planning | 2024-10-09 | 0 | 0 | 0 | 0 | 0 | 3619 | 0 | 0 | 0 | 0 | 0 | 20 | 1 | 1 | 2 | https://katytimes.com/stories/chamber-hosts-energy-experts,88922 | Update: Katy City Council denies project: https://www.chron.com/news/houston-texas/article/katy-battery-storage-facility-council-19863234.php . Earlier update: 10 people overall (Not just ACE)
Lexington Solar | Silicon Ranch | Solar | Fayette County | Pending |  | 21067 | KY | Lexington-Fayette's County Board of Adjustment | Lexington-Fayette County's Planning Commission / Urban County Council | The project requires a zoning text amendment. The Lexington-Fayette Urban County Council reviewed and denied the amendment. Our understanding is the Urban County Council has the final authority on the text amendment. If approved, the conditional use permit would be issued by the County Board of Adjustment | GoodPower | Project | Solar Zoning | 0 | 0 | https://news.civiclex.org/council-advances-solar-regulations/ - Effectively blocked. LFUCG adopted Solar Panel ZOTA on Sept 11, 2025, which bans large-scale ground-mounted solar in rural/ag zones | 2024-09-26 | 2024-09-26 |  | Digital ads only | FALSE | TRUE | Commission rejected proposal for utility-scale solar expansion. Commission’s recommendation will be taken to the Lexington Fayette Urban County Government’s city council, which will have the final say on its implementation. | 2024-10-15 | 1120432 | 210391 | 225452 | 15020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | https://www.kentucky.com/news/local/counties/fayette-county/article293034494.html | Commission rejected, company seems to be looking to continue, wrote new op-ed since hearing in local paper
Prospect and Janus Solar Project |  | Solar | Weld County | Win |  | 8123 | CO | Weld County Board of Commissioners |  |  | Greenlight | Project | Planning Meeting | 179 | 0.179 |  | 2024-10-01 | 2024-10-23 |  | Peer to Peer only | TRUE | FALSE | Joint hearings - Commission reviewed projects on 10/1, voting to approve on 10/23 | 2024-10-15 | 0 | 0 | 0 | 0 | 0 | 1286 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 |  | Vote on 22nd Oct
Town of Babylon BESS Moratorium | Moratorium | BESS | Suffolk County | Pending | Town of Babylon | 36103 | NY | Town of Babylon (Town Board) |  |  | Greenlight | Moratorium | BESS Moratorium | 0 | 0 | Moratorium Ending |  |  |  | Peer to Peer only | FALSE | TRUE | Moratorium currently in place thru 6 months post effective date of 6/5/24 - 12/5/24 | 2024-10-15 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 1 | 18 | https://www.townofbabylon.com/DocumentCenter/View/9791/0605---Adopt-of-LL-11-Moratorium
Dawn Harvest Solar | Invenergy | Solar | Rock County | Win |  | 55105 | WI | Public Service Commission of Wisconsin |  |  | GoodPower | Project | Public Comment Period | 150 | 0.15 | PSC Approved April 24, 2025 (minutes) | 2024-06-01 | 2025-01-21 |  | Digital ads only | TRUE | TRUE | PSC approved project with conditions. Two public comment periods completed. Ace drove 64 support comments | 2025-05-18 | 1027208 | 382536 | 312154 | 20060 | 28915 | 11265 | 9412 | 0 | 0 | 0 | 0 | 218 | 7 | 0 | 7 | https://www.wpr.org/energy/wisconsin-utilities-propose-billions-renewable-energy-projects potentially part of larger deal with state of WI | Project approved by PSC.
Hope Ridge Wind | Enel | Onshore Wind | Dickinson County | Win |  | 20041 | KS | Dickinson County Board of Commissioners |  |  | GoodPower | Project | Public Comment Period | 334 | 0.334 |  | 2024-10-10 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | Project Approved (11/21). Commissioners overrode the Planning Commission recommendation to deny the project. Public Comment is open through 11/19. Sending ACE list members SMS/Email to submit comment. | 2024-11-18 | 341944 | 27260 | 13661 | 1912 | 92 | 9 | 5 | 0 | 0 | 0 | 0 | 1 | 18 | 0 | 18 | https://kclyradio.com/business/dickinson-county-planning-and-zoning-board-votes-to-deny-cup-for-wind-farm/ https://www.kwch.com/2024/10/11/proposed-wind-farm-project-prompts-massive-turnout-dickinson-county-meeting/ | Hearing completed | https://www.kwch.com/2024/10/17/planning-commission-votes-favor-2-year-moratorium-proposed-wind-farm-dickinson-county/
Southampton BESS Moratorium | Nine Dot | BESS | Suffolk County | Loss |  | 36103 | NY | Southampton Town Council |  |  | Greenlight | Moratorium | BESS Moratorium | 0 | 0 |  | 2024-10-22 |  |  | Peer to Peer only | TRUE | FALSE | Early - ground softening | 2024-11-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Birch Coulee | AES | Solar | Renville County | Pending |  | 27129 | MN | Minnesota Public Utilities Commission |  |  | GoodPower | Project | Public Hearing | 125 | 0.125 | Permit Granted Agenda. Awaiting Final ruling from MN PSC | 2024-10-09 | 2024-10-09 |  | Organizing only | TRUE | FALSE | Hearing completed, comment period open until 10/25 - next steps in remarks | 2024-10-15 | 0 | 0 | 0 | 0 | 12690 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | https://www.nujournal.com/news/communities/2024/10/11/245-million-solar-project-proposed-in-franklin/ https://efiling.web.commerce.state.mn.us/documents/%7BC06CE992-0000-C612-B70B-840CAA215451%7D/download?contentSequence=0&rowIndex=5 | An environmental assessment is forecast to be issued in February 2025. Following a March 2025 public hearing, an administrative law judge will file a report in May 2025. The Mn PUC will consider a site permit in June 2025. // Miasia and team attended hearing and will have a report back
Coweta County Solar | Opdenergy | Solar | Coweta County | Loss |  | 13077 | GA | Coweta County Board of Commissioners |  |  | GoodPower | Project | Public Hearing | 476 | 0.476 |  | 2024-09-12 | 2025-01-25 |  | Digital ads only | TRUE | TRUE | first hearing done, work session 10/24, final hearing 11/5. Commissioners extended hearing until January 2025. | 2024-11-21 | 217744 | 12264 | 6819 | 670 | 212 | 78 | 67 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 5 | https://www.times-herald.com/news/county-continues-to-revise-proposed-solar-ordinance/article_e14a6b7c-7157-11ef-8f68-9fc45fcc9ffc.html https://www.times-herald.com/news/commissioners-say-solar-energy-systems-should-be-no-more-than-500-acres/article_c4563780-930d-11ef-8366-67c060426d39.html#:~:text=in%20Coweta%20County.-,The%20Coweta%20County%20Commissioners%20advised%20county%20staff%20to%20not%20allow,is%20the%20House%20of%20Pickleball. | Hearing day of election, moving forward with ACE & CROP ads. Commission has advised staff to add a 500 acre cap on projects, per community feedback
Pinal County Solar | Multiple Developers | Solar | Pinal County | Pending |  | 4021 | AZ | Pinal County Board of Supervisors |  | Projects first need a comprehensive plant amendment. Once granted, they can apply for conditional use permits. | Greenlight | Project | Public Hearing | 1462 | 1.462 | Link |  | 2024-10-30 |  | Digi + P2P | FALSE | TRUE | Comp Plan Zoning Changes approved for solar project sites | 2024-11-18 | 490801 | 35966 | 24353 | 2476 | 0 | 956 | 0 | 0 | 974 | 86 | 0 | 0 | 18 | 3 | 21 | Ore Town: https://copperarea.com/proposed-solar-farm-near-san-manuel-has-residents-asking-questions/ // Many projects in the area up for approval: https://www.pinalcentral.com/maricopa_monitor/news/solar-applications-bombard-pinal-county/article_548cb27e-5a8e-11ef-8df2-cbef43f2ee37.html?utm_campaign=blox&utm_source=facebook&utm_medium=social&fbclid=IwY2xjawF7gNVleHRuA2FlbQIxMQABHWhjkBDsnw1Wn3W-c5OcwL-tR7Ggy1lBppW9Nwh_aFXpUJsIsTc0Uj6wlw_aem_bOVh2rKUdvrOrHXC42CINA | Helping GL with turnout - CROP & AEJ ads
Jackson County Wind | Ordinance | Onshore Wind | Jackson County | Pending |  | 19097 | IA | Jackson County Board of Commissioners |  |  | GoodPower | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-18 | 2024-11-18 |  | Digi + P2P | TRUE | TRUE | Awaiting results of hearing on 11/18. | 2024-11-19 | 11535 | 1361 | 400 | 27 | 20 | 16 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Halifax County Solar | Ordinance | Solar | Halifax County | Loss |  | 51083 | VA | Halifax County Board of Commisioners |  |  | GoodPower | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County passed a very restrictive solar ordinance and lowered density cap from 5% to 3%. Landscape is tough for utility-scale development moving forward | 2024-11-19 | 9881 | 1137 | 200 | 28 | 30 | 20 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cass County Solar | NextEra Energy | Solar | Cass County | Loss |  | 31025 | NE | Cass County Board of Commissioners |  |  | GoodPower | Project | Public Hearing | 265 | 0.265 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County DENIED permit on Feb 14 | 2025-03-03 | 28331 | 3521 | 662 | 80 | 24 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | https://rivercountry.newschannelnebraska.com/story/52367495/county-rejects-cass-county-solar
Bright Leaf & Swift Creek Solar + BESS | Multiple Developers | Solar + BESS | Edgecombe County | Win |  | 37065 | NC | Edgecombe County Board of Commissioners |  |  | GoodPower | Project | Public Comment Period | 192 | 0.192 |  | 2024-12-02 | 2024-12-02 |  | Digi + P2P | TRUE | TRUE | Special use permits DENIED at meeting on 12/2. Connect with devs on any next steps when the current moratorium period is over. Devs appealed to Superior court which ruled the County must issue the CUP. County complied in June 2025 switching from a loss to a win. Bright Leaf SUP application (2024) Swift Creek Solar + BESS application (2024) | 2025-08-04 | 31098 | 3437 | 1975 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | https://cms5.revize.com/revize/edgecombenc/6.%20Minutes%20_June%202%202025_FINAL.pdf | Minutes from December 12 Denial
Surry County BESS | Clenera | BESS | Surry County | Win |  | 51181 | VA | Surry County Board of Commissioners |  |  | GoodPower | Ordinance | Public Hearing | 400 | 0.4 |  | 2024-12-16 | 2025-01-27 | Cont. from Dec hearing | Digi + P2P | FALSE | TRUE | Running second rnd of ads for the continued hearing on 1/27 | 2025-01-13 | 316782 | 24825 | 10643 | 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
Paddlefish Solar | EDF Renewables | Solar | Huntington County | Active |  | 18069 | IN | Huntington County Board of Commissioners |  | Project falls in two counties so needs approval from both | GoodPower | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2024-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298.5 | 244.5 | 0 | 5.5 | 0 | 0 | 0 | https://www.huntingtoncountytab.com/articles/news/county-commissioners-take-a-vote-on-solar-zoning-ordinance-revisions/ https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Tough ordinance reviewed by planning commision in May 2025. Commissioners will review next. Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
Paddlefish Solar | EDF Renewables | Solar | Wells County | Active |  | 18179 | IN | Wells County Council |  | Project falls in two counties so needs approval from both | GoodPower | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2024-10-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 298.5 | 244.5 | 0 | 5.5 | 0 | 0 | 0 | https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
Hope Hull Solar | Silicon Ranch | Solar | Montgomery County | Win | Montgomery | 1101 | AL | City of Montgomery Board of Adjustment |  |  | GoodPower | Project | Public Hearing | 80 | 0.08 |  | 2024-11-21 | 2025-01-16 |  | Digi + P2P | TRUE | TRUE | Final approval granted by Montgomery County Board of Adjustment on 1/16! | 2025-01-16 | 43527 | 7649 | 3423 | 159 | 201 | 7031 | 5768 | 0 | 525 | 0 | 0 | 53 | 78 | 12 | 90
Eastern Cottontail Solar | EDF Renewables | Solar | Fairfield County | Win |  | 39045 | OH | Ohio Power Siting Board |  |  | Greenlight | Project | Public Hearing | 220 | 0.22 | Scripts | 2025-01-27 | 2025-01-27 |  | Digi + P2P | FALSE | TRUE |  | 2025-01-16 | 166275 | 23556 | 10175 | 399 | 0 | 388 | 382 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
Schnebly Coulee Solar | Invenergy | Solar | Kittitas County | Pending |  | 53037 | WA | Kittitas County Board of Commissioners | Kittitas County Hearing Examiner | Hearing examiner hosts public hearing, makes recommendation. Board of Commissioners has ultimate authority | Greenlight | Project | Volunteer Open House | 90 | 0.09 | SUP approved 3/10/25 Notice of Decision | 2024-12-18 |  |  | Peer to Peer only | FALSE | TRUE | A second round of text and phonebanking support provided in Feb 2025 | 2024-12-17 | 0 | 0 | 0 | 0 | 0 | 208 | 0 | 0 | 108 | 19 | 0 | 13 | 8 | 2 | 10
Sussex County Offshore Wind Project | Overall | Offshore Wind | Sussex County | Withdrawn |  | 10005 | DE | Bureau of Ocean Energy Managerment | Deleware DNREC / Sussex City Council | BOEM grants offshore licences and authority. DNREC and City Council regulate onshore construction, like substation and cables | Greenlight | Project | Public Hearing | 0 | 0 |  | 2024-12-10 |  |  | Peer to Peer only | TRUE | FALSE |  | 2024-11-28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Rancho Viejo Solar | AES | Solar + BESS | Santa Fe County | Win |  | 35049 | NM | Santa Fe County Board of Commissioners |  |  | Greenlight | Project | Public Hearing | 144 | 0.144 | GL Campaign | 2024-02-05 | 2025-08-12 |  | Digi + P2P | TRUE | TRUE | Santa Fe Planning Commission voted (6-1) to APPROVE the Conditional Use Permit yesterday. Parties have 30 days to appeal the Planning Commission’s decision to the County Commission. Opposition groups appealed. Commissioners hearing on 8/11-/12 | 2025-07-24 | 43549 | 8424 | 2311 | 447 | 5142 | 2442 | 2010 | 0 | 1350 | 501 | 0 | 68 | 162 | 5 | 167
Hesperus Solar | Primergy | Solar + BESS | La Plata County | Withdrawn |  | 8067 | CO | La Plata County Board of Commissioners |  |  | Longitudinal | Project | Project Hearing | 155 | 0.155 | News Article |  | 2024-10-29 |  |  | FALSE | FALSE | The application for a 1,900-acre solar project has been deemed withdrawn by county planners, although the developer has stated an intent to resubmit the application. | 2024-11-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prairie Power Solar Farm | Prairie Power Inc | Solar | Sangamon County | Pending |  | 17167 | IL | Sangamon County Board of Commissioners |  |  | Longitudinal | Project | Pre Application | 200 | 0.2 |  |  |  |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Soul City Solar Project | Apex Clean Energy | Solar | Hinds County | Win |  | 28049 | MS | Hinds County Board of Supervisors |  |  | Longitudinal | Project | Project Approved | 396 | 0.396 | News Article |  | 2024-06-18 |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Libra Solar Project | Arevia Power | Solar + BESS | Mineral County | Win |  | 32021 | NV | Bureau of Land Management | Mineral County | Project is sited on BLM land. BLM will issue approval. Mineral County will issue construction permits. | Longitudinal | Project | Project Approved | 700 | 0.7 | News Article | 2024-09-09 | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Greenlink West Transmission Project | NV Energy | Transmission |  | Win |  |  | NV | Bureau of Land Management | Department of Energy |  | Longitudinal | Project | Project Approved | 0 | 0 | News Article |  | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dry Lake East Energy Center | NextEra | Solar + BESS | Clark County | Win |  | 32003 | NV | Bureau of Land Management |  |  | Longitudinal | Project | Project Approved | 800 | 0.8 | News Article |  | 2024-08-30 |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blue Ridge Solar | Recurrent Energy | Solar | Pittsylvania County | Win |  | 51143 | VA | Pirttsylvania County Board of Zoning Appeals |  |  | Longitudinal | Project | Project Approved | 150 | 0.15 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michaux Solar | Dominion Energy | Solar | Henry County | Win |  | 51089 | VA | Henry County Board of Zoning Appeals |  |  | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Michaux Solar | Dominion Energy | Solar | Pittsylvania County | Win |  | 51089 | VA | Pittsylvania County Board of Zoning Appeals |  |  | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grand Junction Solar | Alliant Energy | Solar + BESS | Greene County | Win |  | 19073 | IA | Greene County Board of Adjustment |  |  | Longitudinal | Project | Project Approved | 150 | 0.15 | News |  |  |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Split Rail Solar | Ameren | Solar | Warren County | Win |  | 29219 | MO | Warren County Board of Commissioners | Missouri Public Service Commission | MO PSC gives regulatory approval for development. County has ultimate permiting authority. | Longitudinal | Project | Project Approved | 300 | 0.3 | News Article |  | 2024-03-22 |  | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Badger Hollow Wind | Invenergy | Onshore Wind | Iowa County | Win |  | 55049 | WI | Wisconsin Public Service Commission |  |  | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-05-02 | 2nd round of public comments end on 5/2/25 | Digi + P2P | TRUE | TRUE | The second public comment period for Badger Hollow Wind is now open. Please submit comments to the PSCW in support of Badger Hollow. The docket is now open for public comments and will close on May 2, 2025. | 2025-04-21 | 321109 | 112817 | 38824.5 | 4939.5 | 35749.5 | 22541 | 18779 | 0 | 0 | 0 | 0 | 310.5 | 0 | 0 | 0 |  |  |  | 9827-CE-100
Badger Hollow Wind | Invenergy | Onshore Wind | Grant County | Win |  | 55043 | WI | Wisconsin Public Service Commission |  |  | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-05-02 | 2nd round of public comments end on 5/2/25 | Digi + P2P | TRUE | TRUE | The second public comment period for Badger Hollow Wind is now open. Please submit comments to the PSCW in support of Badger Hollow. The docket is now open for public comments and will close on May 2, 2025. | 2025-04-21 | 321109 | 112817 | 38824.5 | 4939.5 | 35749.5 | 22541 | 18779 | 0 | 0 | 0 | 0 | 310.5 | 0 | 0 | 0 |  |  |  | 9827-CE-100
Uplands Wind | Pattern Energy | Onshore Wind | Lafayette County | Pending |  | 55065 | WI | Wisconsin Public Service Commission |  |  | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2024-12-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uplands Wind | Pattern Energy | Onshore Wind | Iowa County | Pending |  | 55049 | WI | Wisconsin Public Service Commission |  |  | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2024-12-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Uplands Wind | Pattern Energy | Onshore Wind | Grant County | Pending |  | 55043 | WI | Wisconsin Public Service Commission |  |  | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2024-12-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mount Vernon BESS | NextEra | BESS | Skagit County | Win |  | 53057 | WA | Skagit County Hearing Examiner |  |  | GoodPower | Project | Public Hearing | 200 | 0.2 | Hearing Announcement | 2024-12-20 |  |  | Digi + P2P | FALSE | TRUE | Project approved. Update May 2025: Town of Mount Vernon has issued a 1-yr moratorium on BESS while they draft new regulations | 2025-07-25 | 39408 | 5897 | 931 | 157 | 107 | 64 | 53 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0
Gabriel Solar | Gabriel Energy / Energix US | Solar + BESS | Prince Edward County | Loss |  | 51147 | VA | Prince Edward County Board of Commissioners |  |  | GoodPower | Project | Public Hearing | 200 | 0.2 | Hearing Documents | 2024-12-17 | 2025-02-11 |  | Digi + P2P | FALSE | TRUE | Public hearing of county commissioners on 2/11 | 2025-01-13 | 226826 | 37131 | 5302 | 1290 | 32 | 9 | 6 | 0 | 624 | 288 | 0 | 8 | 1 | 0 | 1
Keystone Wind | RWE | Onshore Wind | Pawnee County | Active |  | 40117 | OK | Oklahoma Corporation Commission |  |  | RWE | Project | Pre Application | [6 empty] | Digital ads only | FALSE | TRUE | Early stages of planning - lease agreements in progress | 2025-06-06 | 375176 | 120729 | 40233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Keystone Wind | RWE | Onshore Wind | Payne County | Active |  | 40119 | OK | Oklahoma Corporation Commission |  |  | RWE | Project | Pre Application | [6 empty] | Digital ads only | FALSE | TRUE | Early stages of planning - lease agreements in progress | 2025-06-06 | 375176 | 120729 | 40233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Prairie Wolf Wind | RWE | Onshore Wind | Hughes County | Active |  | 40063 | OK | Oklahoma Corporation Commission |  |  | RWE | Project | Planning Meeting | 119.5 | 0.1195 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-04-21 | 178594.5 | 58082 | 22184.5 | 52 | 0 | 0 | 0 | 0 | 12.5 | 9 | 0 | 0 | 0 | 0 | 0
Prairie Wolf Wind | RWE | Onshore Wind | Okfuskee County | Active |  | 40107 | OK | Oklahoma Corporation Commission |  |  | RWE | Project | Planning Meeting | 119 | 0.119 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-04-21 | 178594.5 | 58082 | 22184.5 | 52 | 0 | 0 | 0 | 0 | 12.5 | 9 | 0 | 0 | 0 | 0 | 0
Iron Pine Solar | Swift Current Energy | Solar | Pine County | Win |  | 27115 | MN | Minnesota Public Utilities Commission |  |  | GoodPower | Project | Project Hearing | 325 | 0.32 |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | MN PUC granted permit on July 3, 2025. Project approved. | 2025-07-09 | 57786 | 14393 | 4549 | 407 | 7259 | 7284 | 6424 | 0 | 884 | 575 | 0 | 86 | 30 | 0 | 30 |  |  |  | IP7114/GS-23-414 (Site Permit) and IP7114/TL-23-415 (Route Permit) OAH Docket Number: 22-2500-40198
Westfield Battery Ordinance | Jupiter Power | BESS | Hampden County | Pending |  | 25013 | MA | Westfield City Council |  |  | GoodPower | Ordinance | Public Comment Period |  |  | Still listed as indevelopment as of 11/18/25 Keystone Wind |  | 2025-02-06 |  | Digi + P2P | TRUE | TRUE | City council considering strict rules to stifle BESS construction. Council appears united in opposition of BESS and is intervening in Jupiter's application for state approval. | 2025-04-21 | 36565 | 8134 | 99 | 80 | 0 | 0 | 0 | 0 | 665 | 477 | 0 | 0 | 23 | 0 | 23
Bolivar Onshore Wind Ordinance | Steelhead/Vestas | Onshore Wind | Bolivar County | Potential |  | 28011 | MS | Bolivar County Board of Commissioners |  |  | GoodPower | Ordinance | Public Hearing |  |  |  |  | 2025-02-17 |  |  | TRUE | TRUE |  | 2025-02-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bolivar Onshore Wind Ordinance |  | Onshore Wind | Goshen County | Pending |  | 56015 | WY | Goshen County Board of Commissioners |  |  | GoodPower | Ordinance | Public Hearing |  |  |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | Commissioners considering appendix on wind permitting to set guidelines | 2025-02-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lee Onshore Wind & Solar Ordinance |  | Onshore Wind & Solar | Lee County | Withdrawn |  | 19111 | IA | Lee County Board of Supervisors |  |  | GoodPower | Ordinance | [5 empty] | 2025-07-29 |  | Organizing only | TRUE | TRUE | Board of Commissioners has been drafting new wind and solar regulations. Likely target date of April 2025~ | 2025-02-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New York Rapid Act |  | Onshore Wind & Solar |  | Withdrawn |  |  | NY | Governor Kathy Hochul | NY State Assembly / NY State Senate | This was a bill that passed state senate and house and was signed by governor | GoodPower | Legislation | Public Hearing |  |  | Hearing Details | 2025-02-19 | 2025-07-29 |  | Organizing only | TRUE | FALSE | The NY Department of Public Service is holding a public hearing regarding the RAPID act which gives the state broader control to review projects. | 2025-02-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Daviess Solar Ordinance |  | Solar | Daviess County | Potential |  | 21059 | KY | Daviess County Fiscal Court |  |  | Laurie | Ordinance | Public Hearing |  |  |  | 2025-02-20 |  |  | Digi + P2P | TRUE | TRUE | HOLD: Fiscal Court enacted a 12 month moratorium on rewewables at their first reading of the potential new ordinance. Enacted ordinance for 1000 ft setback. | 2025-03-03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surprise BESS Ordinance |  | BESS | Maricopa County | Potential | Surprise | 4013 | AZ | City of Surprise City Council |  |  | AZ Siting Table | Ordinance | Public Comment Period | [6 empty] | Digi + P2P | TRUE | TRUE | The city is likely to schedule a public hearing soon. It is a good time for BESS support messages ahead of the hearings | 2025-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Livingston Energy Storage | Vesper Energy | BESS | Otsego County | Potential |  | 26137 | MI | Otsego County or Livingston Township | Michigan Public Services Commission | This one is complex. MI's CREO law requires local jurisdictions to adopt compatible energy ordinances that meet or exceed state standards. Otsego County nor Livingston Township have done this. If certain criteria are met, the developer can opt to apply directly with the state in which case state would have siting authority. | GoodPower | Project | Pre Application | 300 | 0.3 |  |  |  |  | Digital ads only | FALSE | TRUE | Ground softening ads. A nice way to break in with a new developer. The developer just hosted the first of a series of community meetings. No application has been submitted yet. | 2025-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hanover BESS | Northland Power | BESS | Chautauqua County | Withdrawn | Hanover | 36013 | NY | Town Board of Hanover |  |  | GoodPower | Project | Pre Application | 250 | 0.25 |  | 2025-02-24 |  |  | Digi + P2P | TRUE | TRUE | Town Board public hearing to gauge public input regarding the presence of such a facility in the town. | 2025-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yellow Barn Solar | CS Energy | Solar | Tompkins County | Win |  | 36109 | NY | New York State Office of Renewable Energy Siting (ORES) |  |  | GoodPower | Project | Public Comment Period | 160 | 0.16 |  |  | 2025-02-20 |  | Peer to Peer only | TRUE | TRUE | Public hearing for Yellow Barn Solar. The state has issued a draft permit for the project in December. One of the last remaining hurdles is local input, though approval is ultimately with the state. It is important to show local support for a project like this so the state sees it is not just opposition. | 2025-02-20 | 0 | 0 | 0 | 0 | 228 | 64 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grass Lake Solar | NextEra | Solar | Grass Lake Township | Potential | Grass Lake Township | 26075 | MI | Grass Lake Township Planning Commission | Michigan Public Services Commission | Township is in the process of drafting a CREO-compliant ordinance. If they pass it, they'll maintain siting authority. | GoodPower | Ordinance | Public Hearing | 100 | 0.1 |  |  |  |  | Digi + P2P | TRUE | TRUE | Town supervisor/trustees to hold public hearing by end of month of Feb - Decision to come by early March on mutually agreed upon ordinance with NextEra | 2025-02-20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Frontiers Solar Park | EDPR | Solar | Breckinridge County | Win |  | 21027 | KY | Breckinridge County Fiscal Court |  |  | Laurie | Project | Public Comment Period | 100 | 0.1 | Approved by PSC on May 2 (page 34) |  | 2025-03-20 |  | Digital ads only | FALSE | TRUE | PSC approved the project on May 2, 2025 and issued construction permits valid for 3 years. Note: EDPR's revised site plan was denied as a condition of approval. Unclear what this means for the project | 2025-05-18 | 61116 | 11570 | 11432 | 636 | 8704 | 8760 | 7090 | 0 | 0 | 0 | 0 | 110 | 0 | 0 | 0 |  | Project Approved by PSC on May 2, 2025
Darden Energy Center | Intersect Power | Solar + BESS | Fresno County | Withdrawn |  | 6019 | CA | California Energy Commission |  | Under state law AB 205, large-scale projects can use a new "opt-in" certification program, going straight to the state for expedited approval and bypassing local approvals |  | Project | Public Comment Period | 6100 | 6.1 |  |  | 2025-04-21 |  |  | FALSE | FALSE | This is the first project to move this far in CA’s new “opt-in” regulatory process for largescale renewable projects which dramatically speeds up reviews and approvals for large scale projects. Project must receive a final determination within 270 days from application deemed complete. | 2025-03-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allen County Solar Ordinance |  | Solar | Allen County | Pending |  | 18003 | KY | Allen County Fiscal Court |  | Ordinance Adopted | Solar United Neighbors Indiana | Ordinance | Public Hearing |  |  |  |  | 2025-06-12 |  | Digi + P2P | TRUE | TRUE | Public hearing scheduled for 6/12/25 | 2025-06-05 | 135877 | 18964 | 859 | 551 | 1083 | 338 | 269 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0
Valley Farms Energy Storage | NextEra | BESS | Pinal County | Withdrawn |  | 4021 | AZ | Pinal County Board of Supervisors |  |  | AZCE | Project | Public Hearing | 400 | 0.4 |  |  | 2025-03-31 |  |  | FALSE | FALSE | Project was just recommended for denial last week by the planning commission (5-2 vote). In 4-6 weeks it will be heard by the Board of Supervisors. Supervisors REJECTED project. ACE did not participate | 2025-07-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ironwood Transmission Line | Energy West (NextEra) | Transmission | Yuma County | Potential |  | 4027 | AZ | Arizona Corporation Commission | Yuma County Board of Supervisors | ACC handles permitting of transmission in AZ. However for portions on private land within the County, Yuma County Board has permitting authority |  | Project | Developer Community Meeting | 3000 | 3 |  |  | 2025-04-01 |  | Digi + P2P | TRUE | TRUE | Pre-application, upcoming intervention point. Developer community meeting held by Energy West upcoming. Multi-state project that may traverse BLM land, number of regulatory approvals needed as this will requre permits from both state and federal agencies including CEQA and NEPA approvals. Expected to take 4 years to get all regulatory approvals. | 2025-03-04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Antlers Road Solar | RWE | Solar | Mecklenburg County | Pending |  | 51117 | VA | Meckleburg County Board of Supervisors |  |  | GoodPower | Project | Public Hearing | 90 | 0.09 | Project denied. Developer currently enaged in lawsuit against county. Still in litigation as of 11/18/25 |  |  |  | Organizing only | TRUE | FALSE | In April, the Planning Commission voted to reject the project. It will be heard next by the Board of Commissioenrs where it is expected to be denied. RWE in ilitigation with the County for wrongfully denying the project when it first applied for permits. | 2025-07-23 | 0 | 0 | 0 | 0 | 28 | 22 | 22 | 0 | 2372 | 1734 | 0 | 0 | 5 | 0 | 5
Flickertail Solar | Savion | Solar | Richland County | Win |  |  | ND | North Dakota Public Service Commission |  |  | GoodPower | Project | Public Hearing | 300 | 0.3 | Richland County, ND - Flickertail Solar - Planning Doc | 2025-03-25 |  |  | Digi + P2P | TRUE | TRUE | Flickertail Solar is a 300MW solar project by Savion (Shell subsidiary) in development in Richland County, ND (Abercrombie, specifically). The project is approved on a state level, as it is over 50MW in size. March 25th is the date of the ND PSC’s public hearing to determine approval of the siting permit required to move forward with the project. | 2025-04-21 | 103822 | 7153 | 4122 | 190 | 0 | 0 | 0 | 0 | 680 | 415 | 0 | 0 | 1 | 0 | 1
Gibson Solar | Open Road Renewables | Solar | King George County | Loss |  | 51099 | VA | King George Board of Supervisors |  |  | GoodPower | Project | Public Hearing | 134 | 0.134 | King George County, VA - Gibson Solar Project - Planning Doc | 2025-04-01 |  | BOC denied July 2025 | Digi + P2P | TRUE | TRUE | Open Road renewables is developing a 134 MW solar project in King George County, VA, known as Gibson Solar. The approval for this project lies with the county, with 1 step remaining: 1.) Planning Commission Recommendation (The commission ultimately voted to support the project, emphasizing the need for careful monitoring and adherence to conditions set forth in the zoning ordinance.) 2.) Board of Supervisors next hearing for this project will be held on April 1st by the Board of Supervisors. | 2025-04-21 | 4866 | 706 | 114 | 22 | 19 | 9 | 9 | 1 | 2324 | 2072 | 0 | 0 | 11 | 0 | 11
Midwater Energy Storage | Spearmint Energy | BESS | Freeborn County | Pending |  | 27047 | MN | Minnesota Public Utilities Commission |  |  | GoodPower | Project | Public Comment Period | 150 | 0.15 | Freeborn County MN - Midwater Energy Storage BESS - Planning Doc as of 11/18/25 Still waiting for decision | 2025-04-21 |  |  | Digi + P2P | TRUE | TRUE | The Midwater Energy Storage project is at the first stage in the Minnesota state review process. Open comment period is accepting comments regarding suggestions for the Environmental Assessment (EA). After the EA is complete, there will be public hearings and another comment period to accept general support/opposition comments on the project. | 2025-04-21 | 70714 | 20442 | 9668 | 1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 0
Little Prairie Hybrid | BayWa r.e. | Solar + BESS | Champaign County | Win |  | 17019 | IL | Champaign County Board of County Commissioners |  |  | Greenlight | Project | Public Hearing | 270 | 0.27 | https://us.baywa-re.com/en/americas-cases/little-prairie | 2025-04-10 |  | https://citizenportal.ai/articles/2977427/Champaign-County/Illinois/Champaign-County-considers-zoning-approval-for-Little-Prairie-Solar-Project | Peer to Peer only | TRUE | FALSE | Champaign County, IL considering zoning approval | 2025-04-21 | 0 | 0 | 0 | 0 | 0 | 338 | 338 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yellow Rosebush | Savion | Solar + BESS | Wasco County | Pending |  | 41065 | OR | Oregon Energy Facilities Siting Council (EFSC) |  |  | Greenlight | Project | Public Hearing | 800 | 0.8 | https://www.oregon.gov/energy/facilities-safety/facilities/Pages/YRB.aspx |  |  | TBD | Peer to Peer only | TRUE | FALSE | No set milestones currently, we are estimating there will be some in April. - GL | 2025-04-21 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fort Watt BESS | Cypress Creek | BESS | Tarrant County | Loss | Kennedale | 48439 | TX | City of Kennendale City Council |  |  | Greenlight | Project | Public Hearing | 255 | 0.255 |  | 2025-04-24 | 2025-05-20 |  | Peer to Peer only | TRUE | FALSE | Planning & Zoning approved the project on 4/24/25, City Council denied the project on 5/20. | 2025-07-25 | 0 | 0 | 0 | 0 | 0 | 170 | 170 | 7 | 178 | 21 | 0 | 0 | 0 | 0 | 0
San Luis Obispo OSW | CET | Offshore Wind | San Luis Obispo County | Pending |  | 68154 | CA | California State Lands Commission | California Coastal Commision, Bureau of Ocean Energy management, San Luis Obispo County Board of Directors | California State Lands Commission is the CEQA-designated lead agency. However, the ultimate approver is unclear. Requires multiple state and federal agencies as well as local approvals from the County | Greenlight | Project | Project Hearing |  |  |  | 2025-03-25 |  |  | Peer to Peer only | TRUE | FALSE |  | 2025-05-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757 | 682 | 0 | 20 | 9 | 0 | 9
Buffalo Burr Solar + BESS |  | Solar + BESS | Pueblo County | Potential |  | 8101 | CO | Pueblo County Board of County Commissioners |  |  | Greenlight | Project | [8 empty] | FALSE | FALSE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Developer has decided to slow down, moving this to Q4 2025 (per Greenlight)
Purple Sage BESS | RWE | BESS | Collin County | Active | Weston | 48085 | TX | City of Weston City Council |  | Half of the project is in extrajudicial territory in the County. Developer has been informing County, but don't believe County has any zoning authority over this land | GoodPower | Project |  | 300 | 0.3 | Still waiting for approval as of 11/18 |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-06-06 | 554826 | 242629 | 16521 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Whitewater Solar | Range Power | Solar | Jefferson County | Win |  |  | WI | Wisconsin Public Service Commission |  |  | Wisconsin Table | Project | Public Comment Period | 180 | 0.18 | Planning Commission hearing is July 28, 2025 (found July 25) |  |  |  | Peer to Peer only | TRUE | FALSE | WI PSC public comment period | 2025-07-14 | 0
Isabelle Creek Solar | AES | Solar | Pierce County | Potential | Hartland | 55093 | WI | Pierce County Board of Supervisors |  |  | GoodPower | Project |  | 75 | 0.075 | [5 empty] | FALSE | FALSE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Developer slowing down - to revisit October 2025
Massey BESS | Cypress Creek Renewables | BESS | Harris County | Active | Baytown | 48201 | TX | City of Baytown Texas |  |  | Greenlight | Project | Project Hearing | 200 | 0.2 | This was approved by city council 9/11/25 |  |  |  | Peer to Peer only | TRUE | FALSE
Cobia Solar | Geenex | Solar | Decatur County | Loss |  | 18031 | IN | Decatur County Board of Zoning Appeals |  |  | Indiana Table | Project | Public Hearing | 600 | 0.6 |  | 2025-08-06 |  |  | Peer to Peer only | TRUE | FALSE |  |  | 0 | 0 | 0 | 0 | 14 | 7 | 6 | 0 | 1150 | 546 | 0 | 6 | 0 | 0 | 0
Burr Oak Solar | Leeward Renewable Energy | Solar | Dekalb County | Win |  | 18033 | IL | Dekalb County Board of Commissioners |  |  | GoodPower | Project | Public Hearing | 300 | 0.3 | County Commissioners APPROVED project. Planning and Zoning commission tentatively scheduled August 27 - awaiting official date. BOC will hear it 1 month after PZ. | 2025-08-27 |  | Tentatively scheduled | Digi + P2P | TRUE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 2555 | 0 | 25 | 6 | 0 | 6
Sloopy Solar Energy Center | Invenergy | Solar | Clark County | Active |  | 39023 | OH | Ohio Power Siting Board |  |  | GoodPower | Project | Pre Application | 180 | 0.18 | This is being supported by the Ohio Siting Table. First public meeting was held July 8. Anticipated OPSB application submission later this year. |  |  |  | Digital ads only | FALSE | TRUE |  |  | 195508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Compass Energy Storage | Engie North America | BESS | Orange County | Potential | San Juan Capistrano |  | CA | [6 empty] | 250 | 0.25 | [5 empty] | FALSE | FALSE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wood Duck Solar | Geenex | Solar | Barren County | Active |  | 21009 | KY | Kentucky PSC |  |  | GoodPower | Project | Project Hearing | 100 | 0.1 | Construction approved Nov 14 | 2025-07-15 | 2025-10-02 | July 15 public hearing over 60 people attended. 17 individuals spoke, including 14 opposed and 3 in favor. Written comments still being accepted. case number (2024-00337) email comments to: psc.comment@ky.gov N | Digi + P2P | TRUE | TRUE | Docket is open for public comment through October 2 |  | 164335 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sylvan Solar | AES | Solar | Newaygo County | Active | Freemont | 26123 | MI | Unclear |  | Freemont, MI recently passed revised solar ordinace set a max 500 acre size for solar projects. Unclear of exact siting of Sylvan Solar. This project is much larger than 500 acres. From Landgate, appears one or two of the parcels are in Fremont's jurisdiction. The rest are in the town of Newaygo. Doesn't appear Newaygo Township has an ordinance which means it would defer to state guidelines per CREO | GoodPower | Project | Pre Application | 220 | 0.22 | Public hearing scheduled: November 25, 2025 at 7 p.m. – public hearing on Sylvan Solar’s CUP request at Garfield Township Hall, 7190 Bingham, Newaygo. Written comments accepted until noon on Nov 25. https://www.nearnorthnow.com/news/solar-farm-coming-to-garfield |  |  |  | Digital ads only | FALSE | TRUE |  |  | 61287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mission Clean Energy Solar Project | Mission Clean Energy | Solar | Dakota County | Active |  | 31043 | NE | Dakota County Board of Commissioners |  |  | GoodPower | Project | Public Hearing | 250 | 0.25 | Project has been approved as of 9/15/25 |  | 2025-08-19 | BOC has not yet set a date | Digi + P2P | FALSE | TRUE |  |  | 59195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Taro Solar | NOVI Energy | Solar | Charlotte County | Active |  | 51037 | VA | Charlotte County Board of Supervisors |  |  | GoodPower | Project | Public Hearing | 140 | 0.14 | Close session board meeting held 11/18/25, BOS Public hearing on CUP decision set for 12/10/25 (tentative) | 2025-08-21 | 2025-08-21 | BOS date TBD | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hyco Solar | Cypress Creek Renewables | Solar | Person County | Active |  | 37145 | NC |  |  |  | Greenlight |  |  | 80 | 0.08 | Oct 24, 2025 – Cypress Creek issues “Project Postponement” update, confirming they have requested a postponement of the Person County solar ordinance text-amendment vote related to Hyco Solar and will continue outreach before any vote moves forward. |  |  |  |  | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Union Township Solar Ordinance | RWE | Solar | Erie County | Win | Union Township | 42049 | PA | Union Township Board |  |  | REFA | Ordinance | Project Hearing |  | 0 | Board meeting 8/29 to discuss potential shadow ban ordinance. Flagged by REFA as one of their members in the township has a 1000 acre lease with RWE. In partnership with Greenlight. | 2025-08-29 | 2025-08-29 |  | Peer to Peer only | TRUE | TRUE |  |  | 340063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 160 | 0 | 5 | 0 | 0 | 0
Lakeside Solar Project | Geronimo | Solar | Muskegon | Active |  | 26121 | MI | Unclear - targeting County |  | White River and Montague Townships want to claim siting authority but their new ordinances may be more restrictive than state CREO | GoodPower | Project | Pre Application | 150 | 0.15 | Final decision has to be made by Jan 14, 2026, special meeting proposed for Dec 2 in order to set date for a final vote on the project. Public comment window open until decision is made. |  |  |  | Digital ads only | FALSE | TRUE |  |  | 407394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Key Capture 1 | Key Capture | Solar | Washtenaw County | Active | Salem Township | 26161 | MI | Saline Township |  | Township has a CREO-aligned ordinance so should have full siting authority | Greenlight | Project | Pre Application | 100 | 0.1 | Project in the works since 2021. With the new CREO, township has in place, and a workable local ordinance - 600 ft setbacks. There is local backlash to the scale of the project, viewshed perceptions, and concerns about changing the rural landscape |  |  |  | Digi + P2P | TRUE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grifton Solar | Hexagon Energy | Solar | Pitt County | Active |  | 37147 | NC | Pitt County | NC DEQ | County has approved. Now a CPCN is needed from the state. | GoodPower | Project | Public Comment Period | 80 | 0.08 | This project has been approved as of 8/19/25 | 2025-08-19 | 2025-09-02 | Comment deadline | Peer to Peer only | TRUE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1285 | 992 | 0 | 46 | 0 | 0 | 0
Louis Creek Solar | Allium Renewable Energy | Solar | Iroquois | Active |  | 17075 | IL | Iroquois County Board |  |  | GoodPower | Project | Public Hearing | 60 | 0.06 | The Iroquois County Board sent the conditional use permit request back to the Zoning Board of Appeals (ZBA) for further review instead of approving or denying it outright. That means the ZBA will hold another hearing and issue a revised recommendation before the board votes again (within 1-2 months) |  |  | TBD | Digital ads only | FALSE | TRUE |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Grass River Solar | CS Energy | Solar | St. Lawrence | Active |  | 36089 | NY |  |  |  | GoodPower | Project |  | 80 | 0.08 | Preapplication | [8 empty] | 177226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Allium Hybrid | Longroad | Solar + BESS | San Benito County | Active |  | 6069 | CA |  |  |  | GoodPower | Project |  | 220 | 0.22 | No approval as of 11/19/2025 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dawn Break Solar | Ranger Power | Solar | Waushara County | Active |  | 55137 | WI |  |  |  | WI table | Project |  | 180 | 0.18 | No approval as of 11/19/2025 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Town of Ulster BESS | Terra-Gen | BESS | Ulster County | Active |  | 36111 | NY | Town Board of Ulster, NY |  |  | GoodPower | Project | Project Hearing | 250 | 0.25 | The Town Board must decide on SEQRA determination (Positive or Negative Declaration). That decision will set the timeline for the first formal public comment/hearing period. Date not yet set, but next board meeting is Thursday Sept 18 (agenda items due the friday before) | 2025-09-18 | [7 empty] | 86130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Homer Grid BESS | Eolian | BESS | Washington County | Active |  | 31177 | NE | Washington County Board of Supervisors |  |  | GoodPower | Project | Public Hearing | 200 | 0.2 | Project still in preapproval, not yet docketed. The project mentioned in a BESS presentation at Aug 19 Lancaster County Board of Commisisioners meeting, but no formal public hearning has been scheduled. The last milestone was a public informational meeting Nov 2024 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
North Valley Energy Storage | Cypress Creek Renewables | BESS | Washoe County | Active | Reno | 32031 | NV | Reno City Council |  |  | NV table | Project | Public Hearing | 100 | 0.1 | September 2025 (potentially Sept 17) expected. Reno City Council votes. April 2025: Virtual Town Hall | 2025-09-17 | [7 empty] | 986555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Juniper Springs Solar + BESS | EDF Renewables | Solar + BESS | Apache County | Active |  | 4001 | AZ | Apache County Planning and Zoning |  |  | NV table | Project | Project Hearing | 1000 | 1 | Recap Aug 7: P&Z Public Meeting - decided to table for a bit to get answers to questions that came up (like local wildlife impacts) 2 Upcoming P&Z Hearings: Tentative Sept. 2 P&Z Hearing (12PM Work Session, 1PM Hearing) & One additional P&Z Hearing and Vote Comments to: planning@co.apache.az.us | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Silver Reef Solar | EDF Renewables | Solar + BESS | Pinal County | Active |  | 4021 | AZ | Pinal County Board of Commissioners |  |  | AZ table | Project | Public Hearing | 350 | 0.35 | October 16 - P&Z hearing testimony and vote November 19 - BOS hearing, testimony and vote Request for amendment for comp plan - County then will look at the requests all together. Go to P&Z and a citizen advosory committee for recommendation. Then BOS votes on it on November 19 | 2025-10-16 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Silver King Solar | Arevia Power | Solar + BESS | Pinal County | Active |  | 4021 | AZ | Pinal County Board of Commissioners |  |  | AZ table | Project | Public Hearing | 2200 | 2.2 | October 16 - P&Z hearing testimony and vote November 19 - BOS hearing, testimony and vote Request for amendment for comp plan - County then will look at the requests all together. Go to P&Z and a citizen advosory committee for recommendation. Then BOS votes on it on November 19 | 2025-10-16 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Downstream Solar Energy Center | Invenergy | Solar | Lonoke County | Active |  | 5085 | AR | Lonoke County Judge |  | The Lonoke County Judge is the key local permitting authority for siting/land use, while Arkansas DEQ and federal agencies issue environmental/construction permits. | GoodPower | Project |  | 300 | 0.3 | Lonoke County Judge Doug Erwin signed an agreement (on August 21, 2025) to approve the PILOT arrangement for the Keo solar project. While Lonoke County’s PILOT is already signed, residents and stakeholders still have a chance to weigh in — especially during Pulaski County’s upcoming decision meetings | [8 empty] | 120560 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Soda Mountain | Bechtel Corp. | Solar + BESS | San Bernardino | Active |  | 6071 | CA | California Energy Commission/BLM |  |  | GoodPower | Project |  | 600 | 0.6 | Project is seeking CA opt-in review (expedited 270-day state review) A public information & environmental scoping meeting was held August 29, 2025. There will be at least 2 more formal public comment windows as this advances through the process. Application deemed complete as of July 31, 2025 starting the 270-day clock. Project is on BLM land, so a NEPA is likely required. This and all BLM approvals must be completed wi | [8 empty] | 679429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Honeystone Solar | Enel | Solar + BESS | Cache County | Active |  | 49005 | UT |  |  |  | GoodPower | Ordinance |  | 225 | 0.225 | his is an ordinance amendment to allow for the rezoning and development of land for solar + BESS as there is currently no ordinance. Planning voted to approve - send to BOC (date TBD) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Champaign County BESS Ordinance |  | BESS | Champaign County | Active |  | 17019 | IL | Champaign County Board |  |  | GoodPower | Ordinance | Public Hearing |  | 0 | Ordinance adopted Generally pro-BESS | [8 empty] | 475470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Richland County Solar Moratorium |  | Solar | Richland County | Potential |  | 39141 | OH |  |  |  | OH CCEC | Moratorium | Solar Moratorium |  | 0 | A May 2026 ballot measure will allow residents to vote on whether to overturn the solar and win ban. On July 17, 2025, the Richland County Board of Commissioners unanimously passed a ban on large wind farms and large solar facilities in 11 of the county’s 18 townships (all unincorporated areas). | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tilton-Caitlin Solar | Earthrise | Solar | Vermillion County | Active | Town of Tilton | 17183 | IL | Town of Caitlin |  | On September 18, The Town of Tilton imposed a moratorium through June 1 while they update regs. Project comes within 1.5 miles of the Town ((IL law states towns have jurisdiction within this boundary). The Town of Caitlin has ultimate jurisdiction to review the SUP | GoodPower | Project | Pre Application | 188 | 0.188 | No formal application submitted yet. Early stage | [8 empty] | 250180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Musketeer Wind Energy | Invenergy | Onshore Wind & BESS | Vermillion County | Active |  | 17183 | IL | County Board |  |  | GoodPower | Project | Project Hearing | 300 | 0.3 | County wind and solar Committee unanimously approved the project on September 8. It will now move to the full County Board for a vote, likely in the next month or two (potentially October 14) Committee Approval - Recieved County Approval Oct 14 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Shawboro East Solar Project | Sunenergy1 | Solar | Currituck County | Active |  | 37053 | NC | NC Utilities Commission |  |  | GoodPower | Project | Public Hearing | 150 | 0.15 | Overview: Project is seeking CPCN from NC Utilities Commission. Hearing coming up on October 20 with public testimony. Appears project has received local approvals so this is the last step. | 2025-10-20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
City of Revere BESS Ordinance |  | BESS | Suffolk County | Active | Revere | 25025 | MA | City Council |  |  | GoodPower | Ordinance |  |  | 0 | Zoning Subcommittee tabled the BESS ordinance discussion citing fire and other concerns and the confusion over possible state movement on BESS regulation Local News Report | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Potentia-Viridi BESS | Obra Masetra Renewables | BESS | Alameda County | Active |  | 6001 | CA | CEC |  |  | GoodPower | Project | Public Comment Period | 400 | 0.4 | Going through state's expedited 270-day opt-in process. Comment period is open. CEC Docket | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Robin Energy Storage Project | Copenhagen Infrastructure Partners | BESS | Kenosha County | Active |  | 55059 | WI | Kenosha County Board of Supervisors |  | The approving authority for the Robin Energy Storage Project in Kenosha County is the Kenosha County Planning, Development & Extension Education Committee (PDEEC), plus the Kenosha County Board via its Planning & Development Division | GoodPower | Project | Pre Application |  | 0 | Unclear the project will enter permitting the last quarter of 2025 and first quarter of 2026, with construction starting in the second quarter of 2027 and operations starting in fourth quarter of 2028. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Macon County Solar Project | Doral Renewables | Solar | Macon County | Active |  | 29121 | MO |  |  | Early stage. MO law states that if a county does not have planning and zoning, no approvals are needed for development. No state siting board either. So project can move forward. Developer still needs road use agreements, PILOT etc with County and to build good-will. | GoodPower | Project | Pre Application | 208 | 0.208 | https://ktvo.com/newsletter-daily/macon-county-residents-voice-concerns-over-solar-project-at-public-meeting | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Olympus Solar | Invenergy | Solar | Muscatine County | Active |  | 19139 | IA | County Board |  |  | GoodPower | Project |  | 200 | 0.2 | Residents just learned about the project at the first open house. Very early stage. Local News : Open house | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Gypsum Peak Energy Storage | Vesper Energy | BESS | Van Buren County | Active |  | 26159 | MI | Michigan Public Service Commission | Columbia Township | MPSC is the ultimate siting authority. However, Columbia Township would issue the CUP if it has adopted a compliant ordinance under the new law. If Columbia Township hasn’t updated its ordinance (or denies a CUP), Vesper Energy can apply directly to the MPSC for approval | GoodPower | Project | Pre Application | 200 | 0.2 | Columbia Township recently hosted informational meetings and community panels; local residents circulated petitions; Groveland Township (different county, but same developer) approved a lease for another BESS project, showing Vesper is advancing multiple MI storage sites. No state-level MPSC docket has been filed yet | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kingwood Solar | Vesper Energy | Solar | Greene County | Active |  | 39059 | OH | Ohio Power Siting Board |  |  | OH CCEC | Project |  | 175 | 0.175 | Vesper awaiting ruling from Ohio Supreme Court - whether project should be re-considered. OPSB denied the project in 2023 citing public opposition. This case questions how much OPSB can consider local opposition. If they rule in Vesper favor, project will be re-heard by OPSB - unclear at what stage. In the interim, some landowners are getting cold feet from local opposition (well organized group of retired folks) | [8 empty] | 116809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blendon Township BESS | Key Capture | BESS | Ottawa County | Potential | Blendon Township | 26139 | MI |  |  |  | GoodPower | Project | Pre Application | 100 | 0.1 | Very early stage. No formal application submitted. FLAG: Landowner leasing property has ties to the Planning Commission. Chris Linsmeyer. Commissioner Jordan Decker - he is the person leasing the land Local News Youtube | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jackson County Solar Ordinance | NextEra | Solar | Jackson County | Active |  | 20085 | KS | Jackson County Commissioners |  |  | GoodPower | Ordinance | Public Hearing | 500 | 0.5 | NextEra is planning a 500 MW project in the County. Planning Commission is accepting public comments until October 2 on the Solar Ordinance. Notably the ordinance prohibits BESS, has 1000 ft setbacks from dwellings, and 2,000 acre project cap. The acreage cap would limit the size of the NextEra project. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wapello County Ordinance | Apex Energy | Onshore Wind & Solar | Wapello County | Active |  | 19179 | IA | Wapello County Commissioners |  |  | GoodPower | Ordinance | Public Comment Period | 200 | 0.2 | County has held 3 public meetings. They now begin the official readings of the ordinance at future meetings (TBD). The public comment window remains open. Apex Energy has a 200MW wind project waiting to apply. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bay Breeze Solar | AES | Solar | Jefferson County | Active |  | 36045 | NY |  |  |  | GoodPower | Project | Public Comment Period | 150 | 0.15 | Town of Lyme has enacted a solar moratorium. Does not appear it will impact the Bay Breeze project as it was submitted prior to moratorium. Approval is done by ORES. Public comment window open. Lots of negative comments | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Solano County BESS Ordinance | NextEra | BESS | Solano County | Active |  | 6095 | CA | Solano County Board of Supervisors |  |  | GoodPower | Ordinance | Public Comment Period |  | 0 | County is nearing the end of a 2-year moratorium (end January 26, 2026) while they crafted BESS regs. Unlike many other Counties that decided on an outright ban, Solano has thoughtfully crafted regulations that may encourage developers to seek County approval instead of the state-level opt-in process. Final ordinance draft will be shared soon and public hearing to follow. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Highland County BESS | NextEra | BESS | Highland County | Active |  | 39071 | OH | Highland County Comissioners |  |  | GoodPower | Project | Pre Application | 200 | 0.2 | Project was just introduced to Commissioners. No application submitted yet. More meetings to follow plus the official OPSB process. Project would enter into PILOT agreement with County, ensuring County funds regardless of tax changes at the state level. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Mission Clean Energy Solar Project | NextEra | BESS | Hampden County | Active |  | 25013 | MA |  |  | Town Council is opposed to the project. They are frustrated by new state regs that bring all projects above 100 MW to state review. | GoodPower | Project | Pre Application | 175 | 0.175 | NextEra has been engaging with community via meetings, but no formal application submitted to state yet. | [8 empty] | 59195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Kalamazoo BESS Ordinance |  | BESS | Kalamazoo County | Active |  | 26077 | MI | Comstock Charter Township Board of Trustees | Comstock Township Planning Commission | Planning Commission serving in an advisory role |  | Ordinance | Public Hearing |  | 0 | After a brief moratorium that was lifted early (4-3 vote), the town is working on a BESS ordinance while beginning to discuss a Copenhagen Infrastructure Partners project (size TBD). Early stages. More public hearings to come. September 25 planning and moratorium committee met to hear presentation from CIP and experts about the project. Planning seems open to the idea ( | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Two Rivers Solar | Boralex | Solar | St. Lawrence | Active |  | 36089 | NY | New York State Office of Renewable Energy Siting (ORES) |  |  |  | Project | Public Comment Period | 200 | 0.2 | Project submitted application in Jan, received notice of complete app in August. ORES has issued draft conditions of approval and public comment is open through in-person hearing November 20, 2025 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hillclimber Solar + BESS | RWE | Solar + BESS | Champaign County | Active |  | 39021 | OH | Ohio Power Siting Board |  |  |  | Project | Developer Community Meeting | 156.5 | 0.1565 | Prelim docs received by OPSB. opening docket. This project appears to be brand new to the public-a few disparate posts on social from the last 2 weeks. Public information meeting October 15, 2025 in Urbana. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Akron Solar Project | NextEra | Solar | Adams County | Active |  | 55001 | WI | Wisconsin Public Service Commission |  |  |  | Project | Public Comment Period | 200 | 0.2 | PSC docket comment window opened (through October 24) recently for 2nd round of comments. Public opposition is high (main concerns include lost accessible ATV/wilderness areas, habitat loss, state mandates). Land is currently under “managed forest land” status, open for public use. Packed community meeting Sept 27. Town leadership of Rome is in opposition. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890 | 757 | 0 | 10 | 0 | 0 | 0
Comstock Township BESS Ordinance | Copenhagen Infrastructure Partners | BESS | Kalamazoo County | Active |  | 26077 | MI | Comstock Township Planning Commission | Township Board of Trustees |  |  | Ordinance | Public Hearing | 400 | 0.4 | Over the last two years, Comstock has issued and then lifted a BESS moratorium. Their existing ordinance is NOT CREO compliant, meaning their regulations are stricter than the state’s thresholds. On October 30, Planning Commission is reviewing their existing ordinance in preparation of a likely application from CIP. State law would take siting authority to state level if the ordinance continues as currently drafted. Developer could still choose to go for local approvals | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Putnam County BESS Ordinance | Ecoplex | BESS | Putnam County | Active |  | 13237 | GA | Putnam County Commissioners |  |  |  | Ordinance | Planning Meeting |  | 0 | The county has an existing solar ordinance but it DOES NOT include BESS. Rep from Ecoplex came to the Commissioner's meeting to share materials and request for an amendment to add BESS. County strategically located in between Atlanta, Athens, Augusta, Macon | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Convergent Energy BESS | Covenant Energy & Power | BESS | Thurston County | Active |  | 53067 | WA | Energy Facility Site Evaluation Council (EFSEC) |  | BESS project falls under EFSEC, the coordinated state process, or strictly under local jurisdiction depends on its size, interconnection voltage, and other criteria. |  | Project | Project Hearing | 80 | 0.08 | Hearing examiner public hearing October 16, 2025. Comments can still be submitted for review by examiner. Currently looking through 60+ comments to understand the positive: negative split. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hillman Energy Storage | East Point Energy | BESS | Middlesex + Essex Counties | Active |  |  | MA | Energy Facilities Siting Board (EFSB) |  |  |  | Project | Public Comment Period | 125 | 0.125 | GL asked to do outreach to GAN. We are also planning a phone bank to residents (comment period remains open after hearing for another week+) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1179 | 1018 | 0 | 14 | 0 | 0 | 0
Fortress Solar + BESS | Aypa Power | Solar + BESS | Morgan County | Active |  | 8087 | CO | Morgan County Board of Commissioners |  |  |  | Project | Project Hearing | 600 | 0.6 | PPA just finalized. County has permitting authority. Next step is to secure permits. Project is vying to secure tax credits so time is of the essence. Recommended Intervention | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Earthwise Solar | Earthwise Energy | Solar | Will County | Active |  | 17197 | IL | Will County Board / Land Use Department |  |  |  | Project | Pre Application | 600 | 0.6 | Developer hosted open house Oct 8 -9, formal application to follow. Expected to be ~600 MW but not yet disclosed by the developer (~5400 acres). The County has a reasonable solar ordinance and will have siting authority for this project. | [8 empty] | 341419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fiddlehead Solar | Hecate Energy | Solar | Eaton & Jackson County | Active |  |  | MI | Michigan Public Service Commission (MPSC) |  |  |  | Project | Pre Application | 225 | 0.225 | Still in pre-application. Developer hosted a public information meeting last month. The project will be in three Townships: Hamlin, Brookfield, and Springport. | [8 empty] | 58117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fox Solar Project | NextEra | Solar + BESS | Oconto County | Active |  | 55083 | WI | Wisconsin Public Service Commission (PSCW) |  |  |  | Project | Pre Application | 150 | 0.15 | town hall in Morgan with developer on 10/7. No formal application submitted to PSC yet. Town Board exploring a Joint Development Agreement with NextEra to secure benefits from the project. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
KCE MI 4 | Key Capture Energy | BESS | Ottawa County | Active |  | 26139 | MI | Blendon Township Planning Commission and Ottawa County Department of Strategic Impact (Planning & Performance) |  |  |  | Project | Public Comment Period | 100 | 0.1 | First public hearing with planning board being rescheduled after cancellation October 6. Appears the Township has a CREO-complaint ordinance so they can have siting authority and generate additional $5k/MW grant from the state | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Poblano Solar +BESS | Longroad Energy | Solar + BESS | Pinal County | Active | Eloy | 4021 | AZ | Eloy City Council |  |  |  | Project | Public Comment Period | 200 | 0.2 | Application to expand an already approved 150 MW solar project to add 25 MW to amount additional solar plus 200 MW BESS. P&Z held public hearing and vote last week on whether to recommend it to the City Council. Unclear of outcome. Next step is City Council vote date TBD. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Oakham BESS | Rhynland Energy | BESS | Worcester County | Active |  | 25027 | MA | Oakham Planning Board | Massachusetts Energy Facilities Siting Board (EFSB) provides state-level oversigh |  |  | Project | Public Comment Period | 180 | 0.18 | state review process underway. Public hearing on Oct 16. Written public comments accepted until October 30. Lots of community opposition. 100+ negative comments submitted to the Energy Facility Siting Board. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5129 | 4409 | 0 | 44 | 0 | 0 | 0
Oak Solar | Sun Energy 1 | Solar | Northampton County | Active |  | 37131 | NC | Northampton County Planning Board & Board of Commissioners |  |  |  | Project | Pre Application | 200 | 0.2 | County excited about CBA: The recently signed CBA includes: $1.5 million towards the construction of a new EMS station located in the western side of the county, at least $250,000 towards the purchase of a new ambulance for the county’s EMS fleet, and at least $50,000 towards upfitting and repairs to the county’s existing ambulances. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cherry Solar | Sun Energy 1 | Solar | Northampton County | Active |  | 37131 | NC | Northampton County Planning Board & Board of Commissioners |  |  |  | Project | Pre Application | 300 | 0.3 | County excited about CBA: The recently signed CBA includes: $1.5 million towards the construction of a new EMS station located in the western side of the county, at least $250,000 towards the purchase of a new ambulance for the county’s EMS fleet, and at least $50,000 towards upfitting and repairs to the county’s existing ambulances. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bullitt Bend Solar | NextEra | Solar | Concordia | Active |  | 22029 | LA | Concordia Parish Police Jury |  | primary land-use approval is by the Concordia Parish Police Jury, with parish permits/inspections managed via Concordia Permits/IBTS; state environmental permits handled by LDEQ |  | Project | Public Comment Period | 200 | 0.2 | State application pending. Unclear if local permits have been secured. In July, the Parish agreed to a PILOT agreement for the project. Need to confirm with the developer what permitting steps are ahead. Large-scale projects can be subject to local and state approval. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Barite Solar | Azimuth Renewables | Solar | Concordia | Active |  | 22029 | LA |  |  |  |  | Project | Project Hearing | 150 | 0.15 | Developer has been working with the Parish since last year on its application. Parish reviewing to ensure compliance with local ordinance. A public hearing was held October 13. Unclear if there will be more. It appears the project will be approved locally. Need to confirm with the developer what permitting steps are ahead. Large-scale projects can be subject to local and state approval. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Brandonville Solar | Enel | Solar | Preston County | Active |  | 54077 | WV | Public Service Commission of West Virginia (PSC) |  |  |  | Project | Public Comment Period | 100 | 0.1 | Application Complete. PSC appears to be fast-tracking this project. The PSC has ordered Brandonville Solar to publish a notice of filing in one Preston County newspaper, and if there is no substantial opposition received in 30 days, the formal public hearing could be waived and the siting certificate could be granted. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crowned Ridge Energy Storage I | NextEra | BESS | Codington County | Active |  | 46029 | SD | South Dakota Public Utilities Commission (PUC) |  |  |  | Project | Pre Application | 100 | 0.1 | NextEra’s request for a permitting exemption was denied in August. Notice of Intent submitted to the state on October 20, 2025. Project is sited on an existing 200 MW Crowned Ridge Wind Farm operated by NextEra. This would be the first utility-scale BESS in South Dakota. Pre-application meeting requested for March 2026. Anticipated application submission April 2026 with decision by April 2027. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crossvine Solar Project | AES | Solar + BESS | Dubois County | Active |  | 18037 | IN | Indiana Utility Regulatory Commission (IURC) | Dubois County — local land-use via the Commercial Solar Energy Systems Ordinance |  |  | Project | Developer Community Meeting | 170 | 0.17 | Lightsource bp secured state permits before selling the project to AES in 2024. AES will be seeking road use and other permits from the County (to be confirmed with AES). Community engagement is just beginning with a tentative community meeting on November 13. | 2025-11-13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ten MIle Creek Solar | Xcel | Solar | St. Croix | Active |  | 55109 | WI | Wisconsin Public Service Commission | St. Croix County | County is working on a Joint Development Agreement with Xcel that will ensure certain developent criteria are met | WI table | Project | Pre Application | 300 | 0.3 | Application anticipated filing Q4 2025. State table has identified this project as a priority project. Xcel recently announced adding BESS to the proposal. A second phase of the project could bring it to 650 MW solar, without including the BESS (size TBA) |  |  |  | We met with the developer 1 year ago when they presented to the WI table and pitched them on a partnership. Developer did not proceed at that time. We did not begin engagement with the project until the state table recommended it as a priority project (fall 2025) |  |  | Pre-application | 2025-11-12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fort Edwards Solar | Boralex | Solar | Washington County | Active |  | 36115 | NY | Washington County Planning Board & Board of Supervisors |  |  |  | Project |  | 100 | 0.1 | exploring a potential influencer campaign to counter misinformation from a viral creator near the project. Looking at this as a pilot for potential addition to menu of services. Developer providing some additional info for vetting. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cactus Wren BESS | esVolta | BESS | Pinal County | Active |  | 4021 | AZ | Pinal County Board of Supervisors & Planning & Zoning Commission |  |  |  | Project | Public Comment Period | 250 | 0.25 | ongoing discussions with esVolta about paid partnership. They brought this project to us, looking for a handful of local support letters. They only want to reach out to our GAN (outside of 1 mile radius from site), which we have explained will mean a low number of responses. Comment deadline November 13. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 275 | 0 | 14 | 1 | 0 | 1
Sherco Solar + BESS | Xcel | Solar + BESS | Sherburne County | Active |  | 27141 | MN | Minnesota Public Utilities Commission |  |  |  | Project |  | 500 | 0.5 | BESS to be sited next to a coal plant with planned retirement 2030. 300 MW already approved. New application to double capacity. This would be the state’s largest BESS. Using existing transmission. On October 31, Xcel filed to double the project size from 300 to 600 MW. BESS> 10 MW needs state approval from MPUC. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Blue Lake BESS | Xcel | BESS | Scott County | Active |  | 27139 | MN | Minnesota Public Utilities Commission |  |  |  | Project |  | 135.5 | 0.1355 | In the same notice to the MPUC, Xcel is proposing to expand existing Blue Lake BESS in Scott County by 135.5 MW) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 68 | 0 | 0 | 0 | 0 | 0
New Haven Solar Ordinance |  | Solar | Allen County | Active |  | 18003 | IN |  |  |  |  | Ordinance | Public Hearing |  | 0 | In response to Allen County’s restrictive ordinance, on November 4, 2025, Mayor Steve McMichael met with renewable energy advocates (SUN IN), along with the city’s planning services director and economic development officer, to discuss the draft ordinance. The draft reflects a strong commitment to encouraging responsible solar deployment and local investment. The Mayor is highly supportive. Meeting today to discuss ordinance. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 526 | 492 | 0 | 5 | 0 | 0 | 0
Shawnee County Solar Ordinance |  | Solar | Shawnee County | Active |  | 20177 | KS | Shawnee County Planning Commission & Board of County Commissioners |  |  |  | Ordinance | Project Hearing |  | 0 | In partnership with Greenlight. Drove RSVPs for planning commission hearing October 13. They are still drafting ordinance. Future hearing dates to be announced. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Claire BESS | Balanced Rock | BESS | Harris County | Active |  | 48201 | TX | City of Baytown Planning & Zoning Commission and Baytown City Council |  |  |  | Project | Project Hearing | 406 | 0.406 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 214 | 214 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Silver Reef Solar + Storage | Nadera | Solar + BESS | Pinal County | Active |  | 4021 | AZ | Pinal County Board of Supervisors |  |  |  | Project | Project Hearing | 300 | 0.3 | November 19 BOS hearing, public testimony and vote. Received recommendation for denial from P&Z | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Diamond Solar Energy | Invenergy | Solar | Klamath County | Active |  | 41035 | OR | Oregon Energy Facility Siting Council (EFSC) | Coordinated with Klamath County Planning Department |  |  | Project | Project Hearing | 200 | 0.2 | October 28 planning commission hearing. Not many comments. Decision and BOC public hearing upcoming Overview: Because this project is sited on private land, it goes through local approvals. The Commission closed the hearing and will now deliberate before making a recommendation before moving the project to BOC for final vote. Unclear of timing. Issues include using forested land (developer has plans with land owner to protect other lands as mitigation measure) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Heppner Wind Project | NextEra | Onshore Wind | Morrow County | Active |  | 41049 | OR | Oregon Energy Facility Siting Council (EFSC) | Coordination with Morrow County Planning Department |  |  | Project | Pre Application | 190 | 0.19 | Application expected December 2025. NOI submitted August, 2025 and project docket opened October 10. Awaiting public comment to start -- 67 turbines, max blade height 640 ft, includes 11 miles of new transmission lines. There is opposition, particularly around viewshed impacts. Interest here in the county dates back to 2010s. An earlier version of a Heppner wind facility (a much larger proposal of up to 502 MW) was proposed by a different developer and ultimately terminated. There was lots of opposition to this first iteration of the project. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cactus Flower Solar + Storage | Cyress Creek Renewables | Solar + BESS | Pinal County | Active |  | 4021 | AZ | Pinal County Board of Supervisors |  |  |  | Project |  |  | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Santa Cruz BESS Ordinance |  | BESS | Santa Cruz County | Active |  | 6087 | CA | County Board of Supervisors |  |  |  | Ordinance |  |  | 0 | BOS meeting tomorrow to review draft ordinance with public hearing. More public hearings to follow. If the board approves the ordinance, it would undergo environmental review and face final review by the supervisors and several advisory bodies including the Planning Commission. The process is expected to take up to a year. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reform Solar Project | Ameren | Solar | Callaway County | Active |  | 29027 | MO | MO PSC |  |  |  | Project | Public Comment Period | 250 | 0.25 | Two hearings scheduled Jan 6 and Jan 8 (virtual). Public comment accepted right now via state docket. | 2025-01-06 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Burke County BESS Project | NextEra | BESS | Burke County | Active |  | 38013 | ND | Board of Supervisors |  |  |  | Project | Project Hearing | 100 | 0.1 | This would be ND’s second BESS project. First one is undergoing approval hearing this week. Some state regulators concerned with overreliance on BESS to stabilize grid. New technology in ND. Ripe for educational ground-softening. BOS hearing December 19 | 2025-12-19 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spud Valley Solar + BESS | NextEra | Solar + BESS | Alamosa County | Active |  | 08003 | CO | Board of Supervisors |  |  |  | Project | Project Hearing | 1200 | 1.2 | This would be the largest development in the state. County sees it as an opportunity to pressure Xcel to deploy more transmission to the area. County officials are supportive so far - Planning Commission recommended approval last week.. It would occupy land that is less and less agriculturally relevant given depletion of aquifer, providing stable income to farmers. BOS hearing early 2026. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lemon Hill Solar | Ranger Power | Solar | Olmsted County | Active |  | 27109 | MN | MN PSC |  |  |  | Project | Public Comment Period | 180 | 0.18 | Public Information hearings hosted by MN PSC scheduled for this week (11/19 and 11/20). Public comment period open until December 8. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Acceleration Solar | Ranger Power | Solar | Ingham County | Active |  | 26065 | MI | MI PSC |  |  |  | Project | Project Hearing | 90 | 0.09 | Prehearing November 14. Awaiting official hearing dates from MI PSC. | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Aioli Energy Center | Clearway Energy | BESS | Clark County | Active |  | 32003 | NV | City of Las Vegas Planning Commission |  |  |  | Project | Planning Meeting | 400 | 0.4 | Lots of opposition at recent informational meeting. Lots of concern around BESS safety Planning Commission hearing date set for January 13, 2026. | 2026-01-13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Tracker - For Google Sh (hidden)
Campaign ID | Project | Developer | Type | Jurisdiction | Current Status | City | County FIPS Code | State | Lead Origin | Milestone | Milestone Type | Project Size MW | Project Size GW (formula) | Status Notes and Links | Original Hearing Date | Latest Hearing Date | Hearing Date Notes | Level of Outreach | ACE activation | CROP/AEJ/ASM activation | Which stage? | Status last updated | Total Impressions | Total Reach | Total Emails Sent | Total SMS Messages Sent | Total Calls | Totals Clicks (to page) | Total Comment Submissions (ETT page) | Total RSVPs (Petition page) | Total Attendees | Total RSVPs and Attendees (formula) | Links | Remarks | Report back from Partner | Docket #
ADVO-S-OH-S3-NR-RE-OTHR-Frasier Solar ¦ KNOX CTY | Frasier Solar | Open Roads | Solar | Knox County | Win |  | 39083 | OH | ACE | Project | Project Hearing | 120 | 0.12 | Link | 2024-04-04 |  | TBD | Digital ads only | TRUE | TRUE | 4 local hearings done | 2025-04-01 | 2057706 | 624330 | 25442 | 2044 | 0 | 2400 | 327 | 33 |  | 33 | https://floodlightnews.org/fossil-fuel-interests-solar-ohio/
ADVO-S-CO-NC-NR-FS-OTHR-Mesa County Solar Moratorium | Mesa County Solar Moratorium | Moratorium | Solar | Mesa County | Win |  | 8077 | CO | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-04-23 |  | NA | Digi + P2P | FALSE | TRUE | Moratorium Reversed | 2025-04-01 | 404829 | 186478 | 0 | 7241 | 27 | 700 | 0 | 0 |  | 0
Not Available | Yavapai County Solar Moratorium | Moratorium | Solar | Yavapai County | Loss |  | 4025 | AZ | Greenlight | Moratorium | Solar Moratorium | 0 | 0 |  | 2024-08-08 | 2024-09-06 |  | Digi + P2P | FALSE | TRUE | 3rd meeting on Nov 6th | 2025-04-01 | 243569 | 56958 | 0 | 235 | 55 | 577 | 0 | 2 |  | 2 | https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/News/Solar-Facilities-Zoning-Ordinance https://www.yavapaiaz.gov/Development-and-Permits/Development-Services/Planning-Unit/Planning-Zoning-Cases/Solar-Facilities-Zoning-Ordinance-Amendment | 1 or 2 sign ups | Not hearing good news - so GL not going ahead with supporting
Not Available | Mohave County Solar Moratorium | Moratorium | Solar | Mohave County | Loss |  | 4015 | AZ | Greenlight | Moratorium | Solar Moratorium | 0 | 0 | Link | 2024-06-03 |  |  | Digi + P2P | FALSE | TRUE | Ongoing with lot of gas lobbying | 2025-04-01 | 156574 | 29446 | 0 | 241 | 37 |  | 0 | 29 |  | 29 |  | Handful of RSVPs but no turn out | Passed a restrictive ordinance
Not Available | Propel Transmission | New York Transco and NYPA | Offshore Wind | Nassau County | Pending |  | 36059 | NY | Greenlight | Project | Volunteer Open House | 432 | 0.432 | No hearing yet |  |  | TBD | Peer to Peer only | TRUE | FALSE | Early | 2025-04-01 | 0 | 0 | 0 | 1287 | 124 | 0 | 0 | 2 | 0 | 2 | PROPEL Open House Script | Southampton 9dot is related - looking across the island
Not Available | Clear Mountain | Savion | Solar | Clermont County | Win |  | 39025 | OH | ACE | Project | Public Hearing | 100 | 0.1 | Link | 2024-08-01 | 2024-09-10 |  | Digi + P2P | FALSE | TRUE | 2 Local hearings done | 2025-04-01 | 807968 | 207851 | 0 | 566 | 0 | 5860 | 0 | 1 | 0 | 1
Not Available | Ochoa Energy BESS | Vesper | BESS | Waller County | Loss | Katy | 48473 | TX | Greenlight | Project | Planning Meeting | 500 | 0.5 | Link | 2024-09-10 |  |  | Peer to Peer only | FALSE | FALSE | Initial planning | 2025-04-01 | 0 | 0 | 0 | 3619 | 0 | 0 | 20 | 0 |  | 0 | https://katytimes.com/stories/chamber-hosts-energy-experts,88922 | Update: Katy City Council denies project: https://www.chron.com/news/houston-texas/article/katy-battery-storage-facility-council-19863234.php . Earlier update: 10 people overall (Not just ACE)
INTV-S-KY-S3-NR-RE-SIPE-Lexington Solar | Lexington Solar | Silicon Ranch | Solar | Fayette County | Pending |  | 21067 | KY | ACE | Project | Solar Zoning | 0 | 0 | Rejected by Commission. Council to review end of Q1 2025 | 2024-09-26 | 2024-09-26 |  | Digital ads only | FALSE | TRUE | Commission rejected proposal for utility-scale solar expansion. Commission’s recommendation will be taken to the Lexington Fayette Urban County Government’s city council, which will have the final say on its implementation. | 2025-04-02 | 1120432 | 210391 | 0 | 0 | 0 | 16867 | 0 | 4 |  | 4 | https://www.kentucky.com/news/local/counties/fayette-county/article293034494.html | Commission rejected, company seems to be looking to continue, wrote new op-ed since hearing in local paper
Not Available | Prospect and Janus Solar Project |  | Solar | Weld County | Win |  | 8123 | CO | Greenlight | Project | Planning Meeting | 179 | 0.179 |  | 2024-10-01 | 2024-10-23 |  | Peer to Peer only | TRUE | FALSE | Joint hearings - Commission reviewed projects on 10/1, voting to approve on 10/23 | 2025-04-02 |  |  | 0 | 1281 | 0 |  |  | 1 | 1 | 2 |  | Vote on 22nd Oct
Not Available | Town of Babylon BESS Moratorium | Moratorium | BESS | Suffolk County | Pending | Town of Babylon | 36103 | NY | Greenlight | Moratorium | BESS Moratorium | 0 | 0 | Moratorium Ending |  |  |  | Peer to Peer only | FALSE | TRUE | Moratorium currently in place thru 6 months post effective date of 6/5/24 - 12/5/24 | 2025-04-02 |  |  | 0 | 525 | 0 |  |  | 17 | 1 | 18 | https://www.townofbabylon.com/DocumentCenter/View/9791/0605---Adopt-of-LL-11-Moratorium
INTV-S-WI-S3-NR-RE-SIPE-Dawn Harvest Solar | Dawn Harvest Solar | Invenergy | Solar | Rock County | Win |  | 55105 | WI | ACE | Project | Public Comment Period | 150 | 0.15 |  | 2024-06-01 | 2025-01-21 |  | Digital ads only | TRUE | TRUE | New public comment period in Dec/Jan. Public Comment completed, WI Public Service Commission to decide | 2025-04-02 | 1027208 | 505240 | 23886 | 13530 | 0 | 39162 | 146 | 7 |  | 7 | https://www.wpr.org/energy/wisconsin-utilities-propose-billions-renewable-energy-projects potentially part of larger deal with state of WI | 2nd Comment period open with the PCSW thru 1/23/25
INTV-S-KS-NC-NR-OT-SIPE-Hope Ridge Wind ¦ Commissioner Hearing | Hope Ridge Wind | Enel | Onshore Wind | Dickinson County | Win |  | 20041 | KS | ACE | Project | Public Comment Period | 334 | 0.334 |  | 2024-10-10 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | Project Approved (11/21). Commissioners overrode the Planning Commission recommendation to deny the project. Public Comment is open through 11/19. Sending ACE list members SMS/Email to submit comment. | 2025-04-02 | 341944 | 27260 | 92 | 25 | 0 | 6054 | 1 | 18 |  | 18 | https://kclyradio.com/business/dickinson-county-planning-and-zoning-board-votes-to-deny-cup-for-wind-farm/ https://www.kwch.com/2024/10/11/proposed-wind-farm-project-prompts-massive-turnout-dickinson-county-meeting/ | Hearing completed | https://www.kwch.com/2024/10/17/planning-commission-votes-favor-2-year-moratorium-proposed-wind-farm-dickinson-county/
Not Available | Southampton BESS Moratorium | Nine Dot | BESS | Suffolk County | Loss |  | 36103 | NY | Greenlight | Moratorium | BESS Moratorium | 0 | 0 |  | 2024-10-22 |  |  | Peer to Peer only | TRUE | FALSE | Early - ground softening | 2025-04-02 | 0 | 0 | 0 | 135 | 0 | 0 | 8 | 0 |  | 0
ADVO-S-MN-NC-NR-OT-SIPE-Birch Coulee ¦ Solar | Birch Coulee | AES | Solar | Renville County | Pending |  | 27129 | MN | ACE | Project | Public Hearing | 125 | 0.125 |  | 2024-10-09 | 2024-10-09 |  | Organizing only | TRUE | FALSE | Hearing completed, comment period open until 10/25 - next steps in remarks | 2025-04-02 | 0 | 0 | 12690 | 0 | 5 | 26 | 14 | 0 | 4 | 4 | https://www.nujournal.com/news/communities/2024/10/11/245-million-solar-project-proposed-in-franklin/ https://efiling.web.commerce.state.mn.us/documents/%7BC06CE992-0000-C612-B70B-840CAA215451%7D/download?contentSequence=0&rowIndex=5 | An environmental assessment is forecast to be issued in February 2025. Following a March 2025 public hearing, an administrative law judge will file a report in May 2025. The Mn PUC will consider a site permit in June 2025. // Miasia and team attended hearing and will have a report back
EVEN-S-GA-NC-NR-OT-SIPE-Coweta County Solar | Coweta County Solar | Opdenergy | Solar | Coweta County | Loss |  | 13077 | GA | ACE | Project | Public Hearing | 476 | 0.476 |  | 2024-09-12 | 2025-01-25 |  | Digital ads only | TRUE | TRUE | first hearing done, work session 10/24, final hearing 11/5. Commissioners extended hearing until January 2025. At January hearing, they passed an ordinance with a 500 acre cap for solar, killing the Opdenergy proposal | 2025-04-02 | 217744 | 12264 | 212 | 78 |  | 2640 | 0 | 5 |  | 5 | https://www.times-herald.com/news/county-continues-to-revise-proposed-solar-ordinance/article_e14a6b7c-7157-11ef-8f68-9fc45fcc9ffc.html https://www.times-herald.com/news/commissioners-say-solar-energy-systems-should-be-no-more-than-500-acres/article_c4563780-930d-11ef-8366-67c060426d39.html#:~:text=in%20Coweta%20County.-,The%20Coweta%20County%20Commissioners%20advised%20county%20staff%20to%20not%20allow,is%20the%20House%20of%20Pickleball. | Hearing day of election, moving forward with ACE & CROP ads. Commission has advised staff to add a 500 acre cap on projects, per community feedback. They added it and voted to approve restrictive ordinance in Jan 2025
Not Available | Pinal County Solar | Multiple Developers | Solar | Pinal County | Pending |  | 4021 | AZ | Greenlight | Project | Public Hearing | 1462 | 1.462 | Link |  | 2024-10-30 |  | Digi + P2P | FALSE | TRUE | Comp Plan Zoning Changes approved for solar project sites | 2025-04-02 | 490801 | 35966 | 0 | 948 | 86 | 2476 | 0 | 11 |  | 11 | Ore Town: https://copperarea.com/proposed-solar-farm-near-san-manuel-has-residents-asking-questions/ // Many projects in the area up for approval: https://www.pinalcentral.com/maricopa_monitor/news/solar-applications-bombard-pinal-county/article_548cb27e-5a8e-11ef-8df2-cbef43f2ee37.html?utm_campaign=blox&utm_source=facebook&utm_medium=social&fbclid=IwY2xjawF7gNVleHRuA2FlbQIxMQABHWhjkBDsnw1Wn3W-c5OcwL-tR7Ggy1lBppW9Nwh_aFXpUJsIsTc0Uj6wlw_aem_bOVh2rKUdvrOrHXC42CINA | Helping GL with turnout - CROP & AEJ ads
EVEN-S-IA-NC-NR-OT-SIPE-Jackson County Wind ¦ Ordinance | Jackson County Wind | Ordinance | Onshore Wind | Jackson County | Pending |  | 19097 | IA | ACE | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-18 | 2024-11-18 |  | Digi + P2P | TRUE | TRUE | Awaiting results of hearing on 11/18. | 2025-04-02 | 11535 | 1361 | 20 | 16 | 0 | 2923 | 0 | 0 |  | 0
EVEN-S-VA-NC-NR-OT-SIPE-Halifax County Solar | Halifax County Solar | Ordinance | Solar | Halifax County | Loss |  | 51083 | VA | ACE | Ordinance | Public Hearing | 0 | 0 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County passed a very restrictive solar ordinance and lowered density cap from 5% to 3%. Landscape is tough for utility-scale development moving forward | 2025-04-02 | 9881 | 1137 | 30 | 20 | 0 | 2756 | 0 | 0 |  | 0
EVEN-S-NE-NC-NR-OT-SIPE-Cass County Solar | Cass County Solar | NextEra Energy | Solar | Cass County | Loss |  | 31025 | NE | ACE | Project | Public Hearing | 265 | 0.265 |  | 2024-11-19 | 2024-11-19 |  | Digi + P2P | TRUE | TRUE | County DENIED permit on Feb 14 | 2025-04-02 | 28331 | 3521 | 24 | 12 | 0 | 3027 | 0 | 0 | 0 | 0 |  | https://rivercountry.newschannelnebraska.com/story/52367495/county-rejects-cass-county-solar
ADVO-S-NC-NC-NR-OT-SIPE-Bright Leaf & Swift Creek Solar + BESS | Bright Leaf & Swift Creek Solar + BESS | Multiple Developers | Solar + BESS | Edgecombe County | Loss |  | 37065 | NC | ACE | Project | Public Comment Period | 192 | 0.192 |  | 2024-12-02 | 2024-12-02 |  | Digi + P2P | TRUE | TRUE | Special use permits DENIED at meeting on 12/2. Connect with devs on any next steps when the current moratorium period is over. | 2025-04-02 | 31098 | 3437 | 62 | 0 | 0 | 1358 | 12 |  |  | 0
INTV-S-VA-NC-YOU-BLT-OT-SIPE-Surry County BESS ¦ Ordinance | Surry County BESS | Clenera | BESS | Surry County | Win |  | 51181 | VA | ACE | Ordinance | Public Hearing | 400 | 0.4 |  | 2024-12-16 | 2025-01-27 | Cont. from Dec hearing | Digi + P2P | FALSE | TRUE | Running second rnd of ads for the continued hearing on 1/27 | 2025-04-02 | 316782 | 24825 | 0 | 0 | 0 | 4850 | 6 | 0 | 0 | 0 | https://www.smithfieldtimes.com/2025/05/14/developer-surry-battery-site-would-see-less-traffic-than-solar-farms/ | Ordinance approved April 2 by Commissioners. Clanera now moving forward with application for BESS project
Not Available | Paddlefish Solar | EDF Renewables | Solar | Huntington County | Potential |  | 18069 | IN | ACE | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
Not Available | Paddlefish Solar | EDF Renewables | Solar | Wells County | Potential |  | 18179 | IN | ACE | Project | Public Hearing | 175 | 0.175 |  | 2024-07-01 |  | TBD - Feb 2026 | Digi + P2P + OOH/Print | TRUE | TRUE | Moratorium on project until 2025 | 2025-04-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://www.wane.com/news/local-news/huntington-county-commissioners-hold-extended-until-2025-on-solar-project/ | Longer term project. Planning to incorporate OOH, ACE & MCE ads, etc. 350 MW split into two counties.
INTV-S-AL-NC-NR-OT-SIPE-Hope Hull Solar ¦ Montgomery | Hope Hull Solar | Silicon Ranch | Solar | Montgomery | Win | Montgomery | 1101 | AL | ACE | Project | Public Hearing | 80 | 0.08 |  | 2024-11-21 | 2025-01-16 |  | Digi + P2P | TRUE | TRUE | Final approval granted by Montgomery County Board of Adjustment on 1/16! | 2025-04-02 | 43527 | 6967 | 526 | 7031 | 525 | 1140 | 27 | 77 | 1 | 78
INTV-S-OH-NC-NR-OT-SIPE-Eastern Cottontail Solar | Eastern Cottontail Solar | EDF Renewables | Solar | Fairfield County | Pending |  | 39045 | OH | Greenlight | Project | Public Hearing | 220 | 0.22 | Scripts | 2025-01-27 | 2025-01-27 |  | Digi + P2P | FALSE | TRUE |  | 2025-04-07 | 166275 | 23556 | 0 | 382 | 0 | 74 | 3 | 0 | 0 | 0
Not Available | Schnebly Coulee Solar | Invenergy | Solar | Kittitas County | Pending |  | 53037 | WA | Greenlight | Project | Volunteer Open House | 90 | 0.09 | Toolkit | 2024-12-18 |  |  | Peer to Peer only | FALSE | TRUE | A second round of text and phonebanking support provided in Feb 2025 | 2025-04-07 | 0 | 0 | 2 | 102 | 26 | 0 |  | 2 | 1 | 3 |  | One of our YAN members attended the second hearing and spoke as well
Not Available | Sussex County Offshore Wind Project | Overall | Offshore Wind | Sussex County | Potential |  | 10005 | DE | Greenlight | Project | Public Hearing | 0 | 0 |  | 2024-12-10 |  |  | Peer to Peer only | TRUE | FALSE |  | 2025-04-07 | 0 | 0 |  | 0 | 0 | 0 |  |  |  | 0
Not Available | Santa Fe Planning Commission voted (6-1) to APPROVE the Conditional Use Permit yesterday. Parties have 30 days to appeal the Planning Commission’s decision to the County Commission. Appealed to County Commissioners - Hearing is 8/11 | AES | Solar + BESS | Santa Fe County | Pending |  | 35049 | NM | Greenlight | Project | Public Hearing | 144 | 0.144 | GL Campaign | 2024-02-05 | 2025-02-03 | Next Hearing 8/11 | Digi + P2P | TRUE | TRUE | Santa Fe Planning Commission voted (6-1) to APPROVE the Conditional Use Permit yesterday. Parties have 30 days to appeal the Planning Commission’s decision to the County Commission. Opposition groups say they will appeal. | 2025-06-26 | 18226 | 2338 | 4779 | 2310 | 380 | 1836 | 31 | 55 | 1 | 56
Not Available | Hesperus Solar | Primergy | Solar + BESS | La Plata County | Withdrawn |  | 8067 | CO | Longitudinal | Project | Project Hearing | 155 | 0.155 | News Article |  | 2024-10-29 |  |  | FALSE | FALSE | The application for a 1,900-acre solar project has been deemed withdrawn by county planners, although the developer has stated an intent to resubmit the application. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Prairie Power Solar Farm | Prairie Power Inc | Solar | Sangamon County | Pending |  | 17167 | IL | Longitudinal | Project | Pre Application | 200 | 0.2 |  |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Soul City Solar Project | Apex Clean Energy | Solar | Hinds County | Win |  | 28049 | MS | Longitudinal | Project | Project Approved | 396 | 0.396 | News Article |  | 2024-06-18 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Libra Solar Project | Arevia Power | Solar + BESS | Mineral County | Win |  | 32021 | NV | Longitudinal | Project | Project Approved | 700 | 0.7 | News Article | 2024-09-09 | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Greenlink West Transmission Project | NV Energy | Transmission |  | Win |  |  | NV | Longitudinal | Project | Project Approved | 0 | 0 | News Article |  | 2024-09-09 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Dry Lake East Energy Center | NextEra | Solar + BESS | Clark County | Win |  | 32003 | NV | Longitudinal | Project | Project Approved | 800 | 0.8 | News Article |  | 2024-08-30 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Blue Ridge Solar | Recurrent Energy | Solar | Pittsylvania County | Win |  | 51143 | VA | Longitudinal | Project | Project Approved | 150 | 0.15 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Michaux Solar | Dominion Energy | Solar | Henry County | Win |  | 51089 | VA | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Michaux Solar | Dominion Energy | Solar | Pittsylvania County | Win |  | 51089 | VA | Longitudinal | Project | Project Approved | 25 | 0.025 | Press Release |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Grand Junction Solar | Alliant Energy | Solar + BESS | Greene County | Win |  | 19073 | IA | Longitudinal | Project | Project Approved | 150 | 0.15 | News |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Not Available | Split Rail Solar | Ameren | Solar | Warren County | Win |  | 29219 | MO | Longitudinal | Project | Project Approved | 300 | 0.3 | News Article |  | 2024-03-22 |  | Digital ads only | FALSE | TRUE |  | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
INTV-S-WI-NC-NR-OT-SIPE-Badger Hollow Wind ¦ Comments | Badger Hollow Wind | Invenergy | Onshore Wind | Iowa County | Active |  | 55049 | WI | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-06-24 |  | Digi + P2P | FALSE | TRUE | Public hearings scheduled for June 24, 2pm & 6pm sessions (per WI siting table) | 2025-06-06 | 150650.5 | 28243.5 | 23864 | 11314.5 | 0 | 7622 | 58 | 0 | 0 | 0 |  |  |  | 9827-CE-100
INTV-S-WI-NC-NR-OT-SIPE-Badger Hollow Wind ¦ Comments | Badger Hollow Wind | Invenergy | Onshore Wind | Grant County | Active |  | 55043 | WI | WI Siting Table | Project | Public Comment Period | 59 | 0.059 |  | 2024-12-20 | 2025-06-24 |  | Digi + P2P | FALSE | TRUE | Public hearings scheduled for June 24, 2pm & 6pm sessions (per WI siting table) | 2025-06-06 | 150650.5 | 28243.5 | 23864 | 11314.5 | 0 | 7622 | 59 | 0 | 0 | 0 |  |  |  | 9827-CE-100
Not Available | Uplands Wind | Pattern Energy | Onshore Wind | Lafayette County | Pending |  | 55065 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Not Available | Uplands Wind | Pattern Energy | Onshore Wind | Iowa County | Pending |  | 55049 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
Not Available | Uplands Wind | Pattern Energy | Onshore Wind | Grant County | Pending |  | 55043 | WI | WI Siting Table | Project | Public Comment Period | 200 | 0.2 | News Article |  |  |  |  | FALSE | FALSE | Environmental Public comment period open through 12/20 | 2025-04-07 |  |  |  | 0 | 0 | 0 | 0 |  |  | 0
INTV-S-WA-NC-NR-OT-SIPE-Mount Vernon BESS ¦ Skagit County | Mount Vernon BESS | NextEra | BESS | Skagit County | Win |  | 53057 | WA | ACE | Project | Public Hearing | 200 | 0.2 | Hearing Announcement | 2024-12-20 |  |  | Digi + P2P | FALSE | TRUE | Comment period open ahead of public meeting on 12/20. Decision expected ~2 weeks post-meeting | 2025-04-22 | 39408 | 5093 | 107 | 64 |  | 1983 | 6 | 0 | 0 | 0
INTV-S-VA-NC-NR-OT-SIPE-Gabriel Solar ¦ BESS Prince Edward County | Gabriel Solar | Gabriel Energy / Energix US | Solar + BESS | Prince Edward County | Loss |  | 51147 | VA | ACE | Project | Public Hearing | 200 | 0.2 | Hearing Documents | 2024-12-17 | 2025-02-11 |  | Digi + P2P | FALSE | TRUE | Public hearing of county commissioners on 2/11 | 2025-01-13 | 226826 | 37131 | 32 | 9 |  | 3838 | 6 | 0 | 3 | 3
Not Available | Keystone Wind | RWE | Onshore Wind | Pawnee County | Active |  | 40117 | OK | RWE | Project | [7 empty] | Digital ads only | FALSE | TRUE | Early stages of planning, signing landowners | 2025-05-12 | 607009 | 202844 |  | 0 | 0 | 0 | 0 |  |  | 0
Not Available | Prairie Wolf Wind | RWE | Onshore Wind | Hughes County | Active |  | 40063 | OK | RWE | Project | Planning Meeting | 119.5 | 0.1195 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-02-11 | 171151.5 | 56013 |  | 0 | 0 | 0 | 0 | 17 |  | 17
Not Available | Prairie Wolf Wind | RWE | Onshore Wind | Okfuskee County | Active |  | 40107 | OK | RWE | Project | Planning Meeting | 119 | 0.119 |  |  |  |  | Digital ads only | FALSE | TRUE | Still signing landowners, meeting with community | 2025-02-11 | 171151.5 | 56013 |  | 0 | 0 | 0 | 0 | 17 |  | 17
Not Available | Iron Pine Solar | Swift Current Energy | Solar | Pine County | Win |  | 27115 | MN | ACE | Project | Project Hearing | 325 | 0.32 |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | Awaiting MN PUC decision | 2025-02-26 | 57786 | 14393 | 7259 | 7284 | 884 | 1112 | 86 | 30 | 11 | 41 |  |  |  | IP7114/GS-23-414 (Site Permit) and IP7114/TL-23-415 (Route Permit) OAH Docket Number: 22-2500-40198
Not Available | Westfield Battery Ordinance | Jupiter Power | BESS | Hampden County | Pending |  | 25013 | MA | ACE | Ordinance | Public Comment Period |  |  |  |  | 2025-02-06 |  | Digi + P2P | TRUE | TRUE | City council considering strict rules to stifle BESS construction. Council appears united in opposition of BESS and is intervening in Jupiter's application for state approval. | 2025-02-07 | 36565 | 8134 |  |  |  | 523 | 0 |  |  | 0
Not Available | Bolivar Onshore Wind Ordinance | Steelhead/Vestas | Onshore Wind | Bolivar County | Potential |  |  | MS | ACE | Ordinance | Public Hearing |  |  |  |  | 2025-02-17 |  |  | TRUE | TRUE |  | 2025-04-07 | [5 empty] | 0 | 0 |  |  | 0
Not Available | Goshen Onshore Wind Ordinance |  | Onshore Wind | Goshen County | Pending |  | 56015 | WY | ACE | Ordinance | Public Hearing |  |  |  |  | 2025-02-05 |  | Digi + P2P | TRUE | TRUE | Commissioners considering appendix on wind permitting to set guidelines | 2025-02-07 | 815 | 178 |  |  |  | 346 | 0 |  |  | 0
| Lee Onshore Wind & Solar Ordinance |  | Onshore Wind & Solar | Lee County | Potential |  | 19111 | IA | ACE | Ordinance | [7 empty] | Organizing only | TRUE | TRUE | Board of Commissioners has been drafting new wind and solar regulations. Likely target date of April 2025~ | 2025-04-07
| New York Rapid Act |  | Onshore Wind & Solar | New York State | Potential |  |  | NY | ACE | Legislation | Public Hearing |  |  | Hearing Details | 2025-02-19 |  |  | Organizing only | TRUE | FALSE | The NY Department of Public Service is holding a public hearing regarding the RAPID act which gives the state broader control to review projects. | 2025-04-07
| Daviess Solar Ordinance |  | Solar | Daviess County | Potential |  | 21059 | KY | Laurie | Ordinance | Public Hearing |  |  |  | 2025-02-20 |  |  | Digi + P2P | TRUE | TRUE | HOLD: Fiscal Court enacted a 12 month moratorium on rewewables at their first reading of the potential new ordinance. Enacted ordinance for 1000 ft setback. | 2025-04-07
| Surprise BESS Ordinance |  | BESS | Surprise | Potential | Surprise | 4013 | AZ | AZ Siting Table | Ordinance | Public Comment Period | [6 empty] | Digi + P2P | TRUE | TRUE | The city is likely to schedule a public hearing soon. It is a good time for BESS support messages ahead of the hearings. HOLD UNTIL NEXT STEPS FROM LEGAL | 2025-04-07
| Livingston Energy Storage | Vesper Energy | BESS | Otsego County | Potential |  | 26137 | MI | ACE | Project | Pre Application | 300 | 0.3 |  |  |  |  | Digital ads only | FALSE | TRUE | Ground softening ads. A nice way to break in with a new developer. The developer just hosted the first of a series of community meetings. No application has been submitted yet. | 2025-04-07
| Hanover BESS | Northland Power | BESS | Town of Hanover | Potential | Hanover | 36013 | NY | ACE | Project | Pre Application | 250 | 0.25 |  | 2025-02-24 |  |  | Digi + P2P | TRUE | TRUE | Town Board public hearing to gauge public input regarding the presence of such a facility in the town. | 2025-04-07
| Yellow Barn Solar | CS Energy | Solar | Tompkins County | Win |  | 36109 | NY | ACE | Project | Public Comment Period | 160 | 0.16 |  |  | 2025-02-20 |  | Peer to Peer only | TRUE | TRUE | Public hearing for Yellow Barn Solar. The state has issued a draft permit for the project in December. One of the last remaining hurdles is local input, though approval is ultimately with the state. It is important to show local support for a project like this so the state sees it is not just opposition. | 2025-04-07 | 0 | 0 | 228 | 64 |  |  | 81 |  |  |  | Article citing approval
| Grass Lake Solar | NextEra | Solar | Grass Lake Township | Potential | Grass Lake Township | 26075 | MI | ACE | Ordinance | Public Hearing | 100 | 0.1 |  |  |  |  | Digi + P2P | TRUE | TRUE | Town supervisor/trustees to hold public hearing by end of month of Feb - Decision to come by early March on mutually agreed upon ordinance with NextEra | 2025-04-07 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| New Frontiers Solar Park | EDPR | Solar | Breckinridge County | Win |  | 21027 | KY | Laurie | Project | Public Comment Period | 100 | 0.1 |  |  | 2025-03-20 |  | Digital ads only | FALSE | TRUE | The project is in front of the PSC for approval now and accepting comment. | 2025-03-24 | 61116 | 11570 | 8704 | 8760 |  |  | 110
| Darden Energy Center | Intersect Power | Solar + BESS | Fresno County | Potential |  | 6019 | CA | ACE | Project | Public Comment Period | 6100 | 6.1 |  |  | 2025-04-21 |  |  | FALSE | FALSE | This is the first project to move this far in CA’s new “opt-in” regulatory process for largescale renewable projects which dramatically speeds up reviews and approvals for large scale projects. Project must receive a final determination within 270 days from application deemed complete. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Blue Lake BESS | Power Transitions | BESS | Blue Lake | Potential | Blue Lake | 6023 | CA | ACE | Project | Public Hearing | 20 | 0.02 | Blue Lake, CA - BESS Project - Planning Doc | 2025-02-25 | 2025-03-25 |  | Digi + P2P | TRUE | TRUE | This hearing is regarding whether to move forward with an agreement to sell 2 acres to the developer. It is NOT for a project permit. City will take lead on permitting if/when the project is ready to submit for a CUP | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Allen County Solar Ordinance |  | Solar | Allen County | Active |  | 18003 | IN | Solar United Neighbors Indiana | Ordinance | Public Hearing | [7 empty] | FALSE | FALSE | Public hearings around a solar ordinance in March/April of 2025 | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Valley Farms Energy Storage | NextEra | BESS | Pinal County | Potential |  | 4021 | AZ | AZCE | Project | Public Hearing | 400 | 0.4 | [5 empty] | FALSE | FALSE | Project was just recommended for denial last week by the planning commission (5-2 vote). In 4-6 weeks it will be heard by the Board of Supervisors. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ironwood Transmission Line | Energy West (NextEra) | Transmission | Yuma County | Potential |  | 4027 | AZ |  | Project | Developer Community Meeting | 3000 | 3 |  |  | 2025-04-01 |  | Digi + P2P | TRUE | TRUE | Pre-application, upcoming intervention point. Developer community meeting held by Energy West upcoming. Multi-state project that may traverse BLM land, number of regulatory approvals needed as this will requre permits from both state and federal agencies including CEQA and NEPA approvals. Expected to take 4 years to get all regulatory approvals. | 2025-04-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Flickertail Solar | Savion | Solar | Richland County | Pending |  | 38077 | ND | ACE | Project | Public Hearing | 300 | 0.3 | Richland County, ND - Flickertail Solar - Planning Doc | 2025-03-25 |  |  | Digi + P2P | TRUE | TRUE | The project is up for approval on a state level, as it is over 50MW in size. March 25th is the date of the ND PSC’s public hearing to determine approval of the siting permit required to move forward with the project. | 2025-05-07 | 103822 | 7153 | 0 | 0 | 680 | 0 | 0 | 1 | 0 | 1
| Gibson Solar | Open Road Renewables | Solar | King George County | Pending |  | 51099 | VA | Curate | Project | Public Hearing | 134 | 0.134 | King George County, VA - Gibson Solar Project - Planning Doc | 2025-04-01 |  |  | Digi + P2P | TRUE | TRUE | The approval for this project lies with the county, with 2 steps remaining: 1.) Planning Commission Recommendation and 2.) Board of Supervisors next hearing for this project will be held on April 15th by the Board of Supervisors. | 2025-04-07 | 4866 | 706 | 19 | 9 | 2324 | 0 | 0 | 11 | 0
| Midwater Energy Storage | Spearmint Energy | BESS | Freeborn County | Active |  | 27047 | MN | ACE | Project | Public Comment Period | 150 | 0.15 | Freeborn County MN - Midwater Energy Storage BESS - Planning Doc | 2025-04-07 | 2025-04-21 |  | Digi + P2P | TRUE | TRUE | In the first stage in the Minnesota state review process. Open comment period is accepting comments regarding suggestions for the Environmental Assessment (EA). After the EA is complete, there will be public hearings and another comment period to accept general support/opposition comments on the project. | 2025-05-07 | 70714 | 20442 | 0 | 0 | 0 | 2544 | 102 | 0 | 0 | 0
| Antlers Road Solar | RWE | Solar | Mecklenburg County | Active |  | 51117 | VA | ACE | Project | Public Hearing | 90 | 0.09 |  |  |  |  | Organizing only | TRUE | FALSE |  | 2025-05-07 | 0 | 0 | 28 | 22 | 2372 | 0 | 0 | 5 | 0 | 5
| Little Prairie Hybrid | BayWa r.e. | Solar + BESS | Champaign County | Win |  | 17019 | IL | Greenlight | Project | Public Hearing | 270 | 0.27 | https://us.baywa-re.com/en/americas-cases/little-prairie | 2025-04-10 |  | https://citizenportal.ai/articles/2977427/Champaign-County/Illinois/Champaign-County-considers-zoning-approval-for-Little-Prairie-Solar-Project | Peer to Peer only | TRUE | FALSE | 5-1 vote by the Board APPROVED conditional use permit. | 2025-05-07 | 0 | 0 | 0 | 338 | 0 | 0 | 0 | 0 | 0
| Yellow Rosebush | Savion | Solar + BESS | Wasco County | Active |  | 41065 | OR | Greenlight | Project | Public Hearing | 800 | 0.8 | https://www.oregon.gov/energy/facilities-safety/facilities/Pages/YRB.aspx |  |  |  | Peer to Peer only | TRUE | FALSE | No set milestones currently, we are estimating there will be some in April. - GL | 2025-05-07 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
| Fort Watt BESS | Cypress Creek | BESS | Tarrant County | Active | Kennedale | 48439 | TX | Greenlight | Project | Public Hearing | 255 | 0.255 |  | 2025-04-24 | 2025-05-20 |  | Peer to Peer only | TRUE | FALSE | Planning & Zoning meeting on 4/24/25, City Council on 5/20/25 | 2025-05-07 | 0 | 0 | 0 | 170 | 178 | 0 | 0 | 0 | 0 |  |  | From GL: We had an interim victory in Tarrant County TX this week - the 201.4 MW Fort Watt BESS project being developed by Cypress Creek - with a unanimous victory (all 3 members present voted yes) at the planning and zoning commission.
| Purple Sage BESS | RWE | BESS | Collin County | Active | Weston | 48085 | TX | ACE | Project |  | 300 | 0.3 |  |  |  |  | Digital ads only | FALSE | TRUE |  | 2025-06-06 | [11 empty] | Working with RWE
| San Luis Obispo OSW | CET | Offshore Wind | San Luis Obispo County | Active |  | 68154 | CA | Greenlight | Project | Project Hearing |  |  |  | 2025-03-25 |  |  | Peer to Peer only | TRUE | FALSE |  | 2025-06-06 | 0 | 0 | 0 |  | 757 | 20 |  | 9
| Buffalo Burr Solar + BESS |  | Solar + BESS | Pueblo County | Potential |  | 8101 | CO | Greenlight | Project

## Internal List (Oct onwards) (hidden)
Name | Jurisdiction | Type | State | Upcoming Hearing | County | MW | Posted Date | Local Politics | Notes | News Articles |  |  | Po
County Ordinance 56 | Woodbury County | IA | Wind | September 17th, 24th, and October 1st
Nexamp 5 MW Solar project | Kendall County (Yorkville) | IL | Solar | September 11th 2024
Zoning Ordinance | Fayette County (Lexington) | KY | Solar | September 26th, 2024
Stark Wind Project | Herkimer County | NY | Wind | 2024-09-09
Grange Solar | Washington, Stokes, Richland, McArthur and Bloomfield Townships, Logan County, | OH | Solar | 2024-09-05
Firefly | Lawrence County/North Beaver Township | PA | Solar
Hazle Township Solar Project | Luzerne County (Hazle Township) | PA | Solar | Oct 7th 2024 - Zoning meeting
AES Corp 150 MW Settler Wind Project | Converse County (Glenrock) | WY | Wind | September 18th 2024
Nextera Clinton Wind Farm | Clinton County Board of Supervisors | Wind | IA | September 18 - discussion. No vote scheduled yet | Clinton County | N/A | 2024-08-30 | N/A - Reviewing current moratorium on accepting renewable overlay apps for wind passed in June, looking at changes to ordinance put in place in 2008. | More than 50 people spoke at their previous hearing in August. Contentious in the area. NextEra spoke at hearing | https://www.clintonherald.com/residents-discuss-county-wind-energy-ordinance/article_7aba017c-6bd7-11ef-8689-138aa8c79f7c.html | From Laurie
Black Moshannon (Ampliform/Prospect14) | Rush Township Board of Supervisors | Solar | PA | September 30 - public hearing for comment and possible adoption of zoning amendment | Centre County | 252MW | 2024-09-06 |  | Solar farm proposed on 1000+ acres of abandoned strip coal mine | https://www.theprogressnews.com/classifieds/community/public_notices/notice-of-public-hearing-rush-township-centre-county/ad_4cd60ad3-c2aa-579e-9e65-4139af67c6e9.html | https://www.centredaily.com/news/local/community/philipsburg/article289515780.html?fbclid=IwY2xjawFMSeFleHRuA2FlbQIxMQABHbkn5a2ZrOxalNovbpi16LuJPupGNptxlR7ZQCOlxvTutXyZGlUznAsuvg_aem_SiEVxCCdvA8S4f3Zd_y8MQ | https://www.blackmoshannonsolar.com/
Warwarsing East & Warwarsing West (Finlo Solar) | Town of Warwarsing Planning Board | Solar | NY | 2024-09-17 | Ulster County | 10MW (5 per site) | 2024-09-05 |  | Public hearing on lot line adjustment ordinance for project | https://shawangunkjournal.com/section/2024/09/05/hearing-notice-solar-energy-facility/369JDH?open=1&force_ignore_preferences=1
LU-Club Ford 1 | Hazle Twp. Zoning Hearing Board | Solar | PA | 2024-10-07 | Luzerne County | 20 MW | 2024-09-05 | 20 residents attended first hearing The proposed solar farm is the latest to be considered in Luzerne County. In recent weeks, the Lehman Twp Zoning Hearing Board and Nanticoke City Council rejected solar farms following lengthy hearings attended by hundreds of people in opposition. |  | https://archive.ph/Bo4Aa
NY Southport I (Delaware River Solar) | Southport Planning Board | Solar | NY | October 7 at 7pm | Chemung County | 14.6 Acres - tbd mw | 2024-09-04 |  | Community Solar | https://www.weny.com/story/51352390/public-hearing-set-for-possible-community-solar-farm-in-southport
Chaberton Solar Wild Turkey | Maryland Public Service Commission | Solar | MD | October 7 or 14 | Frederick County | 5 MW |  |  | Public comment hearing - Originally scheduled for Aug 29, rescheduled for October | https://energycentral.com/news/state-host-second-public-hearing-solar-facility-frederick-countys-rocky-ridge-area
Invenergy and NextEra are trying to develop - this would encompass all commercial wind projects and limit to 70 turbines total - there are already 50. | Floyd County Board of Supervisors | Wind | IA | 2024-10-09 | Floyd County | TBD | 2024-09-05 |  | This will be the 3rd hearing, board of supervisors seem poised to pass this ordinance that the developers are calling "poison" | https://www.charlescitypress.com/front/2024/09/05/split-floyd-county-board-maintains-rules-that-could-kill-future-wind-energy-projects/
TBD | Michigan Public Service Commission | Solar | MI | 2024-10-30 | Ingham County |  |  | Negative FB group https://www.facebook.com/groups/3963435933745616/ | Public Act 233 of 2023 generally preempted local siting control of certain utility-scale renewable energy facilities (solar, wind and battery storage facilities), and shifted it to the Michigan Public Service Commission (MPSC). Under PA 233, which goes into effect Nov. 29, 2024 . A CREO is an ordinance that provides for the development of utility-scale energy facilities within the local unit of government that is no more restrictive than provisions included in Section 226(8) of PA 233. | https://inghamtownship.com/2024/09/06/october-30-2024-630-p-m-notice-public-hearing-for-a-creo-ordinance/
TBD | Coweta County Board of Commissioners | Solar | GA | 2024-11-05 | Coweta County | 476 MW | 2024-09-11 |  | Would be largest solar facility in the state of GA | https://www.times-herald.com/news/county-continues-to-revise-proposed-solar-ordinance/article_e14a6b7c-7157-11ef-8f68-9fc45fcc9ffc.html
TBD - NextEra project - Likely Tsuga Solar | Richland Township Planning Commission | Solar | MI | TBD | Saginaw County | TBD |  | First hearing in September was to address the potential for solar in the community - there will be future hearings once NextEra submits materials for the actual approvals | NextEra is signing agreements with residents, has not submitted materials for approval for needed ordinances to county https://www.nexteraenergyresources.com/tsuga-solar.html | https://www.youtube.com/watch?v=m1wTChyTY-o https://www.abc12.com/news/local/hemlock-to-discuss-ordinance-change-as-firm-eyes-possible-solar-farm/article_0452c5ee-5694-11ef-bb2b-83c82fdccbdb.html
Red Rock Wind Energy Center |  | Wind | IA | Permit denied in September, reviewing county sites to see if they will re-submit. |  | 300 |  | Set up alert for Emmett and Dickinson County Iowa for permit hearings, monitor the Board of Adjustment Agendas to know when project is on docket. | From Laurie | https://www.radioiowa.com/2024/04/24/update-on-wind-farm-planned-in-three-northwest-iowa-counties/ | https://www.iowapublicradio.org/ipr-news/2023-09-20/wind-turbines-iowa-great-lakes-area | https://www.iowapublicradio.org/environment/2023-10-26/dickinson-county-board-rejects-invengery-permit-for-wind-turbines
Macon County Wind |  | Wind | IL | no developer information yet 2 IX applications 200MW each |  |  |  |  | From Laurie | https://khqa.com/news/local/macon-county-residents-discuss-their-concerns-over-wind-turbines | https://www.wandtv.com/news/farmers-consider-joining-wind-farms-in-southern-macon-county/article_bc4423fc-031a-11ed-bf14-575148de0442.html | https://maconcounty.illinois.gov/minutes-agendas/
Fox Solar - NextEra | Morgan Township (Oconto County) | Solar | WI | TBD | Oconto County | 100 | 2024-11-22 | First hearing in Nov '24 was very contentious. 15 people protested outside hearing. Lots of questions from the community and misinformation being echoed. Two board members who support NextEra and let them "use their land" were voted out of office in a recall election in 2022 with conflict of interest charges from residents. Referendum for supporting solar in 2023 showed 67% of residents voted NOT to support. | From Clean WI | https://www.greenbaypressgazette.com/story/news/local/oconto-county/2024/11/15/nextera-discusses-oconto-county-solar-energy-project-but-residents-arent-happy/76306856007/
Tenmile Creek Solar - Xcel | St Croix County | Solar | WI | TBD - Seeking CPCN in Q1 2025 | St Croix County | 350 (could expand to 650) | 2024-11-22 |  | From Clean WI

## For Consideration (hidden)
Input Date | Project Name | Developer | Project Type | Project Size | City | County | State | County FIPS | Partisan Voter Index | Next Key Date | What Happens on the Next Key Date | Project Stage | Public Opposition | Links | Notes 1 | Notes/Updates | Additional Notes
October 21. Still Researching | Wind Moratorium - Emmet County |  | Wind | Not provided |  | Emmet | IA | 19063 |  | 2024-10-24 | Public hearing on revised wind energy ordinance | Moratorium Imposed until January 31, 2025 | None specified | https://kiwaradio.com/news/emmet-county-temporary-moratorium-on-new-wind-turbines/ https://emmetcountyia.gov/wp-content/uploads/2024/10/2024.10.24-Agenda-for-public-hearing.pdf | The Emmet County Board of Supervisors has approved a temporary moratorium on new wind projects, with a public hearing scheduled to discuss ordinance revisions. | New wind ordinance to be discssed October 24
October 21. Still Researching | New Equity Energy |  | Solar | 4 MW |  | Henry | VA | 51089 |  | 2024-10-23 | Public hearings for special use permits for large-scale solar facilities | Public Hearing | None mentioned |  | Two large-scale solar farms are up for discussion in public hearings, with New Energy Equity applying for special use permits.
2024-10-30 | Red Rock Wind Energy Center | Invenergy | Wind | 300 MW |  | Emmet, Dickinson, Clay | IA |  |  | TBD | Unclear | Permit denied. Looking for new site | Yes | https://redrockwindenergycenter.invenergy.com/ | Expected 300 jobs and 8 FTE operations and manintenance, $241 Million payments to local economy
2024-10-30 | Carroll County Ordinance |  | Solar Ordinance | N/A |  | Carroll County | N/A |  |  | N/A | N/A | Ordinance adopted | N/A | Restrictive solar ordinance implemented despite community member opposition.
2024-10-30 | Swift County Review |  | Solar and Wind Farm Moratorium | N/A |  | Swift County | N/A |  |  | N/A | N/A | No moratorium adopted | N/A | Swift County decided against implementing a moratorium on solar and wind projects despite public hearings.
2024-10-30 | Skagit County Energy Storage Moratorium |  | Energy Storage Moratorium | N/A |  | Skagit County | WA |  |  | TBD | Commission will vote on whether to implement 6 mo moratorium while Planning Commission drafts BESS ordinance | Drafting ordinance | Yes- lots of organized opposition | Hearing on 6 mo moratorium while Planning Commission createds ordinance for BESS on ag-NRL zoned land. Held hearings on a temporary moratorium related to energy storage facilities on agricultural land. There is a 200 MW project that has applied called Goldeneye/Goldfinch. County Commission has expressed oppossion to it Ultimately, the state has jurisdiction to site and approve projects. The WA Energy Facility Site Evaluation Council will make recomendation to Governor who will ultimately approve project | https://www.king5.com/article/tech/science/environment/skagit-county-moratorium-proposed-lithium-ion-energy-storage-facility/281-37d02bf5-07d8-4522-8fdf-d5cb4de34151 https://www.skagitcounty.net/Departments/Home/press/082824.htm https://www.efsec.wa.gov/about-efsec/certification-process?utm_medium=email&utm_source=govdelivery https://www.seattletimes.com/seattle-news/climate-lab/why-a-skagit-county-town-hopes-to-fight-off-a-battery-storage-project/
2024-10-30 | Atlantic Shores Offshore Wind |  | Offshore Wind Project | 1,510 MW |  | N/A | NJ |  |  | N/A | N/A | State House Commission approval received | N/A | New Jersey project advancing with state-level approvals, significant renewable energy addition.
2024-10-30 | New York Offshore Wind Leases |  | Offshore Wind Lease Approvals | Approx. 7 GW |  | New York Bight area | NY |  |  | N/A | N/A | Environmental review completed by BOEM | N/A | Multiple lease approvals to support New York's offshore wind goals by 2030.
2024-10-30 | Mayfield Solar Farm |  | Solar | 40 MW |  | Mayfield | NY |  |  | 2024-10-29 | Public Hearing | Zoning Approval Stage | Yes | A public hearing for a proposed solar farm in Mayfield, NY is scheduled.
2024-10-30 | Rush Township Solar Project |  | Solar |  |  | Rush Township | PA |  |  | 2024-10-29 | Public Hearing | Zoning Approval Stage | Yes | Rush Township denies 35- acre solar farm | https://www.tnonline.com/20241030/rush-denies-35-acre-solar-farm/
2024-10-30 | Lightstar Solar Project |  | Solar | 7 MW |  | Unity | PA |  |  | TBD | Public Hearing Continuation | Hearing Stage | Yes | Unity Township’s zoning hearing board continues a fourth session for hearing community concerns about a proposed solar farm.
2024-10-30 | Whitehall RE Moratorium |  | Solar, Wind, BESS | N/A |  | Whitehall | NY |  |  | 2024-11-20 | Public Hearing on Moratorium Extension | Moratorium Consideration | Yes | Whitehall plans to extend its renewable energy moratorium for an additional six months, allowing further consideration and public feedback. Appears proceedural - Board is ready to extend moratorium. | https://nyvtmedia.com/2024/10/23/whitehall-to-extend-solar-moratorium/#:~:text=WHITEHALL%20%E2%80%93%20The%20Town%20Board%20is,existing%20regulations%20governing%20such%20developments. https://www.washingtoncountyny.gov/DocumentCenter/View/25318/Town-Whitehall-Moratorium-with-SEQRAFS
2024-10-30 | Mount Storm Wind Project |  | Wind | N/A |  | Grant County | WV |  |  | TBD | Public Feedback at PSC Hearing | Permit Modification Requested | Mixed | NedPower proposes replacing existing wind turbines with larger models in the Mount Storm area, with public feedback noted at the PSC hearing. | https://wvmetronews.com/2024/10/25/nedpower-mount-storm-llc-gets-positive-public-feedback-for-their-proposal-to-replace-132-wind-turbines-with-78-larger-models/
2024-10-30 | Franklintown Farm Solar Project |  | Solar | Not specified |  | Jefferson County | WV |  |  | Not specified | Approval for conditional use permit | Permitting | Yes | Project approved for conditional use permit by the local zoning board.
2024-10-30 | Vesper Energy Battery Storage |  | Battery Storage | 500 |  | Katy | TX |  |  | Sept 23, 2024 | Special Use Permit (SUP) application hearing | Rejected | Yes | Council rejected the SUP application for a 500 MW battery storage facility.
2024-10-30 | BlueWave Solar |  | Solar | 10 mW |  | Northfield | MA |  |  | 2024-12-01 | Public hearing continuation | Permitting | Not specified | Ongoing public hearing process; project still under review.
2024-10-30 | East Point Energy |  | Battery Storage | 61.2 |  | Talbot County | MD |  |  | 2024-11-07 | Second public hearing for special use permit | Permitting | Not specified | Proposal for a 61.2 MW battery storage facility; community input to be gathered.
2024-10-30 | Katy Battery Storage |  | Battery Storage | TBD |  | Katy | TX |  |  | TBD | Project proposal rejected | Planning | Yes | Proposal for battery storage facility adjacent to public school was rejected by city council due to location concerns.
2024-10-30 | Cass County Solar |  | Solar | 265 MW |  | Cass | NE |  |  | 11/5 or 11/19 meeting | County Commission will vote on project | Permitting | Yes | The planning commission recommended a denial of the permit on 10/21. County Comission will vote next month | https://www.3newsnow.com/papillion-lavista-ralston-bellevue/cass-county-400m-solar-project-goes-to-a-vote-next-month https://www.casscountyne.gov/board-of-commissioners-meetings-agendas https://www.nexteraenergyresources.com/cass-county-solar.html
2024-10-30 | Lodestar Solar |  | Solar | 3 MW |  | Torrington | CT |  |  | 2025-02-01 | Decision on permit application | Permitting | Yes | Public meeting held, but decision on Lodestar's solar project delayed to early 2025.
2024-10-30 | NIMBUS Wind |  | Wind | 180 MW |  | Carroll County | AR |  |  | N/A | Final approval coming | Permitting | Yes | Carroll County Judge set to sign final piece of agreement to start construction. County's only interest is in permitting the roads. Because the county doesn't have planning and zoning, the County has no authority to regulate. Developer is Scout Clean Energy | https://www.ky3.com/2024/09/09/judge-says-controversia-wind-farm-carroll-county-ark-moving-forward/
2024-10-30 | Hughes County Wind Farm | RWE | Wind | 238 MW |  | Hughes County | OK |  |  | Unclear | Unclear | Josh to contact developer | Yes |  | https://americas.rwe.com/our-energy/onshore-wind/onshore-wind-projects-and-locations/prairie-wolf-wind-farm/
2024-10-22 | Volney Solar Farm |  | Solar | 5 MW | Voleny | Oswego | NY | 36075 |  | Public hearing upcoming | Discussion of financial assistance | Awaiting financial assistance approval | N/A |  | Volney solar project is pending financial assistance approval.
2024-10-22 | Halifax County Solar Ordinance Changes |  | Solar Ordinance | N/A |  | Halifax | VA | 51083 | 57% GOP | 2024-11-19 | Public hearing on ordinance changes. Joint meeting of County Commission & County Planning Board | If they chose, Planning Board and County Commissions could do back to back votes to make the ordinance law. | N/A | https://www.yourgv.com/business/local_business/rules-set-to-tighten-for-solar-in-halifax-county/article_21414076-8caf-11ef-8c0b-c32b19d81cde.html https://www.yourgv.com/news/local_news/halifax-county-board-flips-power-back-on-for-solar/article_d4c4c020-5422-11ef-97bf-874048c86b47.html | Halifax County is revisiting its solar ordinance - adding vegetation buffers around solar projects, boosting setbacks. There is a a proposed density cap of 3% of land within a 5 mile radius. Unclear if this is prohibitive. Does not appear to be | There are 6+ solar project applications the city has received during the moratorium that are awaiting review. One could be ready for public hearings ASAP once the ordinance is passed. And they anticipate more applications coming in as soon as they move forward on the ordinance. | In August, Board of Supervisors unanimously agreed to lift the moratorium on solar after four months, citing that they had enough time to research. Solar applications are "backing up" according to the PLanning Commission. The big issue now is the solar density cap and the proposal to reduce it from 5% to 3%
2024-10-22 | Erving Solar Array |  | Solar | 250 kW | Erving | Franklin | MA | 25011 |  | Continuation of public hearing | Further project discussion | Planning | N/A | https://www.recorder.com/Erving-Planning-Board-seeks-more-details-on-proposed-solar-array-on-River-Street-57525417 | Erving continues discussion on a proposed solar array.
2024-10-22 | Buckfield Solar Projects Moratorium |  | Solar Moratorium | N/A | Buckfield | Oxford | ME | 23017 |  | Town meeting scheduled | Vote on moratorium. A special town meeting will be held Oct. 29, to vote on whether to place a 180-day moratorium on commercial solar projects. It will begin at 6:30 p.m. at the Town Office. | Moratorium stage | N/A |  | Planning Board wants a moratorium so they can update regs before any more projects are approved.
2024-10-22 | Wabash County Wind Ordinance |  | Wind Ordinance | N/A |  | Wabash | IL | 17185 |  | 2024-10-21 | Review wind ordinance | Discussion phase | Unknown | https://wsjd.fm/new-blog-1/2024/10/21/wabash-county-board-of-commissioners-agenda | Wabash County reviewing wind ordinance at 10/21 meeting | County of Commissioners agenda did not show wind ordinance.
2024-10-22 | Jackson County Wind Ordinance |  | Wind Ordinance | N/A |  | Jackson | IA | 19097 | 62% GOP in 2020 Presidential | November 18 - Planning Commission Meeting | County has had a moratorium since May 2023 while drafting a wind ordinance for the first time. On November 18 they will discuss new findings on additional topics - like setbacks from cemeteries, ice thrown from blades, and vote on whether to send the ordinace to the County Commission | Final draft stage | Major opposition. Very organized. Opposition FB group in Jackson & Clinton counties has 2k members. Public commenters (video of 10/21 hearing) include concerns about water contamination from drilling during construction, ice falling from blades, noise, light flicker from blades, concerns about maintenance/decommisioning | https://jacksoncounty.iowa.gov/files/meetings/2024-11-18_agenda_1979.pdf https://www.telegraphherald.com/news/tri-state/article_94a5b8c8-907c-11ef-9fe4-0fae27ad2bc9.html | Jackson County Zoning Board discussed final draft of wind ordinance, with local concerns raised. Commissioner in attendence said "We certainly want to sustain our quality of life and our natural resources. We also need to be very respectful of land ownership, so there’s a fine line to draw there.” | Planning Commision Board Chair appears very level and proud of the ordinance and how it takes into consideration resident concerns like setbacks, noise, wildlife etc. (video interview) Draft ordinance is wind development friendly compared to many others. Reasonable setbacks, allowable in all but R-1 residential districts.
2024-10-22 | Fayette County Solar Farm Zoning |  | Solar | 88-acre | Georges Township | Fayette | PA | 42051 |  | None, project denied | Request denied | Denied | Unknown |  | Fayette County denied zoning exception for 88-acre solar farm in Georges Township.
2024-10-22 | Village of Diamond Solar and Wind Moratorium |  | Solar, Wind |  | Village of Diamond | Grundy | IL | 17063 |  | 2024-03-24 | 6 month moratoriu is either extended or lifts. Once Comprehensive Plan approved, solar moratorium will lift. |  |  | https://www.wcsjnews.com/news/local/diamond-mayor-talks-about-two-solar-farm-projects-moratorium-on-solar/article_36025b6e-8afa-11ef-a224-6be0e1f6f418.html https://www.villageofdiamond.org/wp-content/uploads/2023/10/09-24-24-2.pdf | The village passed a moratorium on commercial solar and wind energy systems. After installing two solar projects in town, they put in place a moratorium while they go through Comprehensive Plan. Mayor is supportive of solar, has had good experience with two prior developments. When Comp plan is approved, will allow more solar again. | JOSH CONTACTING TO UNDERSTAND TIMING | Diamond is in Grundy and Will Counties
2024-10-22 | Muhlenberg Solar Farm | Lost City Renewables LLC & TVA | Solar | 250 MW |  | Muhlenberg | KY | 21177 | Very early stages. TVA doesn't have purchase contract with Lost CIty yet. Earliest would be construction starting in 2-3 years. Opposition is already quite fierce and united. | 2024-10-29 | Public meeting with project reps from 6-8pm at Penrod Missionary Baptist Church to learn more about the project | Planning | Yes - neighbors circulating a petition to protect the 1300 acres from development. | https://www.14news.com/2024/10/15/everything-you-need-know-about-proposed-solar-farm-muhlenberg-co/ https://www.tristatehomepage.com/news/muhlenberg-county-residents-concerned-about-solar-farm-development/ |  | contact@lostcitysolar.com or call (843) 510-5254
2024-10-22 | Ørsted Long Island Wind Project (offshore) |  | Wind | 1.5 GW |  | Suffolk | NY | 36103 |  | TBD | TBD | Proposal submitted |  |  | Ørsted submitted a proposal for a 1.4 GW wind project, expected to power 1 million homes. to NY State Energy Reseach and Development Authority. Approval of Long Island Wind hinges on its selection by NYSERDA, the successful negotiation of an Offshore Wind Renewable Energy Certificate (OREC) agreement, and a final investment decision from Ørsted. Project would begin in 2033
2024-10-22 | Washington County Wind Ordinance |  | Wind |  |  | Washington | IA | 17189 |  | 2024-09-17 | County passed restrictive wind ordinance |  | Yes | https://www.southeastiowaunion.com/news/washington-county-wind-ordinance-passes/#:~:text=WASHINGTON%20%E2%80%94%20Washington%20County%20Supervisors%20have,source%20in%20the%20foreseeable%20future. | Final ordiance includes windmill setbacks of 1/2 mile from occupied residences and a clause for developers to pay home owners for reduced home property values. Developers are pulling back, feeling the Commission is not friendly to wind
2024-10-21 | Michigan Wind and Solar Law Class Action |  | Wind/Solar Law | N/A |  |  | MI |  |  | N/A | N/A | Legal action | Yes | https://www.13abc.com/2024/10/22/michigan-communities-band-together-with-lawsuit-state-zoning-battle/ | Class action lawsuit brought by towns and cities across MI challenges new Michigan wind and solar law that Gretchen Whitmer passed last year, goes into effect end of November
2024-10-21 | East Point Solar Project |  | Solar Battery Storage | 60 MW |  | Pittsylvania | VA | 51143 |  | 2024-11-19 | Vote postponed for concerns. Next hearing 11/19 | Hearing postponed to 11/19 | Yes - lots of opposition. Most comments surround fears of battery fires. Community knows litte about the project, according to Board of Commissioners | https://godanriver.com/news/local/article_379240f2-8b68-11ef-95c8-9b53fe052332.html https://www.pittsylvaniacountyva.gov/home/showpublisheddocument/5717/638648647994500000 | Vote delayed by one month to address public concerns on battery storage. | Simpson Energy Center, developer, asked to postpone the decision a month to address some of the concerns with a public meeting and the board of supervisors agreed. The meeting will be held on October 28th at Hurt Elementary School.
2024-10-21 | Prairie County Wind Zoning Ordinance |  | Wind Farm | N/A |  | Prairie | MT | 30079 |  | 2024-10-30 | Public meeting on options for zoning related to wind energy. 5:30pm @ Terry Community Center | First County meeting. Public input | Yes | https://www.terrytribune.com/news/zoning-related-to-wind-farms-will-be-focus-of-oct-30-meeting/article_d0aabf10-8a75-11ef-a192-2b39139ac768.html | Public hearing set to discuss zoning wind. A number of County landowners have leases with development starting 2026. Some residents have raised concerns about decommissioning, changing landscape from turbines.
2024-10-21 | Panther Grove Wind LLC |  | Wind Farm | 400 MW | Taylorville | Christian | IL | 17021 |  | TBD | Unclear | Landowner dispute - developer negotiating with 7 historic properites as identified by state board as having visual impacts from proposed turbines | Yes | https://www.breezecourier.com/2024/10/17/panther-grove-wind-llc-filed-application-for-npdes/ https://www.power-technology.com/data-insights/power-plant-profile-panther-grove-wind-energy-us/?cf-view | Panther Grove Wind LLC filed application for hearing on project permit. State agency found that 7 historic properties will have "adverse visual effects" so dev is now trying to work with these owners. | JOSH CONTACTING DEVELOPER FOR MORE INTEL
2024-10-21 | Emmet County Wind Turbine Moratorium |  | Wind Turbine Moratorium | N/A |  | Emmet | IA | 19063 |  | 2024-10-17 | Wind turbine moratorium decision | Moratorium approval | Yes |  | Emmet County imposes a temporary moratorium on wind turbine permits.
2024-10-21 | Ochoa Energy Storage Facility |  | Battery Storage | 500 MW | Katy | Harris | TX | 48201 |  | 2024-10-14 | Public hearing | Planning | Yes |  | Public hearing scheduled for the Ochoa Energy Storage facility to prevent blackouts. | Katy City Council voted on battery storage facility after public opposition. | Katy is in Harris, Waller & Fort Bend Counties
2024-10-21 | Chelsea Flatiron Energy Battery Storage |  | Battery Storage | N/A | Chelsea | Suffolk | MA | 51800 |  | N/A | Zoning board decision | Zoning | Yes |  | Chelsea Zoning Board approves special permit for Flatiron Energy storage.
2024-10-21 | Pittsylvania County Battery Storage |  | Battery Storage | N/A |  | Pittsylvania | VA | 51143 |  | N/A | Public hearing | Planning | Yes |  | Pittsylvania supervisors push back vote on battery storage after public hearing.
2024-10-21 | Hartland Solar and Battery Storage Ban |  | Solar and Battery Storage | N/A | Hartland | Niagara | NY | 36063 |  | N/A | Law advancing after public hearing | Ban under review | Yes |  | Hartland reviews law to ban industrial solar and battery storage projects.
2024-10-21 | Solar Moratorium - Town of Chili |  | Solar | Projects from 25 kW AC to 25 MW | Chili | Monroe | NY | 36055 |  | 2024-11-13 | Discussion on a six-month moratorium on Tier 3 solar energy system approvals so City can create regulations for future development | Moratorium Proposal | No specific opposition noted | http://www.townofchili.org/notices/#:~:text=PLEASE%20TAKE%20NOTICE%2C%20that%20a,in%20the%20Town%20of%20Chili. https://ecode360.com/documents/CH0024/public/753095484.pdf | The Town of Chili is considering a six-month moratorium on Tier 3 solar energy systems, which will be discussed in a public hearing.
2024-10-21 | Solar Ordinance - Great Bend | Acciona Energy | Solar | 300 MW | Great Bend | Barton | KS | 20009 | 77% GOP in 2020 | 2024-11-25 | On November 25, the City Council will review another round of recommendations from Planning Commission after the Coucil sent the ordinace back to them to tweak language around general liability insurance and groundwater testing. This is the first solar ordinance in the County. | Draft Ordinance | 15 people showed up to 10/21 meeting and one vocal member of opposition spoke. One key concern is proximity of the project to Cheyenne Bottoms - the largest wetlands in the interior US. Though it has been pointed out that housing developments, the county dump and oil wells are present near the Bottoms already. | https://www.gbtribune.com/news/local-news/city-returning-solar-regs-to-planning-commission/ | Solar regulations within the 3-mile zoning jurisdiction of Great Bend are up for discussion at the next city council meeting. Part of the proposed project by Acciona is within the 3-mile limit so it falls under this jurisdiction, not the county. | Project would be two 150-MW installations in the county. Land is leased with option to build by the developer. Benefits include up to 300 construction workers, 30 long term jobs for maintenance/operations, $1.6 Million in tax revenue for county. Some power may stay local in barton County. | Article outlining the history of the solar fight in Barton County
2024-10-21 | Battery Storage Moratorium - Village of Wilson |  | Battery Storage Moratorium |  | Village of Wilson | Niagara | NY | 36063 |  | 2025-10-01 | Public hearing on battery storage moratorium | Moratorium Imposed following a July 2023 battery fire in Lyme, Jefferson County | No opposition noted | https://www.lockportjournal.com/news/local_news/battery-storage-moratorium-approved-in-village-of-wilson/article_fc4d5db4-8d5c-11ef-b738-5f6d81cc929d.html | The village board approved a moratorium on renewable energy systems utilizing battery storage.
2024-10-17 | Zoning Ordinance Amendment for Solar, Wind and Battery Energy Systems |  | Solar/Wind/Battery |  | Worth Township | Sanilac | MI | 26151 | 72% GOP 2020 | 2024-10-28 | Public Hearing @ 6:30pm Worth Township Hall | Planning | Unknown | https://worthtownshipmi.gov/wp-content/uploads/2024/10/DOC072.pdf | The public hearing will discuss the zoning ordinance amendment for solar wind and battery storage systems
2024-10-17 | Croom Road Solar Plant |  | Solar | 5 MW |  | Prince George's | MD | 24033 |  | 2024-10-24 | Public Hearing | Planning | Unknown |  | A public hearing is scheduled for a proposed 5 MW solar plant.
2024-10-17 | Owasco Solar Facility |  | Solar | 7.4 MW | Owasco | Cayuga | NY | 36011 |  | Unknown | Public Hearing | Planning | Yes |  | Residents voiced concerns at the public hearing about the solar facility.
2024-10-17 | Ontario 4 LLC Solar Facility |  | Solar | 5 MW |  | Ontario | NY | 36069 |  | Unknown | Public Hearing | Planning | Unknown |  | The Ontario County IDA held a public hearing for the solar project.
2024-10-17 | Bennington Solar Moratorium |  | Solar | Unknown | Bennington Township | Wyoming | NY | 36121 |  | 2024-10-22 | Public Hearing | Planning | Unknown |  | A public hearing for extending the 6 month solar moratorium has been rescheduled.\ for OCtober 22
2024-10-17 | Darden Clean Energy Project |  | Solar and Battery Storage | 1.15 GW solar + 4600 MWh battery |  | Fresno | CA | 6019 |  | 2024-10-16 | Public Hearing | Planning | Unknown |  | The California Energy Commission will hold a public hearing for this large solar and battery storage project.
2024-10-17 | Mount Storm Wind Farm Expansion |  | Wind | 300 MW |  | Grant | WV | 54023 |  | 2024-10-24 | Public Comment Hearing, WV public service commission | Planning | Unknown | https://www.psc.state.wv.us/press/2024/Press_20241007111243.pdf | Public comments are invited regarding modifications to the wind farm project.
2024-10-17 | Clinton County Wind Moratorium |  | Wind | Unknown |  | Clinton | IA | 19045 |  | 2024-12-31 | Moratorium Expires | Planning | Lots of opposition - 500 town members came to last meeting asking for moratorium |  | The wind farm moratorium was extended while officials hold public hearings.
2024-10-17 | Oyster Bay Battery Storage Moratorium |  | Battery Storage |  | Oyster Bay | Nassau | NY | 36059 |  | Moratorium expired on October 14. Likely will extend another 6 months | Moratorium extension |  | Yes, many residents speaking out with safety concerns - citing fire risk. Arguement to delay allowing these projects until batteries are safer | https://antonmediagroup.com/east-oyster-bay-residents-plead-with-town-board-to-extend-battery-moratorium/?utm_medium=email&_hsenc=p2ANqtz-_HBCHUnD-kKtFZL2SbWGggaGnit209hEwQ91t2B_s8g6q64ErHDuvFS4NyuSM3v08cpMwqptR0ybPDYIffz3bbcpiSwDRZe32yoKfZIcakPqf1WJg&_hsmi=329487830&utm_content=329487830&utm_source=hs_email
2024-10-17 | Brooks County GA Solar Moratorium |  |  |  |  | Brooks | GA | 13027 | 60% GOP 2020 | 2025-02-01 | Moratorium Expires Feb 2025 giving county commissioners time to hear community concerns. |  | Yes - recent public meeting was overflowing with opposition citing concerns for ruining the rural landscape, noise compaints. | https://www.wctv.tv/2024/09/12/brooks-county-residents-rally-solar-panel-restrictions/ https://www.kait8.com/2024/09/16/rural-residents-say-they-are-fed-up-with-crop-farms-turning-into-solar-farms-bringing-noise/ https://wwals.net/2024/09/11/solar-in-brooks-county-town-hall-2024-09-12/ | Lots of opposition though some speaking up for property rights. One of the commissioners has a lease with a solar company. many existing leases will be able to move forward once the moratorium ends. Locals want more regulation and to slow down solar development.
2024-10-10 | Jupiter Power Battery Storage |  | Battery | Not listed | Saline Township | Washtenaw | MI | 26161 | 46.83 | 2024-10-08 | Public hearing on potential battery plant | Early stage/Pre-application | Opposed by residents | https://www.mlive.com/news/ann-arbor/2024/10/officials-weigh-local-control-vs-state-regulations-for-potential-saline-township-battery-plant.html | Local municipalities have until November 29, 2024 to pass their own renewables ordinances, called CREOs. If they do not, they cede regulatory authority to the Michigan Public Services Commission. Includes utility-scale renewable energy facilities (solar, wind and battery storage facilities). A CREO is an ordinance that provides for the development of utility-scale energy facilities within the local unit of government that is no more restrictive than provisions included in Section 226(8) of PA 233.
2024-10-10 | Acton Energy Storage Project |  | Battery | 400 MW | Acton | Los Angeles | CA | 6037 |  | 2024-10-24 | Public hearing on battery storage project | Permitted | Opposed by residents
2024-10-10 | Scotts Bluff Solar Energy Zoning |  | Solar | Ordinance |  | Scotts Bluff | NE | 31157 |  | 2024-10-14 | Public hearing on new zoning regulations | Draft Ordinance | Not mentioned | https://ruralradio.com/kneb-fm/news/public-hearing-scheduled-for-revamped-scotts-bluff-county-solar-energy-zoning-regs/ | Negative FB group https://www.facebook.com/groups/3963435933745616/ | Unclear when the Board will vote to approve the new solar regulations
2024-10-10 | TBD |  | General Renewables Ordinance | N/A |  | Ingham | MI | 26065 |  | 2024-10-30 | Public hearing | Draft Ordinace | Yes | https://inghamtownship.com/2024/09/06/october-30-2024-630-p-m-notice-public-hearing-for-a-creo-ordinance/ Negative FB group https://www.facebook.com/groups/3963435933745616/ | Local municipalities have until November 29, 2024 to pass their own renewables ordinances, called CREOs. If they do not, they cede regulatory authority to the Michigan Public Services Commission. Includes utility-scale renewable energy facilities (solar, wind and battery storage facilities). A CREO is an ordinance that provides for the development of utility-scale energy facilities within the local unit of government that is no more restrictive than provisions included in Section 226(8) of PA 233. | Josh left message with county clerk re: October 30 CREO public comment date. there is no October 30 meeting date currently on the county calendar
2024-10-10 | TBD - NextEra project - Likely Tsuga Solar |  | Richland Township Planning Commission | Solar | Richlannd Township | Saginaw | MI | 26145 |  | TBD | Public Hearing | Pre-application |  | https://www.youtube.com/watch?v=m1wTChyTY-o https://www.abc12.com/news/local/hemlock-to-discuss-ordinance-change-as-firm-eyes-possible-solar-farm/article_0452c5ee-5694-11ef-bb2b-83c82fdccbdb.html | NextEra is signing agreements with residents, has not submitted materials for approval for needed ordinances to county https://www.nexteraenergyresources.com/tsuga-solar.html | First hearing in September was to address the potential for solar in the community - there will be future hearings once NextEra submits materials for the actual approvals
2024-10-10 | Pinal County Solar Projects (Cactus Flower, Frontier Solar East, Ore Town Solar, Tap Solar-BLM land) |  | Solar | 1462 MW |  | Pinal | AZ | 4021 |  | 2024-10-30 | Board of Supervisors will discuss amendments to allow projects to proceed. Citizen advisory committee & planing and zoning commission report out to Board. | Planning. | Yes - residents aren’t pleased with a project that upsets their view and tourist attraction. City of Maricopa is fighting development claiming they have already planned to develop 4k houses & 2 elementary schools on the land. | https://www.pinalcentral.com/maricopa_monitor/news/solar-applications-bombard-pinal-county/article_548cb27e-5a8e-11ef-8df2-cbef43f2ee37.html https://www.inmaricopa.com/city-planners-protest-solar-farm-zoning-proposal/ | https://www.pinalcentral.com/casa_grande_dispatch/area_news/pinal-board-approves-large-solar-farm-in-narrow-vote/article_17fce1e8-2e89-11ef-b099-0baf8bf3acf5.html | Interesting angle: many farmers are out of water so selling to solar developers is an attractive option for the land. Commission is generally friendly to solar projects as they fit into the County's general plan. They approved a 1600 acre solar farm (3-2 vote) in July | Developer - Sawtooth Dev Co Kimley-Horn/Keith Nichter 602-313-7206 Operator - Copia Power. Legal rep: Jordan Rose - , Rose Law Group Scottsdale AZ
2024-10-03 | Vega SES 6 Solar and Battery Storage Project |  | Solar + Battery Storage | 320 acres | Brawley | Imperial | CA | 6025 |  | 2024-10-01 | Project approval hearing | Approved | Not mentioned
2024-10-03 | Moorpark Battery Energy Storage System (BESS) |  | Battery Storage | 100MW/400MWh | Moorpark | Ventura | CA | 6111 |  | Not specified | Project zoning discussions | Proposed | Not mentioned
2024-10-03 | Hanover Solar Facility |  | Solar | 1,500 acres |  | Hanover | VA | 51085 |  | Not specified | Project discussion by supervisors | Rejected | Yes
2024-10-03 | Nimbus Wind Farm Project |  | Wind | Not specified |  | Carrol | AK | 5015 |  | TBD - public comment period (date not set) | Information meeting for public comment | Proposed | Not mentioned
2024-10-03 | Whetstone Wind Project |  | Wind | Not specified |  | Gunnison | CO | 8051 |  | 2024-10-08 | Final public hearing | Final review | Not mentioned
2024-10-03 | Invenergy Wind Projects (Lyon County) |  | Wind | 250 MW |  | Lyon | MN | 27083 |  | TBD | Told commission they had 90% of land for project secured. Moving forward (Sept 10) | Pre-Permit application | Not mentioned
2024-10-03 | Atlantic Shores Offshore Wind Projects (1 and 2) |  | Offshore Wind | 5.25 GW |  |  | NJ |  |  | Not specified | Federal review and approval process | Approved by federal government | Yes
2024-10-03 | TBD |  | Solar | 476 MW |  | Coweta | GA | 13077 |  | 2024-11-05 | Coweta County Board of Commissioners meeting with public comment | Commission discussing Solar ordinance because of proposal to build largest solar project in Georgia | Yes | https://www.times-herald.com/news/county-continues-to-revise-proposed-solar-ordinance/article_e14a6b7c-7157-11ef-8f68-9fc45fcc9ffc.html | Field pilot potential, digital outreach bearing in mind the black out dates on Meta
2024-10-03 | Nedpower Mount Storm Modification (replacing existing turbines) |  | Wind | 300 MW (existing) |  | Grant | WV | 54023 |  | 2024-10-24 | Public comment hearing on modification ot allow fewer and larger turbines to replace existing turbines | Permitting | No. Project has community support. | https://therealwv.com/2024/10/08/nedpower-mount-storm-modification-public-comment-hearing-set/#:~:text=The%20company%2C%20Nedpower%20Mount%20Storm,comments%20filed%20with%20the%20Commission. | Only positive comments have been received thus far. Unless that changes, may cancel the hearing. This is to replace 132 smaller turbines with 78 larger ones
2024-10-03 | Plymouth Wind Energy |  | Wind |  |  | Plymouth | IA | 19149 |  | 2024-10-16 | Supervisors meeting on wind area projects | Informational | None reported |  | Reference in minutes to "adding culverts and roads in the County Wind Urban Renewal Plan." Does not seem relevant to us.
2024-09-26 | US Wind Expansion Project |  | Offshore Wind | Not specified | Ocean City | Worcester | MD | 24047 |  | 2024-10-16 | Public hearing on US Wind's request to revise and expand the offshore wind project | PROJECT APPROVED | Yes
2024-09-26 | Paddlefish Solar Project |  | Solar | 350 MW |  | Wells | IN | 18179 |  | 2025-02-01 | Moratorium will lift - hearing dates tbd | Proposed, impacted by moratorium | Implied | https://www.insideindianabusiness.com/articles/huntington-county-puts-temporary-ban-on-solar-projects | 7 months from the last hearing | Reach out to EDF - initiate contact. We noticed that you all proposed this. Research county commission - voting history etc. Get in touch with Miranda and voting data on the County.
2024-09-26 | Royalton Battery Storage Moratorium |  | Battery Storage | triggered by 5 MW storage proposal | Royalton | Niagara | NY | 36063 |  | 21-Oct-24 @ 7pm | Public hearing to extend moratorium on battery storage projects | Moratorium extension | Yes | https://www.lockportjournal.com/news/local_news/royalton-eyeing-extension-on-battery-storage-moratorium/article_1629bcea-80f7-11ef-ba51-af4885b37f80.html
2024-09-26 | Birch Coulee Solar Project |  | Solar | 125 MW |  | Renville | MN | 27129 |  | October 9 @ 6pm | MN public utilities commission discussing project | Site permit application | Not mentioned | https://www.wctrib.com/news/local/site-in-minnesotas-renville-county-could-be-home-to-245m-solar-project
2024-09-26 | Stearns County Solar Gardens |  | Solar | 5 MW | Sartell | Benton | MN | 27009 |  | Not specified | Public hearing on amendments to county land use and zoning ordinance | Permit approval | Not mentioned
2024-11-14 | Surry County BESS Ordinance | Clenera | BESS | 416-acre parcel |  | Surry | VA |  |  | 2024-12-16 | County Commission Hearing on guidelines for BESS. Current solar ordinance does not have BESS regulations |  | Unclear |  | On 10/28, Planning Commission Director discussed an application to amend zoning ordinance to allow BESS (sponsored by Clenera). CUP application can only be submitted and reviewed once ordinance is updated.
2024-11-14 | Purpole Sage Energy Center | Primenergy Solar | Solar+BESS | 800 MW | Pahrump | Nye | AZ |  |  | 2024-01-14 | BLM Public Hearing | Public Hearing on Jan 14, 2025 | FB Nye County Opposition Group
2024-11-19 | 2267-acre solar project |  | Solar | 2267 acres |  | Mohave County | Arizona |  |  |  |  | Proposed | YES | In October, Planning COmmission voted uninimously to deny. Planning staff also recommend denial | The Mohave County Board of Supervisors will discuss a 2267-acre solar project proposed for construction just outside Kingman at their Monday meeting. | Commission + staff are both against project. Low likelihood of approval | Just outside Kingman | Kingman
2024-11-19 | County considering zoning amendments for solar farms, wind turbines |  | Solar and Wind | Not specified |  | Schuylkill | Pennsylvania |  |  | 2024-11-13 | Public Hearing County Commissioners re: amendments to wind and solar ordinance | Planning | Not specified |  | The county is considering amendments to its zoning ordinance and its subdivision for solar farms and wind turbines. In October, Planning COmmission voted uninimously to deny. Planning staff also recommend denial | Commission + staff are both against project. Low likelihood of approval | Pottsville | Pottsville
2024-11-19 | Major Powerline |  | Wind and Solar Energy | Not Specified |  |  | Minnesota |  |  | 2024-11-25 | State accepting public comment through 11/25 | Proposal Stage | Not Specified |  | A major powerline proposed for southwest Minnesota to connect wind and solar energy to the grid. The state Public Utilities Commission is accepting comments on the project until Nov. 25. | Easy to engage - can submit online comments though portal is a bit clunky. | Southwest Minnesota | Not Specified
2024-11-19 | Groveland Twp. PC OKs battery storage ordinance |  | Battery Storage Ordinance | Not mentioned |  | Groveland Township | Not mentioned |  |  | 2024-10-22 | Groveland Township Planning Commission voted 5-2 to recommend to the township board | Recommended to the township board | Not mentioned |  | Following several months of deliberation, on Oct. 22, the Groveland Township Planning Commission voted 5-2 to recommend to the township board of ... |  | Groveland Township | Not mentioned
2024-11-19 | Seabed 'hydro spheres' to store offshore wind power |  | Offshore Wind Power Storage | Not mentioned |  | Not mentioned | US and Germany |  |  |  |  | Not mentioned | Not mentioned |  | The project involves the use of seabed 'hydro spheres' to store offshore wind power, backed by the US and Germany. |  | US and Germany | Not mentioned
2024-11-19 | Large lithium batteries next step in SD wind power growth |  | Wind Power Storage | Industrial-sized | Waverly | Not mentioned | South Dakota |  |  | Unable to find | Unclear | Not mentioned | Not mentioned | https://www.sdnewswatch.org/large-lithium-batteries-rural-solar-wind-power/ | A Florida energy company plans to build a set of industrial-sized lithium-ion batteries in South Dakota, US, as the next step in wind power growth. |  | South Dakota, US | Not mentioned
2024-11-19 | Center Township Solar Ordinance |  | Solar Ordinance | Not mentioned | Center Township | Indiana County | Pennsylvania |  |  |  |  | Approved for advertising | Not mentioned |  | The Center Township Supervisors approved advertising an ordinance concerning solar panels. |  | Center Township | Center Township
2024-11-19 | Georgia Power Battery Storage Projects |  | Battery Storage | Not Specified |  | Not Specified | Georgia |  |  | 2024-12-03 | GA PSC voting on whether to approve 4 BESS projects | Proposal Stage | Not Specified | https://psc.ga.gov/public-comments/ | Georgia Power executives pitched a proposal to build battery energy storage systems at four sites to the state Public. | Easy to engage - can submit online comments though portal is a bit clunky. | Atlanta | Atlanta | https://metroatlantaceo.com/news/2024/11/georgia-power-outlines-battery-storage-projects-psc/ | Note: this would add to energy storage which would be used for both solar and natural gas power
2024-11-19 | Weld Solar Project |  | Solar | One of the largest in the country |  | Weld | Colorado |  |  |  |  | Approved | Not mentioned | https://www.kunc.org/news/2024-11-04/weld-commissioners-approve-one-of-the-largest-solar-projects-in-the-country | The commissioners voted 4-1 to approve the massive project proposed by Magnum Feedyard owner Steve Gabel. Commissioner Mike Freemen was the lone. | Project approved | Weld | Weld
2024-11-19 | McDonough County Solar Ordinance |  | Solar Ordinance | Not Specified |  | McDonough | Illinois |  |  |  |  | Under Discussion | Not Specified |  | McDonough County Board Law & Legal Committee met to discuss the Solar Ordinance. They signed off on fee structure. Unclear if they voted on it and what comes next. | No upcoming dates. Tracking. | McDonough County | Not Specified | JOSH CONTACT RECORDER ON STATUS
2024-11-19 | Iroquois County Tax/Planning & Zoning Committee |  | Ordinance | Not mentioned |  | Iroquois County | Illinois |  |  |  |  | Not mentioned | Not mentioned |  | Iroquois County Tax/Planning & Zoning Committee met Nov. 4 to discuss Solar Ordinance. They are drafting the solar ordinance which will then influence the drafting of the wind and BESS ordinances. Still early stages. WIll track for other public hearing opportunities for ordinances. There were no public comments at the Nov 4. meeting. | No upcoming dates. Tracking. | Iroquois County | Not mentioned | JOSH CONTACT RECORDER ON STATUS
2024-11-19 | Johnson County Wind Farms Moratorium |  | Wind Farm | Not Specified |  | Johnson County | Indiana |  |  |  |  | Moratorium | Not Specified |  | 3-year commercial wind moratorium approved November 5. Permits and land use petitions for commercial wind farm projects are now temporarily halted as Johnson County officials review standards. |  | Johnson County | Not Specified
2024-11-19 | Randolph County Indiana Wind Project |  | Wind | Not mentioned |  | Randolph County | Indiana |  |  | 2027 | Project completion | Not mentioned | Not mentioned |  | The scope of the next planned wind farm in Randolph County is unchanged. | Wind project already approved. | Randolph County | Not mentioned
2024-11-19 | Washington County Public Notice |  | Wind | Not mentioned |  | Washington County | Iowa |  |  | 2024-11-18 | Public Hearing | Not mentioned | Not mentioned | https://www.southeastiowaunion.com/news/washington-county-residents-ask-for-stricter-wind-turbine-rules/ | The Board of Supervisors for Washington County, Iowa held a public hearing on a very restrictive wind ordinance. They said they would like to ban wind altogether but don't have authority to. | No. Too much opposition | Washington County | Not mentioned
2024-11-19 | Yavapai county approves solar ordinance |  | Solar | Not mentioned |  | Yavapai | Not mentioned |  |  |  |  | Under consideration | Not mentioned | https://www.dcourier.com/news/yavapai-county-approves-regulations-for-largescale-solar-operations/article_c2d93a56-9e20-11ef-b3b1-6fab5392d551.html | An amendment to the county ordinance on solar facilities, a Community Health Center update on recent successes and progress, and a discussion |  | Yavapai County | Not mentioned
2024-11-19 | Hazle Twp. solar farm |  | Solar farm | Massive |  | Not mentioned | Not mentioned |  |  |  |  | Pending | Not mentioned |  | Residents of the township will once again have to wait to find out if a massive solar farm will be approved along Club 40 Road near. |  | Club 40 Road near | Hazle Twp.
2024-11-19 | Lahaina Energy Partnership |  | Renewable Energy | Not mentioned |  | Not mentioned | Hawaii |  |  |  |  | Not mentioned | Not mentioned |  | The Lahaina Energy Partnership has formed in the wake of Maui's devastating fires to make sure community members have a voice in their energy. |  | Maui | Lahaina
2024-11-19 | Floyd Co. Supervisors to Form Mediation Team for Wind Turbine Ordinance |  | Wind Turbine Ordinance | Not mentioned |  | Floyd County | Iowa |  |  | Uncelar |  | Planning | Not mentioned |  | Floyd County's controversial ordinance regulating the construction of wind energy systems. If approved, amendments to the ordinance by Supervisors Jim | No go. Tremendous opposition on the Board. | Floyd County | Not mentioned
2024-11-19 | Local Law #2 — 2024 Solar Energy Systems Law |  | Solar Energy Systems Law | Not mentioned |  | Cattaraugus | New York |  |  |  |  | Not mentioned | Not mentioned | https://townofconklin.org/proposed-local-law-2-of-2024-solar-energy-systems-law/ | The Humphrey Town Board will hold a public hearing to discuss the law. They passed it. Similar law seen in other NY towns, like Conklin. |  | Humphrey | Humphrey
2024-11-19 | Monmouth County New Jersey Wind Project |  | Wind |  |  | Monmouth County | New Jersey | [7 empty] | The project is mentioned in relation to a Monmouth Conservation Foundation event. Further details about the project are not provided in the text. | No. Project approved in October. | Monmouth County | Monmouth
2024-11-19 | Riverbed Wind Project |  | Wind | Not mentioned |  | Sanilac | Michigan |  |  | 2024-11-07 |  | Appeal Stage | Not mentioned |  | The Fremont Township Zoning Board of Appeals (ZBA) heard an argument last month for overturning the planning commission's denial of the project. It was denied based on the Board's consideration of a non-expert report citing conerns about noise above 45 db. Dev says this is not true and appealing to Planning board to overturn decision. |  | Fremont Township, Sanilac County, Michigan | Fremont
2024-11-19 | Gabriel Battery Storage |  | Battery Storage | 2 GW |  | Not Mentioned | California |  |  |  |  | Not Mentioned | Not Mentioned |  | Aypa Power has secured California RA agreements with an investor-owned utility for the Gabriel Battery Storage project, totalling 2GWh. The outline plan was shown at a July meeting of the board of directors at CCA Peninsula Clean Energy. | FURTHER RESEARCH REQUIRED - unclear of stage | California | Not Mentioned
2024-11-19 | Cape Horn Solar Project |  | Solar Farm | 3 MW |  | Not mentioned | Not mentioned |  |  | 2024-11-12 | Virtual public hearing | Proposal stage | Not mentioned |  | Elk Development's proposal for a solar farm project. | Only 3 MW | Hampstead and Sykesville | Not mentioned
2024-11-19 | Carnesville Development Moratorium |  | Moratorium |  | Carnesville | Franklin | GA |  |  |  |  | Planning Stage | No |  | The Carnesville City Council voted unanimously to impose another nine-month moratorium on residential development. |  | Carnesville | Carnesville
2024-11-19 | Henderson battery storage project |  | Battery Storage | 12 MW |  | Henderson County | Kentucky |  |  |  |  | Rezoning approved | Not mentioned | https://www.yahoo.com/news/rezoning-recommended-henderson-battery-storage-034228169.html | The Henderson County Joint Planning Commission approved a proposal that will move plans forward for a battery storage project. | Only 12 MW | Henderson | Henderson
2024-11-19 | 5,500 acre solar farm | Geenex/Cobia | Project | 5,500 acres |  | Decatur County | Unknown |  |  | 2024-12-04 | Decatur County Board of Zoning Appeals meeting. Again held in large auditorium public comment on project | Zoning appeal. Project was denied on a 5-0 vote, developer is appealing. | Yes. Over 200 people signed up to comment at the meeting. Most were opposition. 4 landowners spoke up as well as some other supporters | https://www.greensburgdailynews.com/news/local_news/cobia-makes-pitch-for-5-500-acre-solar-farm/article_690686f6-9d1b-11ef-96b6-4fe7836635a4.html#:~:text=GREENSBURG%20%E2%80%93%20Geenex%2FCobia%20Solar%20made,Board%20of%20Zoning%20Appeals%20meeting. | Cobia makes pitch for a large solar farm, public hearings held through the summer |  | Decatur County | Decatur County
2024-11-19 | Proposed Surry battery storage facility |  | Battery Storage | Not mentioned |  | Surry | Not mentioned |  |  | 2024-12-16 | Hearing on the proposed ordinance change | Proposed | Not mentioned |  | A proposed battery storage facility off White Marsh Road in Smithfield. The hearing on the proposed ordinance change is scheduled for Dec. 16. |  | White Marsh Road | Smithfield
2024-11-19 | Bright Leaf Solar | Clenera | Solar + BESS | Large, but unclear on MW. Approx 733 acres. (6-8acre/MW estimate >> 92-122 MW |  | Edgecombe County | Not mentioned |  |  | 2024-12-02 | Public hearings | CUP submission | Not mentioned | https://cms5.revize.com/revize/edgecombenc/Agenda%20Packet%20_November%204%202024.pdf https://mytarborotoday.com/commissioners-enact-ninemonth-moratorium-on-new-solar-farms-p1899-106.htm#:~:text=In%20a%20unanimous%20vote%20that,3%20Solar%20Energy%20Conversion%20Systems. | Not mentioned |  | Edgecombe County | Not mentioned
2024-11-19 | Swift Creek Solar | Clenera | Solar + BESS | 100 MW |  | Edgecombe/ Rocky Mount County | Not mentioned |  |  | 2024-12-02 | Public hearings | Submitted Special Use Permit on October 24, 2024 | Not mentioned | https://cms5.revize.com/revize/edgecombenc/Agenda%20Packet%20_November%204%202024.pdf https://mytarborotoday.com/commissioners-enact-ninemonth-moratorium-on-new-solar-farms-p1899-106.htm#:~:text=In%20a%20unanimous%20vote%20that,3%20Solar%20Energy%20Conversion%20Systems. | Not mentioned |  | Edgecombe County | Not mentioned
2024-11-19 | Project Ponderosa |  | Solar Farm | $55 million | Laurens | Not mentioned | SC |  |  | 2024-12-09 | Public hearing | First reading | Not mentioned | https://www.golaurens.com/news/county-council-approves-first-reading-to-attract-55-million-solar-farm/article_7031b23e-a38d-11ef-bf29-3b6405123e55.html | A County advertisement says a public hearing will be conducted on Project Ponderosa at the Dec. 9 meeting | Appears the County is trying to pass the ordinance so that Duke energy will site the project in the County. So at first glance appears high probabilty of passage. | Not mentioned | Not mentioned
| Delta County Solar Ordinance |  | Solar |  |  | Delta | Pennsylvania |  |  | 2024-12-02 | Planning Commission Public Hearing | Draft Ordinance |  | https://www.dailypress.net/news/local-news/2024/11/delta-county-board-holds-public-hearing-on-renewable-energy-ordinance/
| New York Power Authority |  | All renewables | 40 projects |  |  | New York |  |  | 2024-12-09 | State accepting public comment on 40 RE project proposals before recommendation to the state legislature | Public Comment |  | https://www.binghamtonhomepage.com/news/local-news/nypa-seeking-public-comment-on-40-renewable-energy-projects/
2024-11-21 | Starke Central & North Bend Solar Projects | Hoosier Solar | Solar | 410 MW |  | Starke | Indiana |  |  | 2024-12-16 | Continued public hearing on tax abatement request from developer, and vote from County Council, who will send their recommendation to the Board of Commissioners. | Project permits have already been APPROVED. This isi strictly in regards to the tax abatement request. Will go to County Commissioners for final approval vote after Deceber 16. | Some. Even with supporters | https://wkvi.com/2024/11/starke-county-council-holds-public-hearing-on-tax-abatement-requests-from-hoosier-solar/ https://wkvi.com/2024/11/starke-county-council-to-hold-public-hearing-on-tax-abatement-requests-from-hoosier-solar/ | Community Benefits: 24.6 Million in tax revenue over 20 years, approx 10 jobs @ 75k each. Farmers spoke up in support. | County Commissioners voted this week on a motarotium for BESS but denied a motion for a moratorium (2-1) on solar projects.
| Emmett County Wind Ordinance (Red Rock Wind Energy Project) | Invenergy |  | 19 turbines | [5 empty] | 2025-01-31 | Temp wind moratorium expires. | CUP appplication. Project submitted application before wind moratorium enacted so it is moving forward. Overflow crowd (split supporters and opposition) at Planning Hearing on CUP on 11/20. Resuming 11/21. |  | https://kilrradio.com/kirl-news/769275 https://redrockwindenergycenter.invenergy.com/about-project | County has one of the highest average wind rates in the state of Iowa. Lots of interest in future wind dev.
| Morro Bay BESS Moratorium |  | Moratorium |  | Morro Bay |  | CA |  |  | 2025-01-01 | City staff urging Council to implement emergency ordinance to block any future BESS applications, until City has an ordinance. They will bring emergency ordinance to Council in Jan 2025 for vote |  |  | https://www.ksby.com/morro-bay/morro-bay-city-staff-to-develop-urgency-ordinance-on-future-battery-project-proposals | City Mayor says they are all for renewables, just want to make sure they are sited in the right place. Seems reasonable. | Gov Newsome passed a law allowing developers to come to the state for approval of solar and wind projects, instead of seeking local approvals. https://calmatters.org/environment/2022/08/renewable-energy-california-counties/ | https://www.ewg.org/news-insights/news-release/2024/04/fight-save-rooftop-solar-california-heads-state-supreme-court
2024-11-26 | Plus Power Battery Storage |  | BESS | 150 MW | Albuquerque |  | NM |  |  | TBD | Plus Power announced that its 150 MW / 600 MWh Corazon Energy Storage project was awarded a 20-year contract by Public Service Company | Planning. Still needs permit approvals. |  | https://www.prnewswire.com/news-releases/plus-power-battery-storage-project-wins-public-service-company-of-new-mexico-award-302315592.html?tc=eml_cleartime
2025-01-21 | Rancho Viejo Solar and Battery Storage | AES | Solar and BESS | 96MW Solar, 48 MW BESS | Santa Fe | Santa Fe | NM |  | Rancho Viejo Info Sheet (AES) | The Santa Fe Planning Commission will hold a vote on the proposed project on February 3, 2025. |  | Previous meetings: The developer held a pre-application meeting with the community on August 22, 2024 at the Santa Fe Community College. Santa Fe County Fire Department and the Growth Management Department will hold a virtual meetings in November to discuss hazard mitigation analysis and emergency response planning relative to the installation of Battery Energy Storage System (BESS) Projects. Santa Fe County held a Public Hearing with SLDC Hearing Officer, December 4 at the Santa Fe Community Convention Center. | https://www.aes.com/project/rancho-viejo-solar | Santa Fe County application page: https://www.santafecountynm.gov/growth-management/building-development/large-scale-renewable-energy-projects-2024/uaes | Sierra Club and 350.org are engaging publicly
2025-01-21 | Mora Line (under Lucky Corridor) | RETA and Lucky Corridor, LLC (owned by Ameren Transmission) are co-developers of the $83 million project | Transmission | 182 MW, enough to power 50,000 homes | The Mora Line route is entirely on private land |  | San Miguel County: Las Vegas Mora County: Wagon Mound, Watrous Colfax County: Springer Union County: Don Carlos | Estimated construction date is 2025 | Mora Line Info Sheet (Lucky Corridor) | TBD - more research needed | RETA and Lucky Corridor, LLC (owned by Ameren Transmission) are co-developers of the $83 million project | https://nmreta.com/transmission-lines/ | http://www.luckycorridor.com/MoraProject.html#info_openhouse | https://nmreta.com/mora-transmission-project/#:~:text=About%20the%20Mora%20Transmission%20Project,which%20has%20tremendous%20renewable%20resources. | 115-mile transmission line operating at 345kV and 115kV. The first segment stretches approximately 47 miles and operates at 345kV. It will connect the Don Carlos Wind Farm in Union County to a new Mora 345kV/115 kV Substation that will be located adjacent to and interconnect with the Springer Substation owned and operated by Tri-State Generation and Transmission Association (Tri-State). The second segment will step down to 115kV and extend 68 miles south to connect with the Arriba Substation near Las Vegas, NM that is owned and operated by Public Service Company of New Mexico (PNM).
Garden County NE Moratorium - DRAFTING

## Wider List (hidden)
State | County name | Project Name (If available)
AZ | Apache County
Cochise County
Coconino County
Gila County
Graham County
Greenlee County
| La Paz County | Ranegras Plains Energy Center
Maricopa County
Mohave County
Navajo County
Pima County
Pinal County
Santa Cruz County
Yavapai County
Yuma County
CA | Alpine County
Amador County
Butte County
Calaveras County
Colusa County
Contra Costa County
Del Norte County
El Dorado County
Fresno County
Glenn County
| Humboldt County | California Floating Wind
Imperial County
Inyo County
Kern County
Kings County
Lake County
Lassen County
Los Angeles County
Madera County
Marin County
Mariposa County
Mendocino County
Merced County
Modoc County
Mono County
Monterey County
Napa County
Nevada County
Placer County
Plumas County
Riverside County
Sacramento County
San Benito County
San Bernardino County
San Diego County
San Joaquin County
San Luis Obispo County
San Mateo County
Santa Barbara County
Santa Clara County
Santa Cruz County
| Shasta County | Fountain Wind
Sierra County
Siskiyou County
Solano County
Sonoma County
Stanislaus County
Sutter County
Tehama County
Trinity County
Tulare County
Tuolumne County
Ventura County
Yolo County
Yuba County
CO | Adams County
Alamosa County
Arapahoe County
Archuleta County
Baca County
Bent County
Boulder County
Chaffee County
Cheyenne County
Clear Creek County
Conejos County
Costilla County
Crowley County
Custer County
Delta County
Dolores County
Douglas County
Eagle County
El Paso County
Elbert County
Fremont County
Garfield County
Gilpin County
Grand County
Gunnison County
Hinsdale County
Huerfano County
Jackson County
Jefferson County
Kiowa County
Kit Carson County
| La Plata County | Hesperus Solar
Lake County
Larimer County
Las Animas County
Lincoln County
Logan County
Mesa County
Mineral County
Moffat County
Montezuma County
Montrose County
| Morgan County | Taelor Solar Project
Otero County
Ouray County
Park County
Phillips County
Pitkin County
Prowers County
Pueblo County
Rio Blanco County
Rio Grande County
Routt County
Saguache County
San Miguel County
Sedgwick County
Summit County
Teller County
Washington County
Weld County
Yuma County
DE | Kent County
New Castle County
Sussex County
IA | Muscatine County
ID | Ada County
Adams County
Bannock County
Bear Lake County
Benewah County
Bingham County
Blaine County
Boise County
Bonner County
Bonneville County
Boundary County
Butte County
Camas County
Canyon County
Caribou County
Cassia County
Clark County
Clearwater County
Custer County
Elmore County
Franklin County
Fremont County
Gem County
Gooding County
Idaho County
Jefferson County
Jerome County
Kootenai County
Latah County
Lemhi County
Lewis County
Lincoln County
Madison County
| Minidoka County | Lava Ridge
Nez Perce County
Oneida County
Owyhee County
Payette County
Power County
Shoshone County
Teton County
Twin Falls County
Valley County
Washington County
IL | Adams County
Alexander County
Bond County
Boone County
Brown County
Bureau County
Calhoun County
Carroll County
Cass County
Champaign County
Christian County
Clark County
Clay County
Clinton County
Coles County
Crawford County
Cumberland County
De Witt County
DeKalb County
Douglas County
Edgar County
Edwards County
Effingham County
Fayette County
Ford County
Franklin County
Fulton County
Gallatin County
Greene County
Grundy County
Hamilton County
Hancock County
Hardin County
Henderson County
Henry County
Iroquois County
Jackson County
Jasper County
Jefferson County
Jersey County
Jo Daviess County
Johnson County
Kane County
Kankakee County
Kendall County
| Knox County | Blackberry Solar
LaSalle County
Lawrence County
Lee County
Livingston County
Logan County
Macon County
Macoupin County
Madison County
Marion County
Marshall County
Mason County
Massac County
McDonough County
McHenry County
McLean County
Menard County
Mercer County
Monroe County
| Montgomery County | Grand Prairie Energy Park
Morgan County
Moultrie County
Ogle County
Peoria County
Perry County
Piatt County
Pike County
Pope County
Pulaski County
Putnam County
Randolph County
Richland County
Rock Island County
Saline County
Sangamon County
Schuyler County
Scott County
Shelby County
St. Clair County
Stark County
Stephenson County
Tazewell County
Union County
Vermilion County
Wabash County
Warren County
Washington County
Wayne County
White County
Whiteside County
Will County
Williamson County
Winnebago County
Woodford County
IN | Carroll County
| DeKalb County | Sculpin Solar
Huntington
| Wells County | Paddlefish Solar
KS | Allen County
Anderson County
Atchison County
Barber County
Barton County
Bourbon County
Brown County
Butler County
Chase County
Chautauqua County
Cherokee County
Cheyenne County
Clark County
Clay County
Cloud County
Coffey County
Comanche County
Cowley County
Crawford County
Decatur County
| Dickinson County | Hope Ridge Wind
Doniphan County
Douglas County
Edwards County
Elk County
Ellis County
Ellsworth County
Finney County
Ford County
Franklin County
Geary County
Gove County
Graham County
Grant County
Gray County
Greeley County
Greenwood County
Hamilton County
Harper County
Harvey County
Haskell County
Hodgeman County
Jackson County
Jefferson County
Jewell County
Johnson County
Kearny County
Kingman County
Kiowa County
Labette County
Lane County
Leavenworth County
Lincoln County
Linn County
Logan County
Lyon County
Marion County
Marshall County
McPherson County
Meade County
Miami County
Mitchell County
Montgomery County
Morris County
Morton County
Nemaha County
Neosho County
Ness County
Norton County
| Osage County | Auburn Harvest
| Osborne County | Rolling Prairie Wind Project
Ottawa County
Pawnee County
Phillips County
Pottawatomie County
Pratt County
Rawlins County
Reno County
Republic County
Rice County
Riley County
Rooks County
Rush County
Russell County
Saline County
Scott County
Sedgwick County
Seward County
Shawnee County
Sheridan County
Sherman County
Smith County
Stafford County
Stanton County
Stevens County
Sumner County
Thomas County
Trego County
Wabaunsee County
Wallace County
Washington County
Wichita County
Wilson County
Woodson County
Wyandotte County
MD | Dorchester County | Choptank
ME | Penobscot County | Bradley Solar
MN | Traverse County | Traverse Gap Wind Project
MO | Adair County
Andrew County
Atchison County
Audrain County
Barry County
Barton County
Bates County
Benton County
Bollinger County
Boone County
Buchanan County
Butler County
Caldwell County
Callaway County
Camden County
Cape Girardeau County
Carroll County
Carter County
Cass County
Cedar County
Chariton County
Christian County
Clark County
Clay County
Clinton County
Cole County
Cooper County
Crawford County
| Dade County | Buffalo Branch
Dallas County
Daviess County
DeKalb County
Dent County
Douglas County
Dunklin County
Franklin County
Gasconade County
Gentry County
Greene County
Grundy County
Harrison County
Henry County
Hickory County
Holt County
Howard County
Howell County
Iron County
Jackson County
Jasper County
Jefferson County
Johnson County
Knox County
Laclede County
Lafayette County
Lawrence County
Lewis County
Lincoln County
Linn County
Livingston County
Macon County
Madison County
Maries County
Marion County
McDonald County
Mercer County
Miller County
Mississippi County
Moniteau County
Monroe County
Montgomery County
Morgan County
New Madrid County
Newton County
Nodaway County
Oregon County
Osage County
Ozark County
Pemiscot County
Perry County
Pettis County
Phelps County
Pike County
Platte County
Polk County
Pulaski County
Putnam County
Ralls County
Randolph County
Ray County
Reynolds County
Ripley County
Saline County
Schuyler County
Scotland County
Scott County
Shannon County
Shelby County
St. Charles County
St. Clair County
St. Francois County
St. Louis County
Ste. Genevieve County
Stoddard County
Stone County
Sullivan County
Taney County
Texas County
Vernon County
Warren County
Washington County
Wayne County
Webster County
Worth County
Wright County
MS | Hinds County | Hinds Solar Project
MT | Beaverhead County
Big Horn County
Blaine County
Broadwater County
Carbon County
Carter County
Cascade County
Chouteau County
Custer County
Daniels County
Dawson County
Deer Lodge County
Fallon County
Fergus County
Flathead County
Gallatin County
Garfield County
Glacier County
Golden Valley County
Granite County
Hill County
Jefferson County
Judith Basin County
Lake County
Lewis and Clark County
Liberty County
Lincoln County
Madison County
McCone County
Meagher County
Mineral County
Missoula County
| Musselshell County | Musselshell
Park County
Petroleum County
Phillips County
Pondera County
Powder River County
Powell County
Prairie County
Ravalli County
Richland County
Roosevelt County
Rosebud County
Sanders County
Sheridan County
Silver Bow County
Stillwater County
Sweet Grass County
Teton County
Toole County
Treasure County
Valley County
Wheatland County
Wibaux County
Yellowstone County
NE | Adams County
Antelope County
Arthur County
Banner County
Blaine County
Boone County
Box Butte County
Boyd County
Brown County
Buffalo County
Burt County
Butler County
Cass County
Cedar County
Chase County
Cherry County
Cheyenne County
Clay County
Colfax County
Cuming County
Custer County
Dakota County
Dawes County
Dawson County
Deuel County
Dixon County
Dodge County
Douglas County
Dundy County
Fillmore County
Franklin County
Frontier County
Furnas County
Gage County
Garden County
Garfield County
Gosper County
Grant County
Greeley County
Hall County
Hamilton County
Harlan County
Hayes County
Hitchcock County
Holt County
Hooker County
Howard County
Jefferson County
Johnson County
Kearney County
Keith County
Keya Paha County
Kimball County
Knox County
Lancaster County
Lincoln County
Logan County
Loup County
Madison County
McPherson County
Merrick County
Morrill County
Nance County
Nemaha County
Nuckolls County
Otoe County
Pawnee County
Perkins County
Phelps County
Pierce County
Platte County
Polk County
Red Willow County
Richardson County
Rock County
Saline County
Sarpy County
Saunders County
| Scotts Blluff County | Situla Energy Project
Scotts Bluff County
Seward County
Sheridan County
Sherman County
Sioux County
Stanton County
Thayer County
Thomas County
Thurston County
Valley County
Washington County
Wayne County
Webster County
Wheeler County
York County
NJ | Atlantic County
Burlington County
Camden County
Cape May County
Cumberland County
Gloucester County
Hunterdon County
Mercer County
Monmouth County
Morris County
Ocean County
Passaic County
Salem County
Somerset County
Sussex County
Warren County
NM | Bernalillo County
Catron County
Chaves County
Cibola County
Colfax County
Curry County
De Baca County
Doña Ana County
Eddy County
Grant County
Guadalupe County
| Harding County | New Mexico North Path Project
Hidalgo County
Lea County
| Lincoln County | SunZia Wind
Los Alamos County
Luna County
| Mckinley County | New Mexico North Path Project
Mora County
Otero County
Quay County
Rio Arriba County
Roosevelt County
San Juan County
| San Miguel County | SunZia Wind
| Sandoval County | New Mexico North Path Project
| Santa Fe County | Rancho Viejo Solar
Sierra County
Socorro County
Taos County
| Torrance County | SunZia Wind
| Union County | New Mexico North Path Project
Valencia County
NV | Churchill County | Greenlink North
| Clark County | Greenlink West
| Esmeralda County | Greenlink West
| Eureka County | Greenlink North
| Lander County | Greenlink North
| Lyon County | Greenlink North & West
| Mineral County | Greenlink West
| Nye County | Greenlink West
| Storey County | Greenlink West
| White Pine County | Greenlink North
NY | Wayne County | Rosalen Solar Energy Center
OH | Erie County
| Greene County | Kingwood Solar
Warren County
OK | Adair County
Alfalfa County
Atoka County
Beaver County
Beckham County
Blaine County
Bryan County
Caddo County
Canadian County
Carter County
Cherokee County
Choctaw County
Cimarron County
Cleveland County
Coal County
Comanche County
Cotton County
Craig County
Creek County
Custer County
Delaware County
Dewey County
Ellis County
Garfield County
Garvin County
Grady County
Grant County
Greer County
Harmon County
Harper County
Haskell County
Hughes County
Jackson County
Jefferson County
Johnston County
Kay County
Kingfisher County
Kiowa County
Latimer County
Le Flore County
Lincoln County
Logan County
Love County
Major County
Marshall County
Mayes County
McClain County
McCurtain County
McIntosh County
Murray County
Muskogee County
Noble County
Nowata County
Okfuskee County
Oklahoma County
Okmulgee County
Osage County
Ottawa County
Pawnee County
Payne County
Pittsburg County
Pontotoc County
Pottawatomie County
Pushmataha County
Roger Mills County
Rogers County
Seminole County
Sequoyah County
Stephens County
Texas County
Tillman County
Tulsa County
Wagoner County
Washington County
Washita County
Woods County
Woodward County
OR | Baker County
Benton County
Clackamas County
Clatsop County
Columbia County
Coos County
Crook County
Curry County
Deschutes County
Douglas County
Gilliam County
Grant County
Harney County
Hood River County
Jackson County
Jefferson County
Josephine County
Klamath County
Lake County
Lane County
Lincoln County
Linn County
Malheur County
Marion County
Modoc County
Morrow County
Multnomah County
Polk County
Sherman County
Tillamook County
Umatilla County
Union County
Wallowa County
Wasco County
Washington County
Wheeler County
Yamhill County
PA | Armstrong County | Sunny Fields Rewnewable Energy Project
| Bradford County | Bradford Solar
Crawford County
Erie County
| Indiana County | Sunny Fields Rewnewable Energy Project
| Lawrence County | Firefly Solar
| McKean County | Amazon PA Project
| Potter County | Amazon PA Project
Somerset County
TX | Anderson County
Andrews County
Angelina County
Aransas County
Archer County
Armstrong County
Atascosa County
Austin County
Bailey County
| Bandera County | Rio Lago
Bastrop County
Baylor County
Bee County
Bell County
Bexar County
Blanco County
Borden County
Bosque County
Bowie County
Brazoria County
Brazos County
Brewster County
Briscoe County
Brooks County
Brown County
Burleson County
Burnet County
Caldwell County
Calhoun County
Callahan County
Cameron County
Camp County
Carson County
Cass County
Castro County
Chambers County
Cherokee County
Childress County
Clay County
Cochran County
Coke County
Coleman County
Collin County
Collingsworth County
Colorado County
Comal County
Comanche County
Concho County
Cooke County
Coryell County
Cottle County
Crane County
Crockett County
Crosby County
Culberson County
Dallam County
Dallas County
Dawson County
Deaf Smith County
Delta County
Denton County
DeWitt County
Dickens County
Dimmit County
Donley County
Duval County
Eastland County
Ector County
Edwards County
El Paso County
Ellis County
Erath County
Falls County
Fannin County
Fayette County
Fisher County
Floyd County
Foard County
Fort Bend County
Franklin County
Freestone County
Frio County
Gaines County
Galveston County
Garza County
Gillespie County
Glasscock County
Goliad County
Gonzales County
Gray County
Grayson County
Gregg County
Grimes County
Guadalupe County
Hale County
Hall County
Hamilton County
Hansford County
Hardeman County
Hardin County
Harris County
Harrison County
Hartley County
Haskell County
Hays County
Hemphill County
Henderson County
Hidalgo County
| Hill County | Aquilla
Hockley County
Hood County
Hopkins County
Houston County
Howard County
Hudspeth County
Hunt County
Hutchinson County
Irion County
Jack County
Jackson County
Jasper County
Jeff Davis County
Jefferson County
Jim Hogg County
Jim Wells County
Johnson County
Jones County
Karnes County
Kaufman County
Kendall County
Kenedy County
Kent County
Kerr County
Kimble County
Kinney County
Kleberg County
Knox County
La Salle County
Lamar County
Lamb County
Lampasas County
Lavaca County
Lee County
Leon County
Liberty County
Limestone County
Lipscomb County
Live Oak County
Llano County
Loving County
Lubbock County
Lynn County
Madison County
Marion County
Martin County
Mason County
Matagorda County
Maverick County
McCulloch County
McLennan County
McMullen County
Medina County
Menard County
Midland County
Milam County
Mills County
Mitchell County
Montague County
Montgomery County
Moore County
Morris County
Motley County
Nacogdoches County
Navarro County
Newton County
Nolan County
Nueces County
Ochiltree County
Oldham County
Orange County
Palo Pinto County
Panola County
Parker County
Parmer County
Pecos County
Polk County
Potter County
Presidio County
Rains County
Randall County
Reagan County
Real County
Red River County
Reeves County
Refugio County
Roberts County
Robertson County
Rockwall County
Runnels County
Rusk County
Sabine County
San Augustine County
San Jacinto County
San Patricio County
San Saba County
Schleicher County
Scurry County
Shackelford County
Shelby County
Sherman County
Smith County
Somervell County
Starr County
Stephens County
Sterling County
Stonewall County
Sutton County
Swisher County
Tarrant County
Taylor County
Terrell County
Terry County
Throckmorton County
Titus County
Tom Green County
Travis County
Trinity County
Tyler County
Upshur County
Upton County
Uvalde County
Val Verde County
Van Zandt County
Victoria County
Walker County
Waller County
Ward County
Washington County
Webb County
Wharton County
Wheeler County
Wichita County
Wilbarger County
Willacy County
Williamson County
Wilson County
Winkler County
Wise County
Wood County
Yoakum County
Young County
Zapata County
Zavala County
VA | Dinwiddie County | Sappony Solar
| Henry County | Axton Solar Project
| Pittsylvania County | Axton Solar Project
| Sussex County | Cabin Point Solar Project
WA | Adams County
Asotin County
Benton County
Chelan County
Clallam County
Clark County
Columbia County
Cowlitz County
Douglas County
Ferry County
| Franklin County | Horse Heaven Clean Energy Center
Garfield County
Grant County
Grays Harbor County
Island County
Jefferson County
King County
Kitsap County
Kittitas County
Klickitat County
Lewis County
Lincoln County
Mason County
Okanogan County
Pacific County
Pend Oreille County
Pierce County
San Juan County
Skagit County
Skamania County
Snohomish County
Spokane County
Stevens County
Thurston County
Wahkiakum County
Walla Walla County
Whatcom County
| Whitman County | Harvest Hills Wind Project
Yakima County
WV | Jefferson County
WY | Albany County
Big Horn County
Campbell County
Carbon County
Converse County
Crook County
Fremont County
Goshen County
Hot Springs County
Johnson County
Laramie County
Lincoln County
Natrona County
Niobrara County
Park County
Platte County
Sheridan County
Sublette County
Sweetwater County
Teton County
Uinta County
Washakie County
Weston County

## Longitudinal Study Counties (hidden)
State | County | Project Name
AZ | La Paz County | Ranegras Plains Energy Center
CA | Humboldt County | California Floating Wind
| Shasta County | Fountain Wind
Sutter County
CO | La Plata County | Hesperus Solar
Larimer County
| Morgan County | Taelor Solar Project
DE | Sussex County
IA | Muscatine County | NA
ID | Minidoka County | Lava Ridge
IL | Knox County | Blackberry Solar
Macoupin County
| Montgomery County | Grand Prairie Energy Park
Sangamon County
IN | Carroll County
| DeKalb County | Sculpin Solar
Huntington
| Wells County | Paddlefish Solar
KS | Dickinson County | Hope Ridge Wind
| Osage County | Auburn Harvest
| Osborne County | Rolling Prairie Wind Project
| Shawnee County | NA
MD | Dorchester County | Choptank
ME | Penobscot County | Bradley Solar
MN | Traverse County | Traverse Gap Wind Project
MO | Dade County | Buffalo Branch
| Saline County | --
MS | Hinds County | Hinds Solar Project
MT | Musselshell County | Musselshell
NE | Scotts Blluff County | Situla Energy Project
NM | Harding County | New Mexico North Path Project
| Lincoln County | SunZia Wind
| Mckinley County | New Mexico North Path Project
| San Miguel County | New Mexico North Path Project
SunZia Wind
| Sandoval County | New Mexico North Path Project
| Santa Fe County | New Mexico North Path Project
Rancho Viejo Solar
| Torrance County | SunZia Wind
| Union County | New Mexico North Path Project
NV | Churchill County | Greenlink North
New Mexico North Path Project
| Clark County | Greenlink West
| Esmeralda County | Greenlink West
| Eureka County | Greenlink North
| Lander County | Greenlink North
| Lyon County | Greenlink North
Greenlink West
| Mineral County | Greenlink West
| Nye County | Greenlink West
| Storey County | Greenlink West
| White Pine County | Greenlink North
NY | Wayne County | Rosalen Solar Energy Center
OH | Erie County
| Greene County | Kingwood Solar
Warren County
PA | Armstrong County | Sunny Fields Rewnewable Energy Project
| Bradford County | Bradford Solar
Crawford County
Erie County
| Indiana County | Sunny Fields Rewnewable Energy Project
| Lawrence County | Firefly Solar
| McKean County | Amazon PA Project
| Potter County | Amazon PA Project
Somerset County
TX | Bandera County | Rio Lago
Dallas County
| Hill County | Aquilla
VA | Dinwiddie County | Sappony Solar
| Henry County | Axton Solar Project
| Pittsylvania County | Axton Solar Project
| Sussex County | Cabin Point Solar Project
WA | Franklin County | Horse Heaven Clean Energy Center
| Whitman County | Harvest Hills Wind Project
WV | Jefferson County | Two projects

## Priority List (Old Greenlight) (hidden)
Name | Jurisdiction | State | Type | Upcoming Hearing
Sun Depot | City of Avondale (Maricopa County) | AZ | Battery Storage
Ordinance/Moratorium | Mohave County | AZ | Solar (Moratorium extended) | Moratorium extended (loss)
Ordinance/Moratorium | Yavapai County | AZ | Solar | Ongoing volunteer calls
Draconis Solar | Chino Valley - Yavapai County | AZ | Solar
Ordinance/Moratorium | Pinal County | AZ | Solar
Sun Dog | Pinal County | AZ | Solar
CA Offshore Wind | Multiple | CA | Offshore wind
Morro Bay Energy Storage Project | Morro Bay | CA | BESS
Moratorium | Mesa County | CO | Solar | Reversed (win)
Pivot Energy (Multiple) | Weld County | CO | Solar (community)
Taelor Solar | Weld and Morgan County | CO | Solar and BESS
Ordinance/Moratorium | San Miguel County | CO |  | September 11th 2024 link
Mountain Daisy Solar | Severance - Weld County | CO | Solar
McCracken | McCracken County | KY | Solar
MD Offshore Wind | Multiple | MD | Offshore Wind
Maine Wind Port | Town of Searsport | ME | Offshore Wind
NJ Offshore Wind | Multiple | NJ | Offshore wind
Rancho Viejo Solar | Santa Fe County | NM
Multiple | Long Island BESS & Propel Transmission | NY | Battery Storage; Transmission
NY Offshore Wind | Multiple | NY | Offshore wind
Clearmount Energy Center | Clermont County | OH | BESS | Last hearing 08/01; no updates
Bradford Solar | Bradford County | PA | Solar ordinance
Black Moshannon | Rush Township (Centre County) | PA | Solar
Ochoa Energy Storage | Harris, Fort Bend and Waller Counties (Katy) | TX | BESS
VA Offshore Wind | Virginia Beach | VA | Offshore wind
VA Offshore Wind | Multiple | VA | Offshore wind
Badger Hollow Wind | Iowa & Grant County | WI | Wind
Uplands Wind | Lafayette, Iowa & Grant County | WI | Wind
Vista Sands | State of WI (Portage County) | WI | Solar
Eastern Cotton tail | Fairfield | OH | Solar ordinance | https://www.edf-re.com/project/eastern-cottontail-solar-project/

## CountyFIPS (hidden)
name | state | fips
Abbeville County | SC | 45001
Acadia Parish | LA | 22001
Accomack County | VA | 51001
Ada County | ID | 16001
Adair County | IA | 19001
Adair County | KY | 21001
Adair County | MO | 29001
Adair County | OK | 40001
Adams County | CO | 8001
Adams County | ID | 16003
Adams County | IL | 17001
Adams County | IN | 18001
Adams County | IA | 19003
Adams County | MS | 28001
Adams County | NE | 31001
Adams County | ND | 38001
Adams County | OH | 39001
Adams County | PA | 42001
Adams County | WA | 53001
Adams County | WI | 55001
Addison County | VT | 50001
Aiken County | SC | 45003
Aitkin County | MN | 27001
ALABAMA | NA | 1000
Alachua County | FL | 12001
Alamance County | NC | 37001
Alameda County | CA | 6001
Alamosa County | CO | 8003
ALASKA | NA | 2000
Albany County | NY | 36001
Albany County | WY | 56001
Albemarle County | VA | 51003
Alcona County | MI | 26001
Alcorn County | MS | 28003
Aleutians East Borough | AK | 2013
Aleutians West Census Area | AK | 2016
Alexander County | IL | 17003
Alexander County | NC | 37003
Alexandria city | VA | 51510
Alfalfa County | OK | 40003
Alger County | MI | 26003
Allamakee County | IA | 19005
Allegan County | MI | 26005
Allegany County | MD | 24001
Allegany County | NY | 36003
Alleghany County | NC | 37005
Alleghany County | VA | 51005
Allegheny County | PA | 42003
Allen County | IN | 18003
Allen County | KS | 20001
Allen County | KY | 21003
Allen County | OH | 39003
Allen Parish | LA | 22003
Allendale County | SC | 45005
Alpena County | MI | 26007
Alpine County | CA | 6003
Amador County | CA | 6005
Amelia County | VA | 51007
Amherst County | VA | 51009
Amite County | MS | 28005
Anchorage Municipality | AK | 2020
Anderson County | KS | 20003
Anderson County | KY | 21005
Anderson County | SC | 45007
Anderson County | TN | 47001
Anderson County | TX | 48001
Andrew County | MO | 29003
Andrews County | TX | 48003
Androscoggin County | ME | 23001
Angelina County | TX | 48005
Anne Arundel County | MD | 24003
Anoka County | MN | 27003
Anson County | NC | 37007
Antelope County | NE | 31003
Antrim County | MI | 26009
Apache County | AZ | 4001
Appanoose County | IA | 19007
Appling County | GA | 13001
Appomattox County | VA | 51011
Aransas County | TX | 48007
Arapahoe County | CO | 8005
Archer County | TX | 48009
Archuleta County | CO | 8007
Arenac County | MI | 26011
ARIZONA | NA | 4000
ARKANSAS | NA | 5000
Arkansas County | AR | 5001
Arlington County | VA | 51013
Armstrong County | PA | 42005
Armstrong County | TX | 48011
Aroostook County | ME | 23003
Arthur County | NE | 31005
Ascension Parish | LA | 22005
Ashe County | NC | 37009
Ashland County | OH | 39005
Ashland County | WI | 55003
Ashley County | AR | 5003
Ashtabula County | OH | 39007
Asotin County | WA | 53003
Assumption Parish | LA | 22007
Atascosa County | TX | 48013
Atchison County | KS | 20005
Atchison County | MO | 29005
Athens County | OH | 39009
Atkinson County | GA | 13003
Atlantic County | NJ | 34001
Atoka County | OK | 40005
Attala County | MS | 28007
Audrain County | MO | 29007
Audubon County | IA | 19009
Auglaize County | OH | 39011
Augusta County | VA | 51015
Aurora County | SD | 46003
Austin County | TX | 48015
Autauga County | AL | 1001
Avery County | NC | 37011
Avoyelles Parish | LA | 22009
Baca County | CO | 8009
Bacon County | GA | 13005
Bailey County | TX | 48017
Baker County | FL | 12003
Baker County | GA | 13007
Baker County | OR | 41001
Baldwin County | AL | 1003
Baldwin County | GA | 13009
Ballard County | KY | 21007
Baltimore city | MD | 24510
Baltimore County | MD | 24005
Bamberg County | SC | 45009
Bandera County | TX | 48019
Banks County | GA | 13011
Banner County | NE | 31007
Bannock County | ID | 16005
Baraga County | MI | 26013
Barber County | KS | 20007
Barbour County | AL | 1005
Barbour County | WV | 54001
Barnes County | ND | 38003
Barnstable County | MA | 25001
Barnwell County | SC | 45011
Barren County | KY | 21009
Barron County | WI | 55005
Barrow County | GA | 13013
Barry County | MI | 26015
Barry County | MO | 29009
Bartholomew County | IN | 18005
Barton County | KS | 20009
Barton County | MO | 29011
Bartow County | GA | 13015
Bastrop County | TX | 48021
Bates County | MO | 29013
Bath County | KY | 21011
Bath County | VA | 51017
Baxter County | AR | 5005
Bay County | FL | 12005
Bay County | MI | 26017
Bayfield County | WI | 55007
Baylor County | TX | 48023
Beadle County | SD | 46005
Bear Lake County | ID | 16007
Beaufort County | NC | 37013
Beaufort County | SC | 45013
Beauregard Parish | LA | 22011
Beaver County | OK | 40007
Beaver County | PA | 42007
Beaver County | UT | 49001
Beaverhead County | MT | 30001
Becker County | MN | 27005
Beckham County | OK | 40009
Bedford city | VA | 51515
Bedford County | PA | 42009
Bedford County | TN | 47003
Bedford County | VA | 51019
Bee County | TX | 48025
Belknap County | NH | 33001
Bell County | KY | 21013
Bell County | TX | 48027
Belmont County | OH | 39013
Beltrami County | MN | 27007
Ben Hill County | GA | 13017
Benewah County | ID | 16009
Bennett County | SD | 46007
Bennington County | VT | 50003
Benson County | ND | 38005
Bent County | CO | 8011
Benton County | AR | 5007
Benton County | IN | 18007
Benton County | IA | 19011
Benton County | MN | 27009
Benton County | MS | 28009
Benton County | MO | 29015
Benton County | OR | 41003
Benton County | TN | 47005
Benton County | WA | 53005
Benzie County | MI | 26019
Bergen County | NJ | 34003
Berkeley County | SC | 45015
Berkeley County | WV | 54003
Berks County | PA | 42011
Berkshire County | MA | 25003
Bernalillo County | NM | 35001
Berrien County | GA | 13019
Berrien County | MI | 26021
Bertie County | NC | 37015
Bethel Census Area | AK | 2050
Bexar County | TX | 48029
Bibb County | AL | 1007
Bibb County | GA | 13021
Bienville Parish | LA | 22013
Big Horn County | MT | 30003
Big Horn County | WY | 56003
Big Stone County | MN | 27011
Billings County | ND | 38007
Bingham County | ID | 16011
Black Hawk County | IA | 19013
Blackford County | IN | 18009
Bladen County | NC | 37017
Blaine County | ID | 16013
Blaine County | MT | 30005
Blaine County | NE | 31009
Blaine County | OK | 40011
Blair County | PA | 42013
Blanco County | TX | 48031
Bland County | VA | 51021
Bleckley County | GA | 13023
Bledsoe County | TN | 47007
Blount County | AL | 1009
Blount County | TN | 47009
Blue Earth County | MN | 27013
Boise County | ID | 16015
Bolivar County | MS | 28011
Bollinger County | MO | 29017
Bon Homme County | SD | 46009
Bond County | IL | 17005
Bonner County | ID | 16017
Bonneville County | ID | 16019
Boone County | AR | 5009
Boone County | IL | 17007
Boone County | IN | 18011
Boone County | IA | 19015
Boone County | KY | 21015
Boone County | MO | 29019
Boone County | NE | 31011
Boone County | WV | 54005
Borden County | TX | 48033
Bosque County | TX | 48035
Bossier Parish | LA | 22015
Botetourt County | VA | 51023
Bottineau County | ND | 38009
Boulder County | CO | 8013
Boundary County | ID | 16021
Bourbon County | KS | 20011
Bourbon County | KY | 21017
Bowie County | TX | 48037
Bowman County | ND | 38011
Box Butte County | NE | 31013
Box Elder County | UT | 49003
Boyd County | KY | 21019
Boyd County | NE | 31015
Boyle County | KY | 21021
Bracken County | KY | 21023
Bradford County | FL | 12007
Bradford County | PA | 42015
Bradley County | AR | 5011
Bradley County | TN | 47011
Branch County | MI | 26023
Brantley County | GA | 13025
Braxton County | WV | 54007
Brazoria County | TX | 48039
Brazos County | TX | 48041
Breathitt County | KY | 21025
Breckinridge County | KY | 21027
Bremer County | IA | 19017
Brevard County | FL | 12009
Brewster County | TX | 48043
Briscoe County | TX | 48045
Bristol Bay Borough | AK | 2060
Bristol city | VA | 51520
Bristol County | MA | 25005
Bristol County | RI | 44001
Broadwater County | MT | 30007
Bronx County | NY | 36005
Brooke County | WV | 54009
Brookings County | SD | 46011
Brooks County | GA | 13027
Brooks County | TX | 48047
Broome County | NY | 36007
Broomfield County | CO | 8014
Broward County | FL | 12011
Brown County | IL | 17009
Brown County | IN | 18013
Brown County | KS | 20013
Brown County | MN | 27015
Brown County | NE | 31017
Brown County | OH | 39015
Brown County | SD | 46013
Brown County | TX | 48049
Brown County | WI | 55009
Brule County | SD | 46015
Brunswick County | NC | 37019
Brunswick County | VA | 51025
Bryan County | GA | 13029
Bryan County | OK | 40013
Buchanan County | IA | 19019
Buchanan County | MO | 29021
Buchanan County | VA | 51027
Buckingham County | VA | 51029
Bucks County | PA | 42017
Buena Vista city | VA | 51530
Buena Vista County | IA | 19021
Buffalo County | NE | 31019
Buffalo County | SD | 46017
Buffalo County | WI | 55011
Bullitt County | KY | 21029
Bulloch County | GA | 13031
Bullock County | AL | 1011
Buncombe County | NC | 37021
Bureau County | IL | 17011
Burke County | GA | 13033
Burke County | NC | 37023
Burke County | ND | 38013
Burleigh County | ND | 38015
Burleson County | TX | 48051
Burlington County | NJ | 34005
Burnet County | TX | 48053
Burnett County | WI | 55013
Burt County | NE | 31021
Butler County | AL | 1013
Butler County | IA | 19023
Butler County | KS | 20015
Butler County | KY | 21031
Butler County | MO | 29023
Butler County | NE | 31023
Butler County | OH | 39017
Butler County | PA | 42019
Butte County | CA | 6007
Butte County | ID | 16023
Butte County | SD | 46019
Butts County | GA | 13035
Cabarrus County | NC | 37025
Cabell County | WV | 54011
Cache County | UT | 49005
Caddo County | OK | 40015
Caddo Parish | LA | 22017
Calaveras County | CA | 6009
Calcasieu Parish | LA | 22019
Caldwell County | KY | 21033
Caldwell County | MO | 29025
Caldwell County | NC | 37027
Caldwell County | TX | 48055
Caldwell Parish | LA | 22021
Caledonia County | VT | 50005
Calhoun County | AL | 1015
Calhoun County | AR | 5013
Calhoun County | FL | 12013
Calhoun County | GA | 13037
Calhoun County | IL | 17013
Calhoun County | IA | 19025
Calhoun County | MI | 26025
Calhoun County | MS | 28013
Calhoun County | SC | 45017
Calhoun County | TX | 48057
Calhoun County | WV | 54013
CALIFORNIA | NA | 6000
Callahan County | TX | 48059
Callaway County | MO | 29027
Calloway County | KY | 21035
Calumet County | WI | 55015
Calvert County | MD | 24009
Camas County | ID | 16025
Cambria County | PA | 42021
Camden County | GA | 13039
Camden County | MO | 29029
Camden County | NJ | 34007
Camden County | NC | 37029
Cameron County | PA | 42023
Cameron County | TX | 48061
Cameron Parish | LA | 22023
Camp County | TX | 48063
Campbell County | KY | 21037
Campbell County | SD | 46021
Campbell County | TN | 47013
Campbell County | VA | 51031
Campbell County | WY | 56005
Canadian County | OK | 40017
Candler County | GA | 13043
Cannon County | TN | 47015
Canyon County | ID | 16027
Cape Girardeau County | MO | 29031
Cape May County | NJ | 34009
Carbon County | MT | 30009
Carbon County | PA | 42025
Carbon County | UT | 49007
Carbon County | WY | 56007
Caribou County | ID | 16029
Carlisle County | KY | 21039
Carlton County | MN | 27017
Caroline County | MD | 24011
Caroline County | VA | 51033
Carroll County | AR | 5015
Carroll County | GA | 13045
Carroll County | IL | 17015
Carroll County | IN | 18015
Carroll County | IA | 19027
Carroll County | KY | 21041
Carroll County | MD | 24013
Carroll County | MS | 28015
Carroll County | MO | 29033
Carroll County | NH | 33003
Carroll County | OH | 39019
Carroll County | TN | 47017
Carroll County | VA | 51035
Carson City | NV | 32510
Carson County | TX | 48065
Carter County | KY | 21043
Carter County | MO | 29035
Carter County | MT | 30011
Carter County | OK | 40019
Carter County | TN | 47019
Carteret County | NC | 37031
Carver County | MN | 27019
Cascade County | MT | 30013
Casey County | KY | 21045
Cass County | IL | 17017
Cass County | IN | 18017
Cass County | IA | 19029
Cass County | MI | 26027
Cass County | MN | 27021
Cass County | MO | 29037
Cass County | NE | 31025
Cass County | ND | 38017
Cass County | TX | 48067
Cassia County | ID | 16031
Castro County | TX | 48069
Caswell County | NC | 37033
Catahoula Parish | LA | 22025
Catawba County | NC | 37035
Catoosa County | GA | 13047
Catron County | NM | 35003
Cattaraugus County | NY | 36009
Cavalier County | ND | 38019
Cayuga County | NY | 36011
Cecil County | MD | 24015
Cedar County | IA | 19031
Cedar County | MO | 29039
Cedar County | NE | 31027
Centre County | PA | 42027
Cerro Gordo County | IA | 19033
Chaffee County | CO | 8015
Chambers County | AL | 1017
Chambers County | TX | 48071
Champaign County | IL | 17019
Champaign County | OH | 39021
Chariton County | MO | 29041
Charles City County | VA | 51036
Charles County | MD | 24017
Charles Mix County | SD | 46023
Charleston County | SC | 45019
Charlevoix County | MI | 26029
Charlotte County | FL | 12015
Charlotte County | VA | 51037
Charlottesville city | VA | 51540
Charlton County | GA | 13049
Chase County | KS | 20017
Chase County | NE | 31029
Chatham County | GA | 13051
Chatham County | NC | 37037
Chattahoochee County | GA | 13053
Chattooga County | GA | 13055
Chautauqua County | KS | 20019
Chautauqua County | NY | 36013
Chaves County | NM | 35005
Cheatham County | TN | 47021
Cheboygan County | MI | 26031
Chelan County | WA | 53007
Chemung County | NY | 36015
Chenango County | NY | 36017
Cherokee County | AL | 1019
Cherokee County | GA | 13057
Cherokee County | IA | 19035
Cherokee County | KS | 20021
Cherokee County | NC | 37039
Cherokee County | OK | 40021
Cherokee County | SC | 45021
Cherokee County | TX | 48073
Cherry County | NE | 31031
Chesapeake city | VA | 51550
Cheshire County | NH | 33005
Chester County | PA | 42029
Chester County | SC | 45023
Chester County | TN | 47023
Chesterfield County | SC | 45025
Chesterfield County | VA | 51041
Cheyenne County | CO | 8017
Cheyenne County | KS | 20023
Cheyenne County | NE | 31033
Chickasaw County | IA | 19037
Chickasaw County | MS | 28017
Chicot County | AR | 5017
Childress County | TX | 48075
Chilton County | AL | 1021
Chippewa County | MI | 26033
Chippewa County | MN | 27023
Chippewa County | WI | 55017
Chisago County | MN | 27025
Chittenden County | VT | 50007
Choctaw County | AL | 1023
Choctaw County | MS | 28019
Choctaw County | OK | 40023
Chouteau County | MT | 30015
Chowan County | NC | 37041
Christian County | IL | 17021
Christian County | KY | 21047
Christian County | MO | 29043
Churchill County | NV | 32001
Cibola County | NM | 35006
Cimarron County | OK | 40025
Citrus County | FL | 12017
Clackamas County | OR | 41005
Claiborne County | MS | 28021
Claiborne County | TN | 47025
Claiborne Parish | LA | 22027
Clallam County | WA | 53009
Clare County | MI | 26035
Clarendon County | SC | 45027
Clarion County | PA | 42031
Clark County | AR | 5019
Clark County | ID | 16033
Clark County | IL | 17023
Clark County | IN | 18019
Clark County | KS | 20025
Clark County | KY | 21049
Clark County | MO | 29045
Clark County | NV | 32003
Clark County | OH | 39023
Clark County | SD | 46025
Clark County | WA | 53011
Clark County | WI | 55019
Clarke County | AL | 1025
Clarke County | GA | 13059
Clarke County | IA | 19039
Clarke County | MS | 28023
Clarke County | VA | 51043
Clatsop County | OR | 41007
Clay County | AL | 1027
Clay County | AR | 5021
Clay County | FL | 12019
Clay County | GA | 13061
Clay County | IL | 17025
Clay County | IN | 18021
Clay County | IA | 19041
Clay County | KS | 20027
Clay County | KY | 21051
Clay County | MN | 27027
Clay County | MS | 28025
Clay County | MO | 29047
Clay County | NE | 31035
Clay County | NC | 37043
Clay County | SD | 46027
Clay County | TN | 47027
Clay County | TX | 48077
Clay County | WV | 54015
Clayton County | GA | 13063
Clayton County | IA | 19043
Clear Creek County | CO | 8019
Clearfield County | PA | 42033
Clearwater County | ID | 16035
Clearwater County | MN | 27029
Cleburne County | AL | 1029
Cleburne County | AR | 5023
Clermont County | OH | 39025
Cleveland County | AR | 5025
Cleveland County | NC | 37045
Cleveland County | OK | 40027
Clinch County | GA | 13065
Clinton County | IL | 17027
Clinton County | IN | 18023
Clinton County | IA | 19045
Clinton County | KY | 21053
Clinton County | MI | 26037
Clinton County | MO | 29049
Clinton County | NY | 36019
Clinton County | OH | 39027
Clinton County | PA | 42035
Cloud County | KS | 20029
Coahoma County | MS | 28027
Coal County | OK | 40029
Cobb County | GA | 13067
Cochise County | AZ | 4003
Cochran County | TX | 48079
Cocke County | TN | 47029
Coconino County | AZ | 4005
Codington County | SD | 46029
Coffee County | AL | 1031
Coffee County | GA | 13069
Coffee County | TN | 47031
Coffey County | KS | 20031
Coke County | TX | 48081
Colbert County | AL | 1033
Cole County | MO | 29051
Coleman County | TX | 48083
Coles County | IL | 17029
Colfax County | NE | 31037
Colfax County | NM | 35007
Colleton County | SC | 45029
Collier County | FL | 12021
Collin County | TX | 48085
Collingsworth County | TX | 48087
Colonial Heights city | VA | 51570
COLORADO | NA | 8000
Colorado County | TX | 48089
Colquitt County | GA | 13071
Columbia County | AR | 5027
Columbia County | FL | 12023
Columbia County | GA | 13073
Columbia County | NY | 36021
Columbia County | OR | 41009
Columbia County | PA | 42037
Columbia County | WA | 53013
Columbia County | WI | 55021
Columbiana County | OH | 39029
Columbus County | NC | 37047
Colusa County | CA | 6011
Comal County | TX | 48091
Comanche County | KS | 20033
Comanche County | OK | 40031
Comanche County | TX | 48093
Concho County | TX | 48095
Concordia Parish | LA | 22029
Conecuh County | AL | 1035
Conejos County | CO | 8021
CONNECTICUT | NA | 9000
Contra Costa County | CA | 6013
Converse County | WY | 56009
Conway County | AR | 5029
Cook County | GA | 13075
Cook County | IL | 17031
Cook County | MN | 27031
Cooke County | TX | 48097
Cooper County | MO | 29053
Coos County | NH | 33007
Coos County | OR | 41011
Coosa County | AL | 1037
Copiah County | MS | 28029
Corson County | SD | 46031
Cortland County | NY | 36023
Coryell County | TX | 48099
Coshocton County | OH | 39031
Costilla County | CO | 8023
Cottle County | TX | 48101
Cotton County | OK | 40033
Cottonwood County | MN | 27033
Covington city | VA | 51580
Covington County | AL | 1039
Covington County | MS | 28031
Coweta County | GA | 13077
Cowley County | KS | 20035
Cowlitz County | WA | 53015
Craig County | OK | 40035
Craig County | VA | 51045
Craighead County | AR | 5031
Crane County | TX | 48103
Craven County | NC | 37049
Crawford County | AR | 5033
Crawford County | GA | 13079
Crawford County | IL | 17033
Crawford County | IN | 18025
Crawford County | IA | 19047
Crawford County | KS | 20037
Crawford County | MI | 26039
Crawford County | MO | 29055
Crawford County | OH | 39033
Crawford County | PA | 42039
Crawford County | WI | 55023
Creek County | OK | 40037
Crenshaw County | AL | 1041
Crisp County | GA | 13081
Crittenden County | AR | 5035
Crittenden County | KY | 21055
Crockett County | TN | 47033
Crockett County | TX | 48105
Crook County | OR | 41013
Crook County | WY | 56011
Crosby County | TX | 48107
Cross County | AR | 5037
Crow Wing County | MN | 27035
Crowley County | CO | 8025
Culberson County | TX | 48109
Cullman County | AL | 1043
Culpeper County | VA | 51047
Cumberland County | IL | 17035
Cumberland County | KY | 21057
Cumberland County | ME | 23005
Cumberland County | NJ | 34011
Cumberland County | NC | 37051
Cumberland County | PA | 42041
Cumberland County | TN | 47035
Cumberland County | VA | 51049
Cuming County | NE | 31039
Currituck County | NC | 37053
Curry County | NM | 35009
Curry County | OR | 41015
Custer County | CO | 8027
Custer County | ID | 16037
Custer County | MT | 30017
Custer County | NE | 31041
Custer County | OK | 40039
Custer County | SD | 46033
Cuyahoga County | OH | 39035
Dade County | GA | 13083
Dade County | MO | 29057
Daggett County | UT | 49009
Dakota County | MN | 27037
Dakota County | NE | 31043
Dale County | AL | 1045
Dallam County | TX | 48111
Dallas County | AL | 1047
Dallas County | AR | 5039
Dallas County | IA | 19049
Dallas County | MO | 29059
Dallas County | TX | 48113
Dane County | WI | 55025
Daniels County | MT | 30019
Danville city | VA | 51590
Dare County | NC | 37055
Darke County | OH | 39037
Darlington County | SC | 45031
Dauphin County | PA | 42043
Davidson County | NC | 37057
Davidson County | TN | 47037
Davie County | NC | 37059
Daviess County | IN | 18027
Daviess County | KY | 21059
Daviess County | MO | 29061
Davis County | IA | 19051
Davis County | UT | 49011
Davison County | SD | 46035
Dawes County | NE | 31045
Dawson County | GA | 13085
Dawson County | MT | 30021
Dawson County | NE | 31047
Dawson County | TX | 48115
Day County | SD | 46037
De Baca County | NM | 35011
De Soto Parish | LA | 22031
De Witt County | IL | 17039
Deaf Smith County | TX | 48117
Dearborn County | IN | 18029
Decatur County | GA | 13087
Decatur County | IN | 18031
Decatur County | IA | 19053
Decatur County | KS | 20039
Decatur County | TN | 47039
Deer Lodge County | MT | 30023
Defiance County | OH | 39039
DeKalb County | AL | 1049
DeKalb County | GA | 13089
DeKalb County | IL | 17037
DeKalb County | IN | 18033
DeKalb County | MO | 29063
DeKalb County | TN | 47041
Del Norte County | CA | 6015
DELAWARE | NA | 10000
Delaware County | IN | 18035
Delaware County | IA | 19055
Delaware County | NY | 36025
Delaware County | OH | 39041
Delaware County | OK | 40041
Delaware County | PA | 42045
Delta County | CO | 8029
Delta County | MI | 26041
Delta County | TX | 48119
Denali Borough | AK | 2068
Dent County | MO | 29065
Denton County | TX | 48121
Denver County | CO | 8031
Des Moines County | IA | 19057
Deschutes County | OR | 41017
Desha County | AR | 5041
DeSoto County | FL | 12027
DeSoto County | MS | 28033
Deuel County | NE | 31049
Deuel County | SD | 46039
Dewey County | OK | 40043
Dewey County | SD | 46041
DeWitt County | TX | 48123
Dickens County | TX | 48125
Dickenson County | VA | 51051
Dickey County | ND | 38021
Dickinson County | IA | 19059
Dickinson County | KS | 20041
Dickinson County | MI | 26043
Dickson County | TN | 47043
Dillingham Census Area | AK | 2070
Dillon County | SC | 45033
Dimmit County | TX | 48127
Dinwiddie County | VA | 51053
DISTRICT OF COLUMBIA | NA | 11000
District of Columbia | DC | 11001
Divide County | ND | 38023
Dixie County | FL | 12029
Dixon County | NE | 31051
Do̱a Ana County | NM | 35013
Doddridge County | WV | 54017
Dodge County | GA | 13091
Dodge County | MN | 27039
Dodge County | NE | 31053
Dodge County | WI | 55027
Dolores County | CO | 8033
Doniphan County | KS | 20043
Donley County | TX | 48129
Dooly County | GA | 13093
Door County | WI | 55029
Dorchester County | MD | 24019
Dorchester County | SC | 45035
Dougherty County | GA | 13095
Douglas County | CO | 8035
Douglas County | GA | 13097
Douglas County | IL | 17041
Douglas County | KS | 20045
Douglas County | MN | 27041
Douglas County | MO | 29067
Douglas County | NE | 31055
Douglas County | NV | 32005
Douglas County | OR | 41019
Douglas County | SD | 46043
Douglas County | WA | 53017
Douglas County | WI | 55031
Drew County | AR | 5043
Dubois County | IN | 18037
Dubuque County | IA | 19061
Duchesne County | UT | 49013
Dukes County | MA | 25007
Dundy County | NE | 31057
Dunklin County | MO | 29069
Dunn County | ND | 38025
Dunn County | WI | 55033
DuPage County | IL | 17043
Duplin County | NC | 37061
Durham County | NC | 37063
Dutchess County | NY | 36027
Duval County | FL | 12031
Duval County | TX | 48131
Dyer County | TN | 47045
Eagle County | CO | 8037
Early County | GA | 13099
East Baton Rouge Parish | LA | 22033
East Carroll Parish | LA | 22035
East Feliciana Parish | LA | 22037
Eastland County | TX | 48133
Eaton County | MI | 26045
Eau Claire County | WI | 55035
Echols County | GA | 13101
Ector County | TX | 48135
Eddy County | NM | 35015
Eddy County | ND | 38027
Edgar County | IL | 17045
Edgecombe County | NC | 37065
Edgefield County | SC | 45037
Edmonson County | KY | 21061
Edmunds County | SD | 46045
Edwards County | IL | 17047
Edwards County | KS | 20047
Edwards County | TX | 48137
Effingham County | GA | 13103
Effingham County | IL | 17049
El Dorado County | CA | 6017
El Paso County | CO | 8041
El Paso County | TX | 48141
Elbert County | CO | 8039
Elbert County | GA | 13105
Elk County | KS | 20049
Elk County | PA | 42047
Elkhart County | IN | 18039
Elko County | NV | 32007
Elliott County | KY | 21063
Ellis County | KS | 20051
Ellis County | OK | 40045
Ellis County | TX | 48139
Ellsworth County | KS | 20053
Elmore County | AL | 1051
Elmore County | ID | 16039
Emanuel County | GA | 13107
Emery County | UT | 49015
Emmet County | IA | 19063
Emmet County | MI | 26047
Emmons County | ND | 38029
Emporia city | VA | 51595
Erath County | TX | 48143
Erie County | NY | 36029
Erie County | OH | 39043
Erie County | PA | 42049
Escambia County | AL | 1053
Escambia County | FL | 12033
Esmeralda County | NV | 32009
Essex County | MA | 25009
Essex County | NJ | 34013
Essex County | NY | 36031
Essex County | VT | 50009
Essex County | VA | 51057
Estill County | KY | 21065
Etowah County | AL | 1055
Eureka County | NV | 32011
Evangeline Parish | LA | 22039
Evans County | GA | 13109
Fairbanks North Star Borough | AK | 2090
Fairfax city | VA | 51600
Fairfax County | VA | 51059
Fairfield County | CT | 9001
Fairfield County | OH | 39045
Fairfield County | SC | 45039
Fall River County | SD | 46047
Fallon County | MT | 30025
Falls Church city | VA | 51610
Falls County | TX | 48145
Fannin County | GA | 13111
Fannin County | TX | 48147
Faribault County | MN | 27043
Faulk County | SD | 46049
Faulkner County | AR | 5045
Fauquier County | VA | 51061
Fayette County | AL | 1057
Fayette County | GA | 13113
Fayette County | IL | 17051
Fayette County | IN | 18041
Fayette County | IA | 19065
Fayette County | KY | 21067
Fayette County | OH | 39047
Fayette County | PA | 42051
Fayette County | TN | 47047
Fayette County | TX | 48149
Fayette County | WV | 54019
Fentress County | TN | 47049
Fergus County | MT | 30027
Ferry County | WA | 53019
Fillmore County | MN | 27045
Fillmore County | NE | 31059
Finney County | KS | 20055
Fisher County | TX | 48151
Flagler County | FL | 12035
Flathead County | MT | 30029
Fleming County | KY | 21069
Florence County | SC | 45041
Florence County | WI | 55037
FLORIDA | NA | 12000
Floyd County | GA | 13115
Floyd County | IN | 18043
Floyd County | IA | 19067
Floyd County | KY | 21071
Floyd County | TX | 48153
Floyd County | VA | 51063
Fluvanna County | VA | 51065
Foard County | TX | 48155
Fond du Lac County | WI | 55039
Ford County | IL | 17053
Ford County | KS | 20057
Forest County | PA | 42053
Forest County | WI | 55041
Forrest County | MS | 28035
Forsyth County | GA | 13117
Forsyth County | NC | 37067
Fort Bend County | TX | 48157
Foster County | ND | 38031
Fountain County | IN | 18045
Franklin city | VA | 51620
Franklin County | AL | 1059
Franklin County | AR | 5047
Franklin County | FL | 12037
Franklin County | GA | 13119
Franklin County | ID | 16041
Franklin County | IL | 17055
Franklin County | IN | 18047
Franklin County | IA | 19069
Franklin County | KS | 20059
Franklin County | KY | 21073
Franklin County | ME | 23007
Franklin County | MA | 25011
Franklin County | MS | 28037
Franklin County | MO | 29071
Franklin County | NE | 31061
Franklin County | NY | 36033
Franklin County | NC | 37069
Franklin County | OH | 39049
Franklin County | PA | 42055
Franklin County | TN | 47051
Franklin County | TX | 48159
Franklin County | VT | 50011
Franklin County | VA | 51067
Franklin County | WA | 53021
Franklin Parish | LA | 22041
Frederick County | MD | 24021
Frederick County | VA | 51069
Fredericksburg city | VA | 51630
Freeborn County | MN | 27047
Freestone County | TX | 48161
Fremont County | CO | 8043
Fremont County | ID | 16043
Fremont County | IA | 19071
Fremont County | WY | 56013
Fresno County | CA | 6019
Frio County | TX | 48163
Frontier County | NE | 31063
Fulton County | AR | 5049
Fulton County | GA | 13121
Fulton County | IL | 17057
Fulton County | IN | 18049
Fulton County | KY | 21075
Fulton County | NY | 36035
Fulton County | OH | 39051
Fulton County | PA | 42057
Furnas County | NE | 31065
Gadsden County | FL | 12039
Gage County | NE | 31067
Gaines County | TX | 48165
Galax city | VA | 51640
Gallatin County | IL | 17059
Gallatin County | KY | 21077
Gallatin County | MT | 30031
Gallia County | OH | 39053
Galveston County | TX | 48167
Garden County | NE | 31069
Garfield County | CO | 8045
Garfield County | MT | 30033
Garfield County | NE | 31071
Garfield County | OK | 40047
Garfield County | UT | 49017
Garfield County | WA | 53023
Garland County | AR | 5051
Garrard County | KY | 21079
Garrett County | MD | 24023
Garvin County | OK | 40049
Garza County | TX | 48169
Gasconade County | MO | 29073
Gaston County | NC | 37071
Gates County | NC | 37073
Geary County | KS | 20061
Geauga County | OH | 39055
Gem County | ID | 16045
Genesee County | MI | 26049
Genesee County | NY | 36037
Geneva County | AL | 1061
Gentry County | MO | 29075
George County | MS | 28039
Georgetown County | SC | 45043
GEORGIA | NA | 13000
Gibson County | IN | 18051
Gibson County | TN | 47053
Gila County | AZ | 4007
Gilchrist County | FL | 12041
Giles County | TN | 47055
Giles County | VA | 51071
Gillespie County | TX | 48171
Gilliam County | OR | 41021
Gilmer County | GA | 13123
Gilmer County | WV | 54021
Gilpin County | CO | 8047
Glacier County | MT | 30035
Glades County | FL | 12043
Gladwin County | MI | 26051
Glascock County | GA | 13125
Glasscock County | TX | 48173
Glenn County | CA | 6021
Gloucester County | NJ | 34015
Gloucester County | VA | 51073
Glynn County | GA | 13127
Gogebic County | MI | 26053
Golden Valley County | MT | 30037
Golden Valley County | ND | 38033
Goliad County | TX | 48175
Gonzales County | TX | 48177
Goochland County | VA | 51075
Goodhue County | MN | 27049
Gooding County | ID | 16047
Gordon County | GA | 13129
Goshen County | WY | 56015
Gosper County | NE | 31073
Gove County | KS | 20063
Grady County | GA | 13131
Grady County | OK | 40051
Grafton County | NH | 33009
Graham County | AZ | 4009
Graham County | KS | 20065
Graham County | NC | 37075
Grainger County | TN | 47057
Grand County | CO | 8049
Grand County | UT | 49019
Grand Forks County | ND | 38035
Grand Isle County | VT | 50013
Grand Traverse County | MI | 26055
Granite County | MT | 30039
Grant County | AR | 5053
Grant County | IN | 18053
Grant County | KS | 20067
Grant County | KY | 21081
Grant County | MN | 27051
Grant County | NE | 31075
Grant County | NM | 35017
Grant County | ND | 38037
Grant County | OK | 40053
Grant County | OR | 41023
Grant County | SD | 46051
Grant County | WA | 53025
Grant County | WV | 54023
Grant County | WI | 55043
Grant Parish | LA | 22043
Granville County | NC | 37077
Gratiot County | MI | 26057
Graves County | KY | 21083
Gray County | KS | 20069
Gray County | TX | 48179
Grays Harbor County | WA | 53027
Grayson County | KY | 21085
Grayson County | TX | 48181
Grayson County | VA | 51077
Greeley County | KS | 20071
Greeley County | NE | 31077
Green County | KY | 21087
Green County | WI | 55045
Green Lake County | WI | 55047
Greenbrier County | WV | 54025
Greene County | AL | 1063
Greene County | AR | 5055
Greene County | GA | 13133
Greene County | IL | 17061
Greene County | IN | 18055
Greene County | IA | 19073
Greene County | MS | 28041
Greene County | MO | 29077
Greene County | NY | 36039
Greene County | NC | 37079
Greene County | OH | 39057
Greene County | PA | 42059
Greene County | TN | 47059
Greene County | VA | 51079
Greenlee County | AZ | 4011
Greensville County | VA | 51081
Greenup County | KY | 21089
Greenville County | SC | 45045
Greenwood County | KS | 20073
Greenwood County | SC | 45047
Greer County | OK | 40055
Gregg County | TX | 48183
Gregory County | SD | 46053
Grenada County | MS | 28043
Griggs County | ND | 38039
Grimes County | TX | 48185
Grundy County | IL | 17063
Grundy County | IA | 19075
Grundy County | MO | 29079
Grundy County | TN | 47061
Guadalupe County | NM | 35019
Guadalupe County | TX | 48187
Guernsey County | OH | 39059
Guilford County | NC | 37081
Gulf County | FL | 12045
Gunnison County | CO | 8051
Guthrie County | IA | 19077
Gwinnett County | GA | 13135
Haakon County | SD | 46055
Habersham County | GA | 13137
Haines Borough | AK | 2100
Hale County | AL | 1065
Hale County | TX | 48189
Halifax County | NC | 37083
Halifax County | VA | 51083
Hall County | GA | 13139
Hall County | NE | 31079
Hall County | TX | 48191
Hamblen County | TN | 47063
Hamilton County | FL | 12047
Hamilton County | IL | 17065
Hamilton County | IN | 18057
Hamilton County | IA | 19079
Hamilton County | KS | 20075
Hamilton County | NE | 31081
Hamilton County | NY | 36041
Hamilton County | OH | 39061
Hamilton County | TN | 47065
Hamilton County | TX | 48193
Hamlin County | SD | 46057
Hampden County | MA | 25013
Hampshire County | MA | 25015
Hampshire County | WV | 54027
Hampton city | VA | 51650
Hampton County | SC | 45049
Hancock County | GA | 13141
Hancock County | IL | 17067
Hancock County | IN | 18059
Hancock County | IA | 19081
Hancock County | KY | 21091
Hancock County | ME | 23009
Hancock County | MS | 28045
Hancock County | OH | 39063
Hancock County | TN | 47067
Hancock County | WV | 54029
Hand County | SD | 46059
Hanover County | VA | 51085
Hansford County | TX | 48195
Hanson County | SD | 46061
Haralson County | GA | 13143
Hardee County | FL | 12049
Hardeman County | TN | 47069
Hardeman County | TX | 48197
Hardin County | IL | 17069
Hardin County | IA | 19083
Hardin County | KY | 21093
Hardin County | OH | 39065
Hardin County | TN | 47071
Hardin County | TX | 48199
Harding County | NM | 35021
Harding County | SD | 46063
Hardy County | WV | 54031
Harford County | MD | 24025
Harlan County | KY | 21095
Harlan County | NE | 31083
Harmon County | OK | 40057
Harnett County | NC | 37085
Harney County | OR | 41025
Harper County | KS | 20077
Harper County | OK | 40059
Harris County | GA | 13145
Harris County | TX | 48201
Harrison County | IN | 18061
Harrison County | IA | 19085
Harrison County | KY | 21097
Harrison County | MS | 28047
Harrison County | MO | 29081
Harrison County | OH | 39067
Harrison County | TX | 48203
Harrison County | WV | 54033
Harrisonburg city | VA | 51660
Hart County | GA | 13147
Hart County | KY | 21099
Hartford County | CT | 9003
Hartley County | TX | 48205
Harvey County | KS | 20079
Haskell County | KS | 20081
Haskell County | OK | 40061
Haskell County | TX | 48207
HAWAII | NA | 15000
Hawaii County | HI | 15001
Hawkins County | TN | 47073
Hayes County | NE | 31085
Hays County | TX | 48209
Haywood County | NC | 37087
Haywood County | TN | 47075
Heard County | GA | 13149
Hemphill County | TX | 48211
Hempstead County | AR | 5057
Henderson County | IL | 17071
Henderson County | KY | 21101
Henderson County | NC | 37089
Henderson County | TN | 47077
Henderson County | TX | 48213
Hendricks County | IN | 18063
Hendry County | FL | 12051
Hennepin County | MN | 27053
Henrico County | VA | 51087
Henry County | AL | 1067
Henry County | GA | 13151
Henry County | IL | 17073
Henry County | IN | 18065
Henry County | IA | 19087
Henry County | KY | 21103
Henry County | MO | 29083
Henry County | OH | 39069
Henry County | TN | 47079
Henry County | VA | 51089
Herkimer County | NY | 36043
Hernando County | FL | 12053
Hertford County | NC | 37091
Hettinger County | ND | 38041
Hickman County | KY | 21105
Hickman County | TN | 47081
Hickory County | MO | 29085
Hidalgo County | NM | 35023
Hidalgo County | TX | 48215
Highland County | OH | 39071
Highland County | VA | 51091
Highlands County | FL | 12055
Hill County | MT | 30041
Hill County | TX | 48217
Hillsborough County | FL | 12057
Hillsborough County | NH | 33011
Hillsdale County | MI | 26059
Hinds County | MS | 28049
Hinsdale County | CO | 8053
Hitchcock County | NE | 31087
Hocking County | OH | 39073
Hockley County | TX | 48219
Hodgeman County | KS | 20083
Hoke County | NC | 37093
Holmes County | FL | 12059
Holmes County | MS | 28051
Holmes County | OH | 39075
Holt County | MO | 29087
Holt County | NE | 31089
Honolulu County | HI | 15003
Hood County | TX | 48221
Hood River County | OR | 41027
Hooker County | NE | 31091
Hoonah-Angoon Census Area | AK | 2105
Hopewell city | VA | 51670
Hopkins County | KY | 21107
Hopkins County | TX | 48223
Horry County | SC | 45051
Hot Spring County | AR | 5059
Hot Springs County | WY | 56017
Houghton County | MI | 26061
Houston County | AL | 1069
Houston County | GA | 13153
Houston County | MN | 27055
Houston County | TN | 47083
Houston County | TX | 48225
Howard County | AR | 5061
Howard County | IN | 18067
Howard County | IA | 19089
Howard County | MD | 24027
Howard County | MO | 29089
Howard County | NE | 31093
Howard County | TX | 48227
Howell County | MO | 29091
Hubbard County | MN | 27057
Hudson County | NJ | 34017
Hudspeth County | TX | 48229
Huerfano County | CO | 8055
Hughes County | OK | 40063
Hughes County | SD | 46065
Humboldt County | CA | 6023
Humboldt County | IA | 19091
Humboldt County | NV | 32013
Humphreys County | MS | 28053
Humphreys County | TN | 47085
Hunt County | TX | 48231
Hunterdon County | NJ | 34019
Huntingdon County | PA | 42061
Huntington County | IN | 18069
Huron County | MI | 26063
Huron County | OH | 39077
Hutchinson County | SD | 46067
Hutchinson County | TX | 48233
Hyde County | NC | 37095
Hyde County | SD | 46069
Iberia Parish | LA | 22045
Iberville Parish | LA | 22047
Ida County | IA | 19093
IDAHO | NA | 16000
Idaho County | ID | 16049
ILLINOIS | NA | 17000
Imperial County | CA | 6025
Independence County | AR | 5063
Indian River County | FL | 12061
INDIANA | NA | 18000
Indiana County | PA | 42063
Ingham County | MI | 26065
Inyo County | CA | 6027
Ionia County | MI | 26067
Iosco County | MI | 26069
IOWA | NA | 19000
Iowa County | IA | 19095
Iowa County | WI | 55049
Iredell County | NC | 37097
Irion County | TX | 48235
Iron County | MI | 26071
Iron County | MO | 29093
Iron County | UT | 49021
Iron County | WI | 55051
Iroquois County | IL | 17075
Irwin County | GA | 13155
Isabella County | MI | 26073
Isanti County | MN | 27059
Island County | WA | 53029
Isle of Wight County | VA | 51093
Issaquena County | MS | 28055
Itasca County | MN | 27061
Itawamba County | MS | 28057
Izard County | AR | 5065
Jack County | TX | 48237
Jackson County | AL | 1071
Jackson County | AR | 5067
Jackson County | CO | 8057
Jackson County | FL | 12063
Jackson County | GA | 13157
Jackson County | IL | 17077
Jackson County | IN | 18071
Jackson County | IA | 19097
Jackson County | KS | 20085
Jackson County | KY | 21109
Jackson County | MI | 26075
Jackson County | MN | 27063
Jackson County | MS | 28059
Jackson County | MO | 29095
Jackson County | NC | 37099
Jackson County | OH | 39079
Jackson County | OK | 40065
Jackson County | OR | 41029
Jackson County | SD | 46071
Jackson County | TN | 47087
Jackson County | TX | 48239
Jackson County | WV | 54035
Jackson County | WI | 55053
Jackson Parish | LA | 22049
James City County | VA | 51095
Jasper County | GA | 13159
Jasper County | IL | 17079
Jasper County | IN | 18073
Jasper County | IA | 19099
Jasper County | MS | 28061
Jasper County | MO | 29097
Jasper County | SC | 45053
Jasper County | TX | 48241
Jay County | IN | 18075
Jeff Davis County | GA | 13161
Jeff Davis County | TX | 48243
Jefferson County | AL | 1073
Jefferson County | AR | 5069
Jefferson County | CO | 8059
Jefferson County | FL | 12065
Jefferson County | GA | 13163
Jefferson County | ID | 16051
Jefferson County | IL | 17081
Jefferson County | IN | 18077
Jefferson County | IA | 19101
Jefferson County | KS | 20087
Jefferson County | KY | 21111
Jefferson County | MS | 28063
Jefferson County | MO | 29099
Jefferson County | MT | 30043
Jefferson County | NE | 31095
Jefferson County | NY | 36045
Jefferson County | OH | 39081
Jefferson County | OK | 40067
Jefferson County | OR | 41031
Jefferson County | PA | 42065
Jefferson County | TN | 47089
Jefferson County | TX | 48245
Jefferson County | WA | 53031
Jefferson County | WV | 54037
Jefferson County | WI | 55055
Jefferson Davis County | MS | 28065
Jefferson Davis Parish | LA | 22053
Jefferson Parish | LA | 22051
Jenkins County | GA | 13165
Jennings County | IN | 18079
Jerauld County | SD | 46073
Jerome County | ID | 16053
Jersey County | IL | 17083
Jessamine County | KY | 21113
Jewell County | KS | 20089
Jim Hogg County | TX | 48247
Jim Wells County | TX | 48249
Jo Daviess County | IL | 17085
Johnson County | AR | 5071
Johnson County | GA | 13167
Johnson County | IL | 17087
Johnson County | IN | 18081
Johnson County | IA | 19103
Johnson County | KS | 20091
Johnson County | KY | 21115
Johnson County | MO | 29101
Johnson County | NE | 31097
Johnson County | TN | 47091
Johnson County | TX | 48251
Johnson County | WY | 56019
Johnston County | NC | 37101
Johnston County | OK | 40069
Jones County | GA | 13169
Jones County | IA | 19105
Jones County | MS | 28067
Jones County | NC | 37103
Jones County | SD | 46075
Jones County | TX | 48253
Josephine County | OR | 41033
Juab County | UT | 49023
Judith Basin County | MT | 30045
Juneau City and Borough | AK | 2110
Juneau County | WI | 55057
Juniata County | PA | 42067
Kalamazoo County | MI | 26077
Kalawao County | HI | 15005
Kalkaska County | MI | 26079
Kanabec County | MN | 27065
Kanawha County | WV | 54039
Kandiyohi County | MN | 27067
Kane County | IL | 17089
Kane County | UT | 49025
Kankakee County | IL | 17091
KANSAS | NA | 20000
Karnes County | TX | 48255
Kauai County | HI | 15007
Kaufman County | TX | 48257
Kay County | OK | 40071
Kearney County | NE | 31099
Kearny County | KS | 20093
Keith County | NE | 31101
Kemper County | MS | 28069
Kenai Peninsula Borough | AK | 2122
Kendall County | IL | 17093
Kendall County | TX | 48259
Kenedy County | TX | 48261
Kennebec County | ME | 23011
Kenosha County | WI | 55059
Kent County | DE | 10001
Kent County | MD | 24029
Kent County | MI | 26081
Kent County | RI | 44003
Kent County | TX | 48263
Kenton County | KY | 21117
KENTUCKY | NA | 21000
Keokuk County | IA | 19107
Kern County | CA | 6029
Kerr County | TX | 48265
Kershaw County | SC | 45055
Ketchikan Gateway Borough | AK | 2130
Kewaunee County | WI | 55061
Keweenaw County | MI | 26083
Keya Paha County | NE | 31103
Kidder County | ND | 38043
Kimball County | NE | 31105
Kimble County | TX | 48267
King and Queen County | VA | 51097
King County | TX | 48269
King County | WA | 53033
King George County | VA | 51099
King William County | VA | 51101
Kingfisher County | OK | 40073
Kingman County | KS | 20095
Kings County | CA | 6031
Kings County | NY | 36047
Kingsbury County | SD | 46077
Kinney County | TX | 48271
Kiowa County | CO | 8061
Kiowa County | KS | 20097
Kiowa County | OK | 40075
Kit Carson County | CO | 8063
Kitsap County | WA | 53035
Kittitas County | WA | 53037
Kittson County | MN | 27069
Klamath County | OR | 41035
Kleberg County | TX | 48273
Klickitat County | WA | 53039
Knott County | KY | 21119
Knox County | IL | 17095
Knox County | IN | 18083
Knox County | KY | 21121
Knox County | ME | 23013
Knox County | MO | 29103
Knox County | NE | 31107
Knox County | OH | 39083
Knox County | TN | 47093
Knox County | TX | 48275
Kodiak Island Borough | AK | 2150
Koochiching County | MN | 27071
Kootenai County | ID | 16055
Kosciusko County | IN | 18085
Kossuth County | IA | 19109
La Crosse County | WI | 55063
La Paz County | AZ | 4012
La Plata County | CO | 8067
La Salle County | TX | 48283
La Salle Parish | LA | 22059
Labette County | KS | 20099
Lac qui Parle County | MN | 27073
Lackawanna County | PA | 42069
Laclede County | MO | 29105
Lafayette County | AR | 5073
Lafayette County | FL | 12067
Lafayette County | MS | 28071
Lafayette County | MO | 29107
Lafayette County | WI | 55065
Lafayette Parish | LA | 22055
Lafourche Parish | LA | 22057
LaGrange County | IN | 18087
Lake and Peninsula Borough | AK | 2164
Lake County | CA | 6033
Lake County | CO | 8065
Lake County | FL | 12069
Lake County | IL | 17097
Lake County | IN | 18089
Lake County | MI | 26085
Lake County | MN | 27075
Lake County | MT | 30047
Lake County | OH | 39085
Lake County | OR | 41037
Lake County | SD | 46079
Lake County | TN | 47095
Lake of the Woods County | MN | 27077
Lamar County | AL | 1075
Lamar County | GA | 13171
Lamar County | MS | 28073
Lamar County | TX | 48277
Lamb County | TX | 48279
Lamoille County | VT | 50015
LaMoure County | ND | 38045
Lampasas County | TX | 48281
Lancaster County | NE | 31109
Lancaster County | PA | 42071
Lancaster County | SC | 45057
Lancaster County | VA | 51103
Lander County | NV | 32015
Lane County | KS | 20101
Lane County | OR | 41039
Langlade County | WI | 55067
Lanier County | GA | 13173
Lapeer County | MI | 26087
LaPorte County | IN | 18091
Laramie County | WY | 56021
Larimer County | CO | 8069
Larue County | KY | 21123
Las Animas County | CO | 8071
LaSalle County | IL | 17099
Lassen County | CA | 6035
Latah County | ID | 16057
Latimer County | OK | 40077
Lauderdale County | AL | 1077
Lauderdale County | MS | 28075
Lauderdale County | TN | 47097
Laurel County | KY | 21125
Laurens County | GA | 13175
Laurens County | SC | 45059
Lavaca County | TX | 48285
Lawrence County | AL | 1079
Lawrence County | AR | 5075
Lawrence County | IL | 17101
Lawrence County | IN | 18093
Lawrence County | KY | 21127
Lawrence County | MS | 28077
Lawrence County | MO | 29109
Lawrence County | OH | 39087
Lawrence County | PA | 42073
Lawrence County | SD | 46081
Lawrence County | TN | 47099
Le Flore County | OK | 40079
Le Sueur County | MN | 27079
Lea County | NM | 35025
Leake County | MS | 28079
Leavenworth County | KS | 20103
Lebanon County | PA | 42075
Lee County | AL | 1081
Lee County | AR | 5077
Lee County | FL | 12071
Lee County | GA | 13177
Lee County | IL | 17103
Lee County | IA | 19111
Lee County | KY | 21129
Lee County | MS | 28081
Lee County | NC | 37105
Lee County | SC | 45061
Lee County | TX | 48287
Lee County | VA | 51105
Leelanau County | MI | 26089
Leflore County | MS | 28083
Lehigh County | PA | 42077
Lemhi County | ID | 16059
Lenawee County | MI | 26091
Lenoir County | NC | 37107
Leon County | FL | 12073
Leon County | TX | 48289
Leslie County | KY | 21131
Letcher County | KY | 21133
Levy County | FL | 12075
Lewis and Clark County | MT | 30049
Lewis County | ID | 16061
Lewis County | KY | 21135
Lewis County | MO | 29111
Lewis County | NY | 36049
Lewis County | TN | 47101
Lewis County | WA | 53041
Lewis County | WV | 54041
Lexington city | VA | 51678
Lexington County | SC | 45063
Liberty County | FL | 12077
Liberty County | GA | 13179
Liberty County | MT | 30051
Liberty County | TX | 48291
Licking County | OH | 39089
Limestone County | AL | 1083
Limestone County | TX | 48293
Lincoln County | AR | 5079
Lincoln County | CO | 8073
Lincoln County | GA | 13181
Lincoln County | ID | 16063
Lincoln County | KS | 20105
Lincoln County | KY | 21137
Lincoln County | ME | 23015
Lincoln County | MN | 27081
Lincoln County | MS | 28085
Lincoln County | MO | 29113
Lincoln County | MT | 30053
Lincoln County | NE | 31111
Lincoln County | NV | 32017
Lincoln County | NM | 35027
Lincoln County | NC | 37109
Lincoln County | OK | 40081
Lincoln County | OR | 41041
Lincoln County | SD | 46083
Lincoln County | TN | 47103
Lincoln County | WA | 53043
Lincoln County | WV | 54043
Lincoln County | WI | 55069
Lincoln County | WY | 56023
Lincoln Parish | LA | 22061
Linn County | IA | 19113
Linn County | KS | 20107
Linn County | MO | 29115
Linn County | OR | 41043
Lipscomb County | TX | 48295
Litchfield County | CT | 9005
Little River County | AR | 5081
Live Oak County | TX | 48297
Livingston County | IL | 17105
Livingston County | KY | 21139
Livingston County | MI | 26093
Livingston County | MO | 29117
Livingston County | NY | 36051
Livingston Parish | LA | 22063
Llano County | TX | 48299
Logan County | AR | 5083
Logan County | CO | 8075
Logan County | IL | 17107
Logan County | KS | 20109
Logan County | KY | 21141
Logan County | NE | 31113
Logan County | ND | 38047
Logan County | OH | 39091
Logan County | OK | 40083
Logan County | WV | 54045
Long County | GA | 13183
Lonoke County | AR | 5085
Lorain County | OH | 39093
Los Alamos County | NM | 35028
Los Angeles County | CA | 6037
Loudon County | TN | 47105
Loudoun County | VA | 51107
Louisa County | IA | 19115
Louisa County | VA | 51109
LOUISIANA | NA | 22000
Loup County | NE | 31115
Love County | OK | 40085
Loving County | TX | 48301
Lowndes County | AL | 1085
Lowndes County | GA | 13185
Lowndes County | MS | 28087
Lubbock County | TX | 48303
Lucas County | IA | 19117
Lucas County | OH | 39095
Luce County | MI | 26095
Lumpkin County | GA | 13187
Luna County | NM | 35029
Lunenburg County | VA | 51111
Luzerne County | PA | 42079
Lycoming County | PA | 42081
Lyman County | SD | 46085
Lynchburg city | VA | 51680
Lynn County | TX | 48305
Lyon County | IA | 19119
Lyon County | KS | 20111
Lyon County | KY | 21143
Lyon County | MN | 27083
Lyon County | NV | 32019
Mackinac County | MI | 26097
Macomb County | MI | 26099
Macon County | AL | 1087
Macon County | GA | 13193
Macon County | IL | 17115
Macon County | MO | 29121
Macon County | NC | 37113
Macon County | TN | 47111
Macoupin County | IL | 17117
Madera County | CA | 6039
Madison County | AL | 1089
Madison County | AR | 5087
Madison County | FL | 12079
Madison County | GA | 13195
Madison County | ID | 16065
Madison County | IL | 17119
Madison County | IN | 18095
Madison County | IA | 19121
Madison County | KY | 21151
Madison County | MS | 28089
Madison County | MO | 29123
Madison County | MT | 30057
Madison County | NE | 31119
Madison County | NY | 36053
Madison County | NC | 37115
Madison County | OH | 39097
Madison County | TN | 47113
Madison County | TX | 48313
Madison County | VA | 51113
Madison Parish | LA | 22065
Magoffin County | KY | 21153
Mahaska County | IA | 19123
Mahnomen County | MN | 27087
Mahoning County | OH | 39099
MAINE | NA | 23000
Major County | OK | 40093
Malheur County | OR | 41045
Manassas city | VA | 51683
Manassas Park city | VA | 51685
Manatee County | FL | 12081
Manistee County | MI | 26101
Manitowoc County | WI | 55071
Marathon County | WI | 55073
Marengo County | AL | 1091
Maricopa County | AZ | 4013
Maries County | MO | 29125
Marin County | CA | 6041
Marinette County | WI | 55075
Marion County | AL | 1093
Marion County | AR | 5089
Marion County | FL | 12083
Marion County | GA | 13197
Marion County | IL | 17121
Marion County | IN | 18097
Marion County | IA | 19125
Marion County | KS | 20115
Marion County | KY | 21155
Marion County | MS | 28091
Marion County | MO | 29127
Marion County | OH | 39101
Marion County | OR | 41047
Marion County | SC | 45067
Marion County | TN | 47115
Marion County | TX | 48315
Marion County | WV | 54049
Mariposa County | CA | 6043
Marlboro County | SC | 45069
Marquette County | MI | 26103
Marquette County | WI | 55077
Marshall County | AL | 1095
Marshall County | IL | 17123
Marshall County | IN | 18099
Marshall County | IA | 19127
Marshall County | KS | 20117
Marshall County | KY | 21157
Marshall County | MN | 27089
Marshall County | MS | 28093
Marshall County | OK | 40095
Marshall County | SD | 46091
Marshall County | TN | 47117
Marshall County | WV | 54051
Martin County | FL | 12085
Martin County | IN | 18101
Martin County | KY | 21159
Martin County | MN | 27091
Martin County | NC | 37117
Martin County | TX | 48317
Martinsville city | VA | 51690
MARYLAND | NA | 24000
Mason County | IL | 17125
Mason County | KY | 21161
Mason County | MI | 26105
Mason County | TX | 48319
Mason County | WA | 53045
Mason County | WV | 54053
Massac County | IL | 17127
MASSACHUSETTS | NA | 25000
Matagorda County | TX | 48321
Matanuska-Susitna Borough | AK | 2170
Mathews County | VA | 51115
Maui County | HI | 15009
Maury County | TN | 47119
Maverick County | TX | 48323
Mayes County | OK | 40097
McClain County | OK | 40087
McCone County | MT | 30055
McCook County | SD | 46087
McCormick County | SC | 45065
McCracken County | KY | 21145
McCreary County | KY | 21147
McCulloch County | TX | 48307
McCurtain County | OK | 40089
McDonald County | MO | 29119
McDonough County | IL | 17109
McDowell County | NC | 37111
McDowell County | WV | 54047
McDuffie County | GA | 13189
McHenry County | IL | 17111
McHenry County | ND | 38049
McIntosh County | GA | 13191
McIntosh County | ND | 38051
McIntosh County | OK | 40091
McKean County | PA | 42083
McKenzie County | ND | 38053
McKinley County | NM | 35031
McLean County | IL | 17113
McLean County | KY | 21149
McLean County | ND | 38055
McLennan County | TX | 48309
McLeod County | MN | 27085
McMinn County | TN | 47107
McMullen County | TX | 48311
McNairy County | TN | 47109
McPherson County | KS | 20113
McPherson County | NE | 31117
McPherson County | SD | 46089
Meade County | KS | 20119
Meade County | KY | 21163
Meade County | SD | 46093
Meagher County | MT | 30059
Mecklenburg County | NC | 37119
Mecklenburg County | VA | 51117
Mecosta County | MI | 26107
Medina County | OH | 39103
Medina County | TX | 48325
Meeker County | MN | 27093
Meigs County | OH | 39105
Meigs County | TN | 47121
Mellette County | SD | 46095
Menard County | IL | 17129
Menard County | TX | 48327
Mendocino County | CA | 6045
Menifee County | KY | 21165
Menominee County | MI | 26109
Menominee County | WI | 55078
Merced County | CA | 6047
Mercer County | IL | 17131
Mercer County | KY | 21167
Mercer County | MO | 29129
Mercer County | NJ | 34021
Mercer County | ND | 38057
Mercer County | OH | 39107
Mercer County | PA | 42085
Mercer County | WV | 54055
Meriwether County | GA | 13199
Merrick County | NE | 31121
Merrimack County | NH | 33013
Mesa County | CO | 8077
Metcalfe County | KY | 21169
Miami County | IN | 18103
Miami County | KS | 20121
Miami County | OH | 39109
Miami-Dade County | FL | 12086
MICHIGAN | NA | 26000
Middlesex County | CT | 9007
Middlesex County | MA | 25017
Middlesex County | NJ | 34023
Middlesex County | VA | 51119
Midland County | MI | 26111
Midland County | TX | 48329
Mifflin County | PA | 42087
Milam County | TX | 48331
Millard County | UT | 49027
Mille Lacs County | MN | 27095
Miller County | AR | 5091
Miller County | GA | 13201
Miller County | MO | 29131
Mills County | IA | 19129
Mills County | TX | 48333
Milwaukee County | WI | 55079
Miner County | SD | 46097
Mineral County | CO | 8079
Mineral County | MT | 30061
Mineral County | NV | 32021
Mineral County | WV | 54057
Mingo County | WV | 54059
Minidoka County | ID | 16067
Minnehaha County | SD | 46099
MINNESOTA | NA | 27000
Missaukee County | MI | 26113
MISSISSIPPI | NA | 28000
Mississippi County | AR | 5093
Mississippi County | MO | 29133
Missoula County | MT | 30063
MISSOURI | NA | 29000
Mitchell County | GA | 13205
Mitchell County | IA | 19131
Mitchell County | KS | 20123
Mitchell County | NC | 37121
Mitchell County | TX | 48335
Mobile County | AL | 1097
Modoc County | CA | 6049
Moffat County | CO | 8081
Mohave County | AZ | 4015
Moniteau County | MO | 29135
Monmouth County | NJ | 34025
Mono County | CA | 6051
Monona County | IA | 19133
Monongalia County | WV | 54061
Monroe County | AL | 1099
Monroe County | AR | 5095
Monroe County | FL | 12087
Monroe County | GA | 13207
Monroe County | IL | 17133
Monroe County | IN | 18105
Monroe County | IA | 19135
Monroe County | KY | 21171
Monroe County | MI | 26115
Monroe County | MS | 28095
Monroe County | MO | 29137
Monroe County | NY | 36055
Monroe County | OH | 39111
Monroe County | PA | 42089
Monroe County | TN | 47123
Monroe County | WV | 54063
Monroe County | WI | 55081
Montague County | TX | 48337
MONTANA | NA | 30000
Montcalm County | MI | 26117
Monterey County | CA | 6053
Montezuma County | CO | 8083
Montgomery County | AL | 1101
Montgomery County | AR | 5097
Montgomery County | GA | 13209
Montgomery County | IL | 17135
Montgomery County | IN | 18107
Montgomery County | IA | 19137
Montgomery County | KS | 20125
Montgomery County | KY | 21173
Montgomery County | MD | 24031
Montgomery County | MS | 28097
Montgomery County | MO | 29139
Montgomery County | NY | 36057
Montgomery County | NC | 37123
Montgomery County | OH | 39113
Montgomery County | PA | 42091
Montgomery County | TN | 47125
Montgomery County | TX | 48339
Montgomery County | VA | 51121
Montmorency County | MI | 26119
Montour County | PA | 42093
Montrose County | CO | 8085
Moody County | SD | 46101
Moore County | NC | 37125
Moore County | TN | 47127
Moore County | TX | 48341
Mora County | NM | 35033
Morehouse Parish | LA | 22067
Morgan County | AL | 1103
Morgan County | CO | 8087
Morgan County | GA | 13211
Morgan County | IL | 17137
Morgan County | IN | 18109
Morgan County | KY | 21175
Morgan County | MO | 29141
Morgan County | OH | 39115
Morgan County | TN | 47129
Morgan County | UT | 49029
Morgan County | WV | 54065
Morrill County | NE | 31123
Morris County | KS | 20127
Morris County | NJ | 34027
Morris County | TX | 48343
Morrison County | MN | 27097
Morrow County | OH | 39117
Morrow County | OR | 41049
Morton County | KS | 20129
Morton County | ND | 38059
Motley County | TX | 48345
Moultrie County | IL | 17139
Mountrail County | ND | 38061
Mower County | MN | 27099
Muhlenberg County | KY | 21177
Multnomah County | OR | 41051
Murray County | GA | 13213
Murray County | MN | 27101
Murray County | OK | 40099
Muscatine County | IA | 19139
Muscogee County | GA | 13215
Muskegon County | MI | 26121
Muskingum County | OH | 39119
Muskogee County | OK | 40101
Musselshell County | MT | 30065
Nacogdoches County | TX | 48347
Nance County | NE | 31125
Nantucket County | MA | 25019
Napa County | CA | 6055
Nash County | NC | 37127
Nassau County | FL | 12089
Nassau County | NY | 36059
Natchitoches Parish | LA | 22069
Natrona County | WY | 56025
Navajo County | AZ | 4017
Navarro County | TX | 48349
NEBRASKA | NA | 31000
Nelson County | KY | 21179
Nelson County | ND | 38063
Nelson County | VA | 51125
Nemaha County | KS | 20131
Nemaha County | NE | 31127
Neosho County | KS | 20133
Neshoba County | MS | 28099
Ness County | KS | 20135
NEVADA | NA | 32000
Nevada County | AR | 5099
Nevada County | CA | 6057
New Castle County | DE | 10003
NEW HAMPSHIRE | NA | 33000
New Hanover County | NC | 37129
New Haven County | CT | 9009
NEW JERSEY | NA | 34000
New Kent County | VA | 51127
New London County | CT | 9011
New Madrid County | MO | 29143
NEW MEXICO | NA | 35000
NEW YORK | NA | 36000
New York County | NY | 36061
Newaygo County | MI | 26123
Newberry County | SC | 45071
Newport County | RI | 44005
Newport News city | VA | 51700
Newton County | AR | 5101
Newton County | GA | 13217
Newton County | IN | 18111
Newton County | MS | 28101
Newton County | MO | 29145
Newton County | TX | 48351
Nez Perce County | ID | 16069
Niagara County | NY | 36063
Nicholas County | KY | 21181
Nicholas County | WV | 54067
Nicollet County | MN | 27103
Niobrara County | WY | 56027
Noble County | IN | 18113
Noble County | OH | 39121
Noble County | OK | 40103
Nobles County | MN | 27105
Nodaway County | MO | 29147
Nolan County | TX | 48353
Nome Census Area | AK | 2180
Norfolk city | VA | 51710
Norfolk County | MA | 25021
Norman County | MN | 27107
NORTH CAROLINA | NA | 37000
NORTH DAKOTA | NA | 38000
North Slope Borough | AK | 2185
Northampton County | NC | 37131
Northampton County | PA | 42095
Northampton County | VA | 51131
Northumberland County | PA | 42097
Northumberland County | VA | 51133
Northwest Arctic Borough | AK | 2188
Norton city | VA | 51720
Norton County | KS | 20137
Nottoway County | VA | 51135
Nowata County | OK | 40105
Noxubee County | MS | 28103
Nuckolls County | NE | 31129
Nueces County | TX | 48355
Nye County | NV | 32023
O'Brien County | IA | 19141
Oakland County | MI | 26125
Obion County | TN | 47131
Ocean County | NJ | 34029
Oceana County | MI | 26127
Ochiltree County | TX | 48357
Oconee County | GA | 13219
Oconee County | SC | 45073
Oconto County | WI | 55083
Ogemaw County | MI | 26129
Ogle County | IL | 17141
Oglethorpe County | GA | 13221
OHIO | NA | 39000
Ohio County | IN | 18115
Ohio County | KY | 21183
Ohio County | WV | 54069
Okaloosa County | FL | 12091
Okanogan County | WA | 53047
Okeechobee County | FL | 12093
Okfuskee County | OK | 40107
OKLAHOMA | NA | 40000
Oklahoma County | OK | 40109
Okmulgee County | OK | 40111
Oktibbeha County | MS | 28105
Oldham County | KY | 21185
Oldham County | TX | 48359
Oliver County | ND | 38065
Olmsted County | MN | 27109
Oneida County | ID | 16071
Oneida County | NY | 36065
Oneida County | WI | 55085
Onondaga County | NY | 36067
Onslow County | NC | 37133
Ontario County | NY | 36069
Ontonagon County | MI | 26131
Orange County | CA | 6059
Orange County | FL | 12095
Orange County | IN | 18117
Orange County | NY | 36071
Orange County | NC | 37135
Orange County | TX | 48361
Orange County | VT | 50017
Orange County | VA | 51137
Orangeburg County | SC | 45075
OREGON | NA | 41000
Oregon County | MO | 29149
Orleans County | NY | 36073
Orleans County | VT | 50019
Orleans Parish | LA | 22071
Osage County | KS | 20139
Osage County | MO | 29151
Osage County | OK | 40113
Osborne County | KS | 20141
Osceola County | FL | 12097
Osceola County | IA | 19143
Osceola County | MI | 26133
Oscoda County | MI | 26135
Oswego County | NY | 36075
Otero County | CO | 8089
Otero County | NM | 35035
Otoe County | NE | 31131
Otsego County | MI | 26137
Otsego County | NY | 36077
Ottawa County | KS | 20143
Ottawa County | MI | 26139
Ottawa County | OH | 39123
Ottawa County | OK | 40115
Otter Tail County | MN | 27111
Ouachita County | AR | 5103
Ouachita Parish | LA | 22073
Ouray County | CO | 8091
Outagamie County | WI | 55087
Overton County | TN | 47133
Owen County | IN | 18119
Owen County | KY | 21187
Owsley County | KY | 21189
Owyhee County | ID | 16073
Oxford County | ME | 23017
Ozark County | MO | 29153
Ozaukee County | WI | 55089
Pacific County | WA | 53049
Page County | IA | 19145
Page County | VA | 51139
Palm Beach County | FL | 12099
Palo Alto County | IA | 19147
Palo Pinto County | TX | 48363
Pamlico County | NC | 37137
Panola County | MS | 28107
Panola County | TX | 48365
Park County | CO | 8093
Park County | MT | 30067
Park County | WY | 56029
Parke County | IN | 18121
Parker County | TX | 48367
Parmer County | TX | 48369
Pasco County | FL | 12101
Pasquotank County | NC | 37139
Passaic County | NJ | 34031
Patrick County | VA | 51141
Paulding County | GA | 13223
Paulding County | OH | 39125
Pawnee County | KS | 20145
Pawnee County | NE | 31133
Pawnee County | OK | 40117
Payette County | ID | 16075
Payne County | OK | 40119
Peach County | GA | 13225
Pearl River County | MS | 28109
Pecos County | TX | 48371
Pembina County | ND | 38067
Pemiscot County | MO | 29155
Pend Oreille County | WA | 53051
Pender County | NC | 37141
Pendleton County | KY | 21191
Pendleton County | WV | 54071
Pennington County | MN | 27113
Pennington County | SD | 46103
PENNSYLVANIA | NA | 42000
Penobscot County | ME | 23019
Peoria County | IL | 17143
Pepin County | WI | 55091
Perkins County | NE | 31135
Perkins County | SD | 46105
Perquimans County | NC | 37143
Perry County | AL | 1105
Perry County | AR | 5105
Perry County | IL | 17145
Perry County | IN | 18123
Perry County | KY | 21193
Perry County | MS | 28111
Perry County | MO | 29157
Perry County | OH | 39127
Perry County | PA | 42099
Perry County | TN | 47135
Pershing County | NV | 32027
Person County | NC | 37145
Petersburg Borough | AK | 2195
Petersburg city | VA | 51730
Petroleum County | MT | 30069
Pettis County | MO | 29159
Phelps County | MO | 29161
Phelps County | NE | 31137
Philadelphia County | PA | 42101
Phillips County | AR | 5107
Phillips County | CO | 8095
Phillips County | KS | 20147
Phillips County | MT | 30071
Piatt County | IL | 17147
Pickaway County | OH | 39129
Pickens County | AL | 1107
Pickens County | GA | 13227
Pickens County | SC | 45077
Pickett County | TN | 47137
Pierce County | GA | 13229
Pierce County | NE | 31139
Pierce County | ND | 38069
Pierce County | WA | 53053
Pierce County | WI | 55093
Pike County | AL | 1109
Pike County | AR | 5109
Pike County | GA | 13231
Pike County | IL | 17149
Pike County | IN | 18125
Pike County | KY | 21195
Pike County | MS | 28113
Pike County | MO | 29163
Pike County | OH | 39131
Pike County | PA | 42103
Pima County | AZ | 4019
Pinal County | AZ | 4021
Pine County | MN | 27115
Pinellas County | FL | 12103
Pipestone County | MN | 27117
Piscataquis County | ME | 23021
Pitkin County | CO | 8097
Pitt County | NC | 37147
Pittsburg County | OK | 40121
Pittsylvania County | VA | 51143
Piute County | UT | 49031
Placer County | CA | 6061
Plaquemines Parish | LA | 22075
Platte County | MO | 29165
Platte County | NE | 31141
Platte County | WY | 56031
Pleasants County | WV | 54073
Plumas County | CA | 6063
Plymouth County | IA | 19149
Plymouth County | MA | 25023
Pocahontas County | IA | 19151
Pocahontas County | WV | 54075
Poinsett County | AR | 5111
Pointe Coupee Parish | LA | 22077
Polk County | AR | 5113
Polk County | FL | 12105
Polk County | GA | 13233
Polk County | IA | 19153
Polk County | MN | 27119
Polk County | MO | 29167
Polk County | NE | 31143
Polk County | NC | 37149
Polk County | OR | 41053
Polk County | TN | 47139
Polk County | TX | 48373
Polk County | WI | 55095
Pondera County | MT | 30073
Pontotoc County | MS | 28115
Pontotoc County | OK | 40123
Pope County | AR | 5115
Pope County | IL | 17151
Pope County | MN | 27121
Poquoson city | VA | 51735
Portage County | OH | 39133
Portage County | WI | 55097
Porter County | IN | 18127
Portsmouth city | VA | 51740
Posey County | IN | 18129
Pottawatomie County | KS | 20149
Pottawatomie County | OK | 40125
Pottawattamie County | IA | 19155
Potter County | PA | 42105
Potter County | SD | 46107
Potter County | TX | 48375
Powder River County | MT | 30075
Powell County | KY | 21197
Powell County | MT | 30077
Power County | ID | 16077
Poweshiek County | IA | 19157
Powhatan County | VA | 51145
Prairie County | AR | 5117
Prairie County | MT | 30079
Pratt County | KS | 20151
Preble County | OH | 39135
Prentiss County | MS | 28117
Presidio County | TX | 48377
Presque Isle County | MI | 26141
Preston County | WV | 54077
Price County | WI | 55099
Prince Edward County | VA | 51147
Prince George County | VA | 51149
Prince George's County | MD | 24033
Prince of Wales-Hyder Census Area | AK | 2198
Prince William County | VA | 51153
Providence County | RI | 44007
Prowers County | CO | 8099
Pueblo County | CO | 8101
Pulaski County | AR | 5119
Pulaski County | GA | 13235
Pulaski County | IL | 17153
Pulaski County | IN | 18131
Pulaski County | KY | 21199
Pulaski County | MO | 29169
Pulaski County | VA | 51155
Pushmataha County | OK | 40127
Putnam County | FL | 12107
Putnam County | GA | 13237
Putnam County | IL | 17155
Putnam County | IN | 18133
Putnam County | MO | 29171
Putnam County | NY | 36079
Putnam County | OH | 39137
Putnam County | TN | 47141
Putnam County | WV | 54079
Quay County | NM | 35037
Queen Anne's County | MD | 24035
Queens County | NY | 36081
Quitman County | GA | 13239
Quitman County | MS | 28119
Rabun County | GA | 13241
Racine County | WI | 55101
Radford city | VA | 51750
Rains County | TX | 48379
Raleigh County | WV | 54081
Ralls County | MO | 29173
Ramsey County | MN | 27123
Ramsey County | ND | 38071
Randall County | TX | 48381
Randolph County | AL | 1111
Randolph County | AR | 5121
Randolph County | GA | 13243
Randolph County | IL | 17157
Randolph County | IN | 18135
Randolph County | MO | 29175
Randolph County | NC | 37151
Randolph County | WV | 54083
Rankin County | MS | 28121
Ransom County | ND | 38073
Rapides Parish | LA | 22079
Rappahannock County | VA | 51157
Ravalli County | MT | 30081
Rawlins County | KS | 20153
Ray County | MO | 29177
Reagan County | TX | 48383
Real County | TX | 48385
Red Lake County | MN | 27125
Red River County | TX | 48387
Red River Parish | LA | 22081
Red Willow County | NE | 31145
Redwood County | MN | 27127
Reeves County | TX | 48389
Refugio County | TX | 48391
Reno County | KS | 20155
Rensselaer County | NY | 36083
Renville County | MN | 27129
Renville County | ND | 38075
Republic County | KS | 20157
Reynolds County | MO | 29179
Rhea County | TN | 47143
RHODE ISLAND | NA | 44000
Rice County | KS | 20159
Rice County | MN | 27131
Rich County | UT | 49033
Richardson County | NE | 31147
Richland County | IL | 17159
Richland County | MT | 30083
Richland County | ND | 38077
Richland County | OH | 39139
Richland County | SC | 45079
Richland County | WI | 55103
Richland Parish | LA | 22083
Richmond city | VA | 51760
Richmond County | GA | 13245
Richmond County | NY | 36085
Richmond County | NC | 37153
Richmond County | VA | 51159
Riley County | KS | 20161
Ringgold County | IA | 19159
Rio Arriba County | NM | 35039
Rio Blanco County | CO | 8103
Rio Grande County | CO | 8105
Ripley County | IN | 18137
Ripley County | MO | 29181
Ritchie County | WV | 54085
Riverside County | CA | 6065
Roane County | TN | 47145
Roane County | WV | 54087
Roanoke city | VA | 51770
Roanoke County | VA | 51161
Roberts County | SD | 46109
Roberts County | TX | 48393
Robertson County | KY | 21201
Robertson County | TN | 47147
Robertson County | TX | 48395
Robeson County | NC | 37155
Rock County | MN | 27133
Rock County | NE | 31149
Rock County | WI | 55105
Rock Island County | IL | 17161
Rockbridge County | VA | 51163
Rockcastle County | KY | 21203
Rockdale County | GA | 13247
Rockingham County | NH | 33015
Rockingham County | NC | 37157
Rockingham County | VA | 51165
Rockland County | NY | 36087
Rockwall County | TX | 48397
Roger Mills County | OK | 40129
Rogers County | OK | 40131
Rolette County | ND | 38079
Rooks County | KS | 20163
Roosevelt County | MT | 30085
Roosevelt County | NM | 35041
Roscommon County | MI | 26143
Roseau County | MN | 27135
Rosebud County | MT | 30087
Ross County | OH | 39141
Routt County | CO | 8107
Rowan County | KY | 21205
Rowan County | NC | 37159
Runnels County | TX | 48399
Rush County | IN | 18139
Rush County | KS | 20165
Rusk County | TX | 48401
Rusk County | WI | 55107
Russell County | AL | 1113
Russell County | KS | 20167
Russell County | KY | 21207
Russell County | VA | 51167
Rutherford County | NC | 37161
Rutherford County | TN | 47149
Rutland County | VT | 50021
Sabine County | TX | 48403
Sabine Parish | LA | 22085
Sac County | IA | 19161
Sacramento County | CA | 6067
Sagadahoc County | ME | 23023
Saginaw County | MI | 26145
Saguache County | CO | 8109
Salem city | VA | 51775
Salem County | NJ | 34033
Saline County | AR | 5125
Saline County | IL | 17165
Saline County | KS | 20169
Saline County | MO | 29195
Saline County | NE | 31151
Salt Lake County | UT | 49035
Saluda County | SC | 45081
Sampson County | NC | 37163
San Augustine County | TX | 48405
San Benito County | CA | 6069
San Bernardino County | CA | 6071
San Diego County | CA | 6073
San Francisco County | CA | 6075
San Jacinto County | TX | 48407
San Joaquin County | CA | 6077
San Juan County | CO | 8111
San Juan County | NM | 35045
San Juan County | UT | 49037
San Juan County | WA | 53055
San Luis Obispo County | CA | 6079
San Mateo County | CA | 6081
San Miguel County | CO | 8113
San Miguel County | NM | 35047
San Patricio County | TX | 48409
San Saba County | TX | 48411
Sanborn County | SD | 46111
Sanders County | MT | 30089
Sandoval County | NM | 35043
Sandusky County | OH | 39143
Sangamon County | IL | 17167
Sanilac County | MI | 26151
Sanpete County | UT | 49039
Santa Barbara County | CA | 6083
Santa Clara County | CA | 6085
Santa Cruz County | AZ | 4023
Santa Cruz County | CA | 6087
Santa Fe County | NM | 35049
Santa Rosa County | FL | 12113
Sarasota County | FL | 12115
Saratoga County | NY | 36091
Sargent County | ND | 38081
Sarpy County | NE | 31153
Sauk County | WI | 55111
Saunders County | NE | 31155
Sawyer County | WI | 55113
Schenectady County | NY | 36093
Schleicher County | TX | 48413
Schley County | GA | 13249
Schoharie County | NY | 36095
Schoolcraft County | MI | 26153
Schuyler County | IL | 17169
Schuyler County | MO | 29197
Schuyler County | NY | 36097
Schuylkill County | PA | 42107
Scioto County | OH | 39145
Scotland County | MO | 29199
Scotland County | NC | 37165
Scott County | AR | 5127
Scott County | IL | 17171
Scott County | IN | 18143
Scott County | IA | 19163
Scott County | KS | 20171
Scott County | KY | 21209
Scott County | MN | 27139
Scott County | MS | 28123
Scott County | MO | 29201
Scott County | TN | 47151
Scott County | VA | 51169
Scotts Bluff County | NE | 31157
Screven County | GA | 13251
Scurry County | TX | 48415
Searcy County | AR | 5129
Sebastian County | AR | 5131
Sedgwick County | CO | 8115
Sedgwick County | KS | 20173
Seminole County | FL | 12117
Seminole County | GA | 13253
Seminole County | OK | 40133
Seneca County | NY | 36099
Seneca County | OH | 39147
Sequatchie County | TN | 47153
Sequoyah County | OK | 40135
Sevier County | AR | 5133
Sevier County | TN | 47155
Sevier County | UT | 49041
Seward County | KS | 20175
Seward County | NE | 31159
Shackelford County | TX | 48417
Shannon County | MO | 29203
Shannon County | SD | 46113
Sharkey County | MS | 28125
Sharp County | AR | 5135
Shasta County | CA | 6089
Shawano County | WI | 55115
Shawnee County | KS | 20177
Sheboygan County | WI | 55117
Shelby County | AL | 1117
Shelby County | IL | 17173
Shelby County | IN | 18145
Shelby County | IA | 19165
Shelby County | KY | 21211
Shelby County | MO | 29205
Shelby County | OH | 39149
Shelby County | TN | 47157
Shelby County | TX | 48419
Shenandoah County | VA | 51171
Sherburne County | MN | 27141
Sheridan County | KS | 20179
Sheridan County | MT | 30091
Sheridan County | NE | 31161
Sheridan County | ND | 38083
Sheridan County | WY | 56033
Sherman County | KS | 20181
Sherman County | NE | 31163
Sherman County | OR | 41055
Sherman County | TX | 48421
Shiawassee County | MI | 26155
Shoshone County | ID | 16079
Sibley County | MN | 27143
Sierra County | CA | 6091
Sierra County | NM | 35051
Silver Bow County | MT | 30093
Simpson County | KY | 21213
Simpson County | MS | 28127
Sioux County | IA | 19167
Sioux County | NE | 31165
Sioux County | ND | 38085
Siskiyou County | CA | 6093
Sitka City and Borough | AK | 2220
Skagit County | WA | 53057
Skagway Municipality | AK | 2230
Skamania County | WA | 53059
Slope County | ND | 38087
Smith County | KS | 20183
Smith County | MS | 28129
Smith County | TN | 47159
Smith County | TX | 48423
Smyth County | VA | 51173
Snohomish County | WA | 53061
Snyder County | PA | 42109
Socorro County | NM | 35053
Solano County | CA | 6095
Somerset County | ME | 23025
Somerset County | MD | 24039
Somerset County | NJ | 34035
Somerset County | PA | 42111
Somervell County | TX | 48425
Sonoma County | CA | 6097
SOUTH CAROLINA | NA | 45000
SOUTH DAKOTA | NA | 46000
Southampton County | VA | 51175
Southeast Fairbanks Census Area | AK | 2240
Spalding County | GA | 13255
Spartanburg County | SC | 45083
Spencer County | IN | 18147
Spencer County | KY | 21215
Spink County | SD | 46115
Spokane County | WA | 53063
Spotsylvania County | VA | 51177
St. Bernard Parish | LA | 22087
St. Charles County | MO | 29183
St. Charles Parish | LA | 22089
St. Clair County | AL | 1115
St. Clair County | IL | 17163
St. Clair County | MI | 26147
St. Clair County | MO | 29185
St. Croix County | WI | 55109
St. Francis County | AR | 5123
St. Francois County | MO | 29187
St. Helena Parish | LA | 22091
St. James Parish | LA | 22093
St. John the Baptist Parish | LA | 22095
St. Johns County | FL | 12109
St. Joseph County | IN | 18141
St. Joseph County | MI | 26149
St. Landry Parish | LA | 22097
St. Lawrence County | NY | 36089
St. Louis city | MO | 29510
St. Louis County | MN | 27137
St. Louis County | MO | 29189
St. Lucie County | FL | 12111
St. Martin Parish | LA | 22099
St. Mary Parish | LA | 22101
St. Mary's County | MD | 24037
St. Tammany Parish | LA | 22103
Stafford County | KS | 20185
Stafford County | VA | 51179
Stanislaus County | CA | 6099
Stanley County | SD | 46117
Stanly County | NC | 37167
Stanton County | KS | 20187
Stanton County | NE | 31167
Stark County | IL | 17175
Stark County | ND | 38089
Stark County | OH | 39151
Starke County | IN | 18149
Starr County | TX | 48427
Staunton city | VA | 51790
Ste. Genevieve County | MO | 29186
Stearns County | MN | 27145
Steele County | MN | 27147
Steele County | ND | 38091
Stephens County | GA | 13257
Stephens County | OK | 40137
Stephens County | TX | 48429
Stephenson County | IL | 17177
Sterling County | TX | 48431
Steuben County | IN | 18151
Steuben County | NY | 36101
Stevens County | KS | 20189
Stevens County | MN | 27149
Stevens County | WA | 53065
Stewart County | GA | 13259
Stewart County | TN | 47161
Stillwater County | MT | 30095
Stoddard County | MO | 29207
Stokes County | NC | 37169
Stone County | AR | 5137
Stone County | MS | 28131
Stone County | MO | 29209
Stonewall County | TX | 48433
Storey County | NV | 32029
Story County | IA | 19169
Strafford County | NH | 33017
Stutsman County | ND | 38093
Sublette County | WY | 56035
Suffolk city | VA | 51800
Suffolk County | MA | 25025
Suffolk County | NY | 36103
Sullivan County | IN | 18153
Sullivan County | MO | 29211
Sullivan County | NH | 33019
Sullivan County | NY | 36105
Sullivan County | PA | 42113
Sullivan County | TN | 47163
Sully County | SD | 46119
Summers County | WV | 54089
Summit County | CO | 8117
Summit County | OH | 39153
Summit County | UT | 49043
Sumner County | KS | 20191
Sumner County | TN | 47165
Sumter County | AL | 1119
Sumter County | FL | 12119
Sumter County | GA | 13261
Sumter County | SC | 45085
Sunflower County | MS | 28133
Surry County | NC | 37171
Surry County | VA | 51181
Susquehanna County | PA | 42115
Sussex County | DE | 10005
Sussex County | NJ | 34037
Sussex County | VA | 51183
Sutter County | CA | 6101
Sutton County | TX | 48435
Suwannee County | FL | 12121
Swain County | NC | 37173
Sweet Grass County | MT | 30097
Sweetwater County | WY | 56037
Swift County | MN | 27151
Swisher County | TX | 48437
Switzerland County | IN | 18155
Talbot County | GA | 13263
Talbot County | MD | 24041
Taliaferro County | GA | 13265
Talladega County | AL | 1121
Tallahatchie County | MS | 28135
Tallapoosa County | AL | 1123
Tama County | IA | 19171
Taney County | MO | 29213
Tangipahoa Parish | LA | 22105
Taos County | NM | 35055
Tarrant County | TX | 48439
Tate County | MS | 28137
Tattnall County | GA | 13267
Taylor County | FL | 12123
Taylor County | GA | 13269
Taylor County | IA | 19173
Taylor County | KY | 21217
Taylor County | TX | 48441
Taylor County | WV | 54091
Taylor County | WI | 55119
Tazewell County | IL | 17179
Tazewell County | VA | 51185
Tehama County | CA | 6103
Telfair County | GA | 13271
Teller County | CO | 8119
TENNESSEE | NA | 47000
Tensas Parish | LA | 22107
Terrebonne Parish | LA | 22109
Terrell County | GA | 13273
Terrell County | TX | 48443
Terry County | TX | 48445
Teton County | ID | 16081
Teton County | MT | 30099
Teton County | WY | 56039
TEXAS | NA | 48000
Texas County | MO | 29215
Texas County | OK | 40139
Thayer County | NE | 31169
Thomas County | GA | 13275
Thomas County | KS | 20193
Thomas County | NE | 31171
Throckmorton County | TX | 48447
Thurston County | NE | 31173
Thurston County | WA | 53067
Tift County | GA | 13277
Tillamook County | OR | 41057
Tillman County | OK | 40141
Tioga County | NY | 36107
Tioga County | PA | 42117
Tippah County | MS | 28139
Tippecanoe County | IN | 18157
Tipton County | IN | 18159
Tipton County | TN | 47167
Tishomingo County | MS | 28141
Titus County | TX | 48449
Todd County | KY | 21219
Todd County | MN | 27153
Todd County | SD | 46121
Tolland County | CT | 9013
Tom Green County | TX | 48451
Tompkins County | NY | 36109
Tooele County | UT | 49045
Toole County | MT | 30101
Toombs County | GA | 13279
Torrance County | NM | 35057
Towner County | ND | 38095
Towns County | GA | 13281
Traill County | ND | 38097
Transylvania County | NC | 37175
Traverse County | MN | 27155
Travis County | TX | 48453
Treasure County | MT | 30103
Trego County | KS | 20195
Trempealeau County | WI | 55121
Treutlen County | GA | 13283
Trigg County | KY | 21221
Trimble County | KY | 21223
Trinity County | CA | 6105
Trinity County | TX | 48455
Tripp County | SD | 46123
Troup County | GA | 13285
Trousdale County | TN | 47169
Trumbull County | OH | 39155
Tucker County | WV | 54093
Tulare County | CA | 6107
Tulsa County | OK | 40143
Tunica County | MS | 28143
Tuolumne County | CA | 6109
Turner County | GA | 13287
Turner County | SD | 46125
Tuscaloosa County | AL | 1125
Tuscarawas County | OH | 39157
Tuscola County | MI | 26157
Twiggs County | GA | 13289
Twin Falls County | ID | 16083
Tyler County | TX | 48457
Tyler County | WV | 54095
Tyrrell County | NC | 37177
Uinta County | WY | 56041
Uintah County | UT | 49047
Ulster County | NY | 36111
Umatilla County | OR | 41059
Unicoi County | TN | 47171
Union County | AR | 5139
Union County | FL | 12125
Union County | GA | 13291
Union County | IL | 17181
Union County | IN | 18161
Union County | IA | 19175
Union County | KY | 21225
Union County | MS | 28145
Union County | NJ | 34039
Union County | NM | 35059
Union County | NC | 37179
Union County | OH | 39159
Union County | OR | 41061
Union County | PA | 42119
Union County | SC | 45087
Union County | SD | 46127
Union County | TN | 47173
Union Parish | LA | 22111
UNITED STATES | NA | 0
Upshur County | TX | 48459
Upshur County | WV | 54097
Upson County | GA | 13293
Upton County | TX | 48461
UTAH | NA | 49000
Utah County | UT | 49049
Uvalde County | TX | 48463
Val Verde County | TX | 48465
Valdez-Cordova Census Area | AK | 2261
Valencia County | NM | 35061
Valley County | ID | 16085
Valley County | MT | 30105
Valley County | NE | 31175
Van Buren County | AR | 5141
Van Buren County | IA | 19177
Van Buren County | MI | 26159
Van Buren County | TN | 47175
Van Wert County | OH | 39161
Van Zandt County | TX | 48467
Vance County | NC | 37181
Vanderburgh County | IN | 18163
Venango County | PA | 42121
Ventura County | CA | 6111
Vermilion County | IL | 17183
Vermilion Parish | LA | 22113
Vermillion County | IN | 18165
VERMONT | NA | 50000
Vernon County | MO | 29217
Vernon County | WI | 55123
Vernon Parish | LA | 22115
Victoria County | TX | 48469
Vigo County | IN | 18167
Vilas County | WI | 55125
Vinton County | OH | 39163
VIRGINIA | NA | 51000
Virginia Beach city | VA | 51810
Volusia County | FL | 12127
Wabash County | IL | 17185
Wabash County | IN | 18169
Wabasha County | MN | 27157
Wabaunsee County | KS | 20197
Wade Hampton Census Area | AK | 2270
Wadena County | MN | 27159
Wagoner County | OK | 40145
Wahkiakum County | WA | 53069
Wake County | NC | 37183
Wakulla County | FL | 12129
Waldo County | ME | 23027
Walker County | AL | 1127
Walker County | GA | 13295
Walker County | TX | 48471
Walla Walla County | WA | 53071
Wallace County | KS | 20199
Waller County | TX | 48473
Wallowa County | OR | 41063
Walsh County | ND | 38099
Walthall County | MS | 28147
Walton County | FL | 12131
Walton County | GA | 13297
Walworth County | SD | 46129
Walworth County | WI | 55127
Wapello County | IA | 19179
Ward County | ND | 38101
Ward County | TX | 48475
Ware County | GA | 13299
Warren County | GA | 13301
Warren County | IL | 17187
Warren County | IN | 18171
Warren County | IA | 19181
Warren County | KY | 21227
Warren County | MS | 28149
Warren County | MO | 29219
Warren County | NJ | 34041
Warren County | NY | 36113
Warren County | NC | 37185
Warren County | OH | 39165
Warren County | PA | 42123
Warren County | TN | 47177
Warren County | VA | 51187
Warrick County | IN | 18173
Wasatch County | UT | 49051
Wasco County | OR | 41065
Waseca County | MN | 27161
Washakie County | WY | 56043
Washburn County | WI | 55129
WASHINGTON | NA | 53000
Washington County | AL | 1129
Washington County | AR | 5143
Washington County | CO | 8121
Washington County | FL | 12133
Washington County | GA | 13303
Washington County | ID | 16087
Washington County | IL | 17189
Washington County | IN | 18175
Washington County | IA | 19183
Washington County | KS | 20201
Washington County | KY | 21229
Washington County | ME | 23029
Washington County | MD | 24043
Washington County | MN | 27163
Washington County | MS | 28151
Washington County | MO | 29221
Washington County | NE | 31177
Washington County | NY | 36115
Washington County | NC | 37187
Washington County | OH | 39167
Washington County | OK | 40147
Washington County | OR | 41067
Washington County | PA | 42125
Washington County | RI | 44009
Washington County | TN | 47179
Washington County | TX | 48477
Washington County | UT | 49053
Washington County | VT | 50023
Washington County | VA | 51191
Washington County | WI | 55131
Washington Parish | LA | 22117
Washita County | OK | 40149
Washoe County | NV | 32031
Washtenaw County | MI | 26161
Watauga County | NC | 37189
Watonwan County | MN | 27165
Waukesha County | WI | 55133
Waupaca County | WI | 55135
Waushara County | WI | 55137
Wayne County | GA | 13305
Wayne County | IL | 17191
Wayne County | IN | 18177
Wayne County | IA | 19185
Wayne County | KY | 21231
Wayne County | MI | 26163
Wayne County | MS | 28153
Wayne County | MO | 29223
Wayne County | NE | 31179
Wayne County | NY | 36117
Wayne County | NC | 37191
Wayne County | OH | 39169
Wayne County | PA | 42127
Wayne County | TN | 47181
Wayne County | UT | 49055
Wayne County | WV | 54099
Waynesboro city | VA | 51820
Weakley County | TN | 47183
Webb County | TX | 48479
Weber County | UT | 49057
Webster County | GA | 13307
Webster County | IA | 19187
Webster County | KY | 21233
Webster County | MS | 28155
Webster County | MO | 29225
Webster County | NE | 31181
Webster County | WV | 54101
Webster Parish | LA | 22119
Weld County | CO | 8123
Wells County | IN | 18179
Wells County | ND | 38103
West Baton Rouge Parish | LA | 22121
West Carroll Parish | LA | 22123
West Feliciana Parish | LA | 22125
WEST VIRGINIA | NA | 54000
Westchester County | NY | 36119
Westmoreland County | PA | 42129
Westmoreland County | VA | 51193
Weston County | WY | 56045
Wetzel County | WV | 54103
Wexford County | MI | 26165
Wharton County | TX | 48481
Whatcom County | WA | 53073
Wheatland County | MT | 30107
Wheeler County | GA | 13309
Wheeler County | NE | 31183
Wheeler County | OR | 41069
Wheeler County | TX | 48483
White County | AR | 5145
White County | GA | 13311
White County | IL | 17193
White County | IN | 18181
White County | TN | 47185
White Pine County | NV | 32033
Whiteside County | IL | 17195
Whitfield County | GA | 13313
Whitley County | IN | 18183
Whitley County | KY | 21235
Whitman County | WA | 53075
Wibaux County | MT | 30109
Wichita County | KS | 20203
Wichita County | TX | 48485
Wicomico County | MD | 24045
Wilbarger County | TX | 48487
Wilcox County | AL | 1131
Wilcox County | GA | 13315
Wilkes County | GA | 13317
Wilkes County | NC | 37193
Wilkin County | MN | 27167
Wilkinson County | GA | 13319
Wilkinson County | MS | 28157
Will County | IL | 17197
Willacy County | TX | 48489
Williams County | ND | 38105
Williams County | OH | 39171
Williamsburg city | VA | 51830
Williamsburg County | SC | 45089
Williamson County | IL | 17199
Williamson County | TN | 47187
Williamson County | TX | 48491
Wilson County | KS | 20205
Wilson County | NC | 37195
Wilson County | TN | 47189
Wilson County | TX | 48493
Winchester city | VA | 51840
Windham County | CT | 9015
Windham County | VT | 50025
Windsor County | VT | 50027
Winkler County | TX | 48495
Winn Parish | LA | 22127
Winnebago County | IL | 17201
Winnebago County | IA | 19189
Winnebago County | WI | 55139
Winneshiek County | IA | 19191
Winona County | MN | 27169
Winston County | AL | 1133
Winston County | MS | 28159
Wirt County | WV | 54105
WISCONSIN | NA | 55000
Wise County | TX | 48497
Wise County | VA | 51195
Wolfe County | KY | 21237
Wood County | OH | 39173
Wood County | TX | 48499
Wood County | WV | 54107
Wood County | WI | 55141
Woodbury County | IA | 19193
Woodford County | IL | 17203
Woodford County | KY | 21239
Woodruff County | AR | 5147
Woods County | OK | 40151
Woodson County | KS | 20207
Woodward County | OK | 40153
Worcester County | MD | 24047
Worcester County | MA | 25027
Worth County | GA | 13321
Worth County | IA | 19195
Worth County | MO | 29227
Wrangell City and Borough | AK | 2275
Wright County | IA | 19197
Wright County | MN | 27171
Wright County | MO | 29229
Wyandot County | OH | 39175
Wyandotte County | KS | 20209
WYOMING | NA | 56000
Wyoming County | NY | 36121
Wyoming County | PA | 42131
Wyoming County | WV | 54109
Wythe County | VA | 51197
Yadkin County | NC | 37197
Yakima County | WA | 53077
Yakutat City and Borough | AK | 2282
Yalobusha County | MS | 28161
Yamhill County | OR | 41071
Yancey County | NC | 37199
Yankton County | SD | 46135
Yates County | NY | 36123
Yavapai County | AZ | 4025
Yazoo County | MS | 28163
Yell County | AR | 5149
Yellow Medicine County | MN | 27173
Yellowstone County | MT | 30111
Yoakum County | TX | 48501
Yolo County | CA | 6113
York County | ME | 23031
York County | NE | 31185
York County | PA | 42133
York County | SC | 45091
York County | VA | 51199
Young County | TX | 48503
Yuba County | CA | 6115
Yukon-Koyukuk Census Area | AK | 2290
Yuma County | AZ | 4027
Yuma County | CO | 8125
Zapata County | TX | 48505
Zavala County | TX | 48507
Ziebach County | SD | 46137

## Detailed - Social & Ads
Project | Source | Platform | Campaign Name | Reach | Impressions | Engagement | Link Clicks | ETT Page Submissions | RSVPs | Attendees | Notes | Owner
Frasier Solar | CROP | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦KNOX-OH | 29789 | 177541 | 116458 | 7 | 327 | 33 |  |  | Sydney Wray
Frasier Solar | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦KNOX-OH¦JOBS | 17961 | 153032 | 77229 | 11 | 0 | 0 |  |  | Sydney Wray
Frasier Solar | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦KNOX-OH¦DITL | 13964 | 62315 | 43671 | 4 | 0 | 0 |  |  | Sydney Wray
Frasier Solar | ACE | Facebook, Instagram | ADVO¦S-OH¦YOU/Knox County - State & County Level | 562616 | 1664818 | 392821 | 7588 | 0 | 0 |  |  | Sydney Wray
Mesa County Solar Moratorium | CROP | Facebook, Instagram | TRAFFIC¦MEETING¦MESA-CO | 6779 | 110739 | 6243 | 686 | 0 |  |  |  | Sydney Wray
Mesa County Solar Moratorium | CROP | Facebook, Instagram | PERS¦S-OH¦ALL¦MESA - CO | 44678 | 155625 | 93327 | 2 | 0 |  |  |  | Sydney Wray
Mesa County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦MESA-CO¦JOBS | 21301 | 111201 | 67359 | 290 | 0 |  |  |  | Sydney Wray
Mesa County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦MESA-CO¦DITL | 11642 | 27264 | 19549 | 2 | 0 |  |  |  | Sydney Wray
Yavapai County Solar Moratorium | CROP | Facebook, Instagram | TRAFFIC¦MEETING¦YAVAPAI-AZ | 19345 | 44987 | 4339 | 500 | 0 |  |  |  | Sydney Wray
Yavapai County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-AZ¦ALL¦YAVAPAI-AZ¦DITL | 6335 | 16392 | 14181 | 0 | 0 |  |  |  | Sydney Wray
Yavapai County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-AZ¦ALL¦YAVAPAI-AZ¦JOBS | 31278 | 182190 | 124113 | 336 | 0 |  |  |  | Sydney Wray
Mohave County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-AZ¦ALL¦MOHAVE-AZ¦DITL | 9862 | 31253 | 27802 | 0 | 0 |  |  |  | Sydney Wray
Mohave County Solar Moratorium | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-AZ¦ALL¦MOHAVE-AZ¦JOBS | 19584 | 125321 | 107146 | 226 | 0 |  |  |  | Sydney Wray
Propel Transmission | [7 empty] | 0 |  |  | No Social Activation | Sydney Wray
Clear Mountain | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦CLERMONT-OH¦JOBS | 56135 | 315218 | 136420 | 779 | 0 |  |  |  | Sydney Wray
Clear Mountain | AEJ | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦CLERMONT-OH¦DITL | 12164 | 32490 | 162279 | 2 | 0 |  |  |  | Sydney Wray
Clear Mountain | CROP | Facebook, Instagram | INCLUDE in IRA Hub ¦TRAFFIC¦MEETING¦CLERMONT-OH | 47742 | 189023 | 51032 | 2921 | 0 |  |  |  | Sydney Wray
Clear Mountain | CROP | Facebook, Instagram | INCLUDE in IRA Hub ¦PERS¦S-OH¦ALL¦CLERMONT | 91810 | 271237 | 124364 | 16 | 0 |  |  |  | Sydney Wray
Ochoa Energy BESS | [10 empty] | No Social Activation | Sydney Wray
Lexington Solar | AEJ | Facebook, Instagram | PERS¦S-KY¦ALL¦Fayette County Solar Vote | 106267 | 479426 | 105406 | 6857 | 0 | 4 |  |  | Sydney Wray
Lexington Solar | CROP | Facebook, Instagram | TRAFFIC¦S-KY¦ALL¦Fayette County Solar Vote | 104124 | 641006 | 120046 | 8163 | 0 | 0 |  |  | Sydney Wray
Prospect and Janus Solar Project | [10 empty] | No Social Activation | Sydney Wray
Town of Babylon BESS Moratorium | [10 empty] | No Social Activation | Sydney Wray
Dawn Harvest Solar | CROP | Facebook, Instagram | ADVO¦S-WI¦ALL¦Dawn Harvest Leads SIPE | 33595 | 168545 | 8588 | 693 | 8 | 7 |  |  | Sydney Wray
Dawn Harvest Solar | CROP | Facebook, Instagram | TRAFFIC¦S-WI¦ALL¦Rock County Solar Comment | 238444 | 606669 | 237082 | 14269 | 51 | 0 |  |  | Sydney Wray
Dawn Harvest Solar | ACE | Facebook, Instagram | TRAFFIC¦S-WI¦ALL¦Rock County Solar Comment | 110497 | 251994 | 66484 | 5098 | 87 | 0 |  |  | Sydney Wray
Hope Ridge Wind | ACE | Facebook, Instagram | TRAFFIC¦S-KS¦ALL¦Dickinson County KS - Wind Hearing | 23728 | 305340 | 12024 | 1823 | 1 | 18 |  |  | Sydney Wray
Hope Ridge Wind | CROP | Facebook, Instagram | TRAFFIC¦S-KS¦ALL¦Dickinson County KS - Wind Hearing | 3532 | 36604 | 1637 | 89 | 0 | 0 |  |  | Sydney Wray
Southampton BESS Moratorium | [10 empty] | No Social Activation | Sydney Wray
Birch Coulee | [10 empty] | No Social Activation | Sydney Wray
Coweta County Solar | CROP | Facebook, Instagram | PERS¦S-GA¦ALL¦Coweta County Solar Ordinance | 12264 | 217744 | 6819 | 670 | 0 | 5 |  |  | Sydney Wray
Pinal County Solar | CROP | Facebook, Instagram | TRAFFIC¦S-AZ¦ALL¦Pinal County Solar | 35966 | 490801 | 24353 | 2476 | 0 | 11 |  |  | Sydney Wray
Jackson County Wind | CROP | Facebook, Instagram | TRAFFIC¦S-IA¦ALL¦Jackson County IA - Wind Ordinance | 1361 | 11535 | 400 | 27 | 0 | 0 |  |  | Sydney Wray
Halifax County Solar | CROP | Facebook, Instagram | TRAFFIC¦S-VA¦ALL¦Halifax County VA - Solar Hearing | 1137 | 9881 | 200 | 28 | 0 | 0 |  |  | Sydney Wray
Cass County Solar | CROP | Facebook, Instagram | TRAFFIC¦S-NE¦ALL¦Cass County NE - Solar Hearing 12.2.24 | 2337 | 17834 | 437 | 53 | 0 | 0 |  |  | Sydney Wray
Cass County Solar | CROP | Facebook, Instagram | TRAFFIC¦S-NE¦ALL¦Cass County NE - Solar Hearing | 1184 | 10497 | 225 | 27 | 0 | 0 |  |  | Sydney Wray
Bright Leaf & Swift Creek Solar + BESS | ASM | Facebook, Instagram | TRAFFIC¦S-NC¦ALL¦ Edgecombe County NC - Solar Commission | 3437 | 31098 | 1975 | 78 | 6 | 0 |  | 6 ETTs submitted from ads | Sydney Wray
Surry County BESS | CROP | Facebook, Instagram | CONVERSION¦S-VA¦ALL¦Surry County Hearing - Second SIPE | 4683 | 33005 | 1349 | 88 | 6 | 0 |  |  | Sydney Wray
Surry County BESS | CROP | Facebook, Instagram | TRAFFIC¦S-VA¦ALL¦Surry County VA BESS ordinance | 20142 | 283777 | 9294 | 922 | 0 | 0 |  |  | Sydney Wray
Paddlefish Solar | [10 empty] | Huntington County - No action yet | Sydney Wray
Paddlefish Solar | [10 empty] | Wells County - No action yet | Sydney Wray
Hope Hull Solar | ASM | Facebook, Instagram | CONVERSION¦S-AL¦ALL¦SR Hope Hull Solar Comment SIPE | 2612 | 15457 | 364 | 51 | 27 | 0 |  |  | Sydney Wray
Hope Hull Solar | ASM | Facebook, Instagram | TRAFFIC¦S-AL¦ALL¦SR Hope Hull Solar Project Intervention | 5037 | 28070 | 3059 | 108 | 0 | 0 |  |  | Sydney Wray
Eastern Cottontail Solar | CROP | Facebook, Instagram | CONVERSION¦S-OH¦COM¦Eastern Cottontail Solar SIPE | 23556 | 166275 | 10175 | 399 | 3 | 0 |  |  | Sydney Wray
Schnebly Coulee Solar | [10 empty] | No social activation | Sydney Wray
Sussex County Offshore Wind Project | [10 empty] | No social activation | Sydney Wray
Rancho Viejo Solar | CROP | Facebook, Instagram | ADVO¦S-NM¦SUP¦Rancho Viejo ETT SIPE | 2338 | 18226 | 979 | 84 | 31 | 55 |  | 0 | Sydney Wray
Rancho Viejo Solar | ASM | Facebook, Instagram | S-NM-SP-RENE-AC0219-Rancho Viejo Solar and BESS-ADVO-META-CONV-ADS-Santa Fe County-ETT Campaign | 6086 | 25323 | 1332 | 363 | 16 | 0 | 0 | 0 | Sydney Wray
Hesperus Solar | [10 empty] | No social activation | Sydney Wray
Prairie Power Solar Farm | [10 empty] | Longitudinal Study | Sydney Wray
Soul City Solar Project | [10 empty] | Longitudinal Study | Sydney Wray
Libra Solar Project | [10 empty] | Longitudinal Study | Sydney Wray
Greenlink West Transmission Project | [10 empty] | Longitudinal Study | Sydney Wray
Dry Lake East Energy Center | [10 empty] | Longitudinal Study | Sydney Wray
Blue Ridge Solar | [10 empty] | Longitudinal Study | Sydney Wray
Michaux Solar | [10 empty] | Longitudinal Study | Sydney Wray
Michaux Solar | [10 empty] | Longitudinal Study | Sydney Wray
Grand Junction Solar | [10 empty] | Longitudinal Study | Sydney Wray
Split Rail Solar | [10 empty] | Longitudinal Study | Sydney Wray
Badger Hollow Wind | CROP | Facebook, Instagram | CONVERSION¦S-WI¦ALL¦Badger Hollow Wind Project | 10224 | 26830 | 7135 | 230 | 117 | 0 |  | Combined Grant & Iowa Counties | Sydney Wray
Badger Hollow Wind | CROP | Facebook, Instagram | TRAFFIC¦S-WI¦ALL¦Badger Hollow Wind Project | 94471 | 224421 | 49454 | 8386 | 0 | 0 |  | Combined Grant & Iowa Counties | Sydney Wray
Badger Hollow Wind | CROP | Facebook, Instagram | ADVO¦S-WI¦ALL¦Badger Hollow Phase 2 | 7657 | 38796 | 13026 | 774 | 125 | 0 |  | Combined Grant & Iowa Counties | Sydney Wray
Badger Hollow Wind | CROP | Facebook, Instagram | S-WI-SP-RENE-AC0081-Badger Hollow Wind-ADVO-META-CONV-ADS-Iowa & Grant Counties-Phase 3 Comment | 113282 | 352171 | 8034 | 489 | 80 | 0 |  | Combined Grant & Iowa Counties | Sydney Wray
Uplands Wind | [10 empty] | Lafayette County | Sydney Wray
Uplands Wind | [10 empty] | Iowa County | Sydney Wray
Uplands Wind | [10 empty] | Grant County | Sydney Wray
Mount Vernon BESS | CROP | Facebook, Instagram | CONVERSION¦S-WA¦COM¦Skagit County WA BESS | 4052 | 36271 | 783 | 141 | 5 | 0 |  |  | Sydney Wray
Mount Vernon BESS | CROP | Facebook, Instagram | TRAFFIC¦S-WI¦ALL¦Skagit County WA BESS | 1845 | 3137 | 148 | 16 | 0 | 0 |  |  | Sydney Wray
Gabriel Solar | CROP | Facebook, Instagram | TRAFFIC¦S-VA¦ALL¦Prince Edward County VA Solar + Storage | 37131 | 226826 | 5302 | 1290 | 8 | 0 |  |  | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency - Aug | 4616 | 13488 | 1103 | 0 | 0 | 0 | 0 | Payne County - Ground Softening | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency - Aug | 6131 | 14998 | 1113 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency - March SIPE - COPY | 10976 | 52075 | 4622 | 0 | 0 | 0 | 0 | Payne County - Ground Softening | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency - March SIPE | 16891 | 62782 | 5529 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency - March SIPE | 77892 | 254081 | 25681 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Keystone Reach Round 2 SIPE | 1180 | 2846 | 329 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | ENGM¦S-OK¦COM¦RWE - Keystone - Ground Softening SIPE | 6369 | 13244 | 5594 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening - Increased Frequency SIPE | 110898 | 327570 | 35429 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Keystone Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Keystone - Ground Softening SIPE | 6505 | 9268 | 1066 | 0 | 0 | 0 | 0 | Pawnee County - Ground Softening Only | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf Reach Round 2 - March SIPE | 1668 | 5586 | 751 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf RSVP SIPE | 1560 | 19063 | 1051 | 55 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf Leads SIPE | 867 | 10675 | 627 | 49 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf Reach Round 2 SIPE | 1324 | 2928 | 391 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ENGM¦S-OK¦COM¦RWE - Prairie Wolf - Ground Softening SIPE | 5576 | 12338 | 4920 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Prairie Wolf - Ground Softening - Increased Frequency SIPE | 95730 | 282364 | 34000 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | PERS¦S-OK¦COM¦RWE - Prairie Wolf - Ground Softening SIPE | 4043 | 5870 | 692 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf Reach Round 3 SIPE | 1258 | 3479 | 321 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Prairie Wolf Wind | CROP | Facebook, Instagram | ADVO¦S-OK¦ALL¦Prairie Wolf Reach Round 3 SIPE | 4138 | 14886 | 1616 | 0 | 0 | 0 | 0 | Combined Hughes & Okfuskee Counties | Sydney Wray
Iron Pine Solar | CROP | Facebook, Instagram | ADVO¦S-MN¦ALL¦Iron Pine Leads SIPE | 14393 | 57786 | 4549 | 407 | 64 | 0 |  |  | Sydney Wray
Westfield Battery Ordinance | ASM | Facebook, Instagram | ADVO¦S-MA¦ALL¦Westfield BESS Ordinance Leads SIPE | 8134 | 36565 | 99 | 80 | 0 | 0 |  |  | Sydney Wray
Bolivar Onshore Wind Ordinance | [10 empty] | No activation | Sydney Wray
Goshen Onshore Wind Ordinance | CROP | Facebook, Instagram | ADVO¦S-WY¦ALL¦Goshen Ordinance Leads SIPE | 178 | 815 | 15 | 1 | 0 | 0 |  |  | Sydney Wray
Lee Onshore Wind & Solar Ordinance | [10 empty] | No activation | Sydney Wray
New York Rapid Act | [10 empty] | No activation | Sydney Wray
Daviess Solar Ordinance | [10 empty] | No activation | Sydney Wray
Surprise BESS Ordinance | [10 empty] | Awaiting legal decision for activation | Sydney Wray
Livingston Energy Storage | [10 empty] | No activation | Sydney Wray
Hanover BESS | [10 empty] | No activation | Sydney Wray
Yellow Barn Solar | [10 empty] | No social activation | Sydney Wray
Grass Lake Solar | [10 empty] | No activation | Sydney Wray
New Frontiers Solar Park | CROP | Facebook, Instagram | ADVO¦S-KY¦ALL¦Breckinridge KY SIPE | 11570 | 61116 | 11432 | 636 | 80 | 0 |  | There were 13 additional comments: 6 from neighboring states—1 IN, 1 MO, 2 OH, 1 TN, 1 WV, and 7 from AL. The 7 comments that appear AL-based are actually KY-based (as evidenced by phone number area codes)—this was a technical mistake fixed early in the process. 2 comments from Breckinridge County | Sydney Wray
Darden Energy Center | [10 empty] | No activation | Sydney Wray
Blue Lake BESS | [10 empty] | No activation | Sydney Wray
Valley Farms Energy Storage | [10 empty] | No activation | Sydney Wray
Ironwood Transmission Line | [10 empty] | No activation | Sydney Wray
Flickertail Solar | CROP | Facebook, Instagram | ADVO¦S-ND¦ALL¦Flickertail - Traffic SIPE | 7153 | 103822 | 4122 | 190 | 0 | 0 | 0 | Mobilize page, not ETT | Sydney Wray
Gibson Solar | CROP | Facebook, Instagram | ADVO¦S-VA¦ALL¦King George Cty ETT SIPE | 706 | 4866 | 114 | 22 | 0 |  |  |  | Sydney Wray
Midwater Energy Storage | CROP | Facebook, Instagram | ADVO¦S-MN¦ALL¦Freeborn MN ETT | 20442 | 70714 | 9668 | 1049 | 102 |  |  | 102 subs from MN, 0 from county | Sydney Wray
Antlers Road Solar | [10 empty] | No activation | Sydney Wray
Allen County Solar Ordinance | ASM | Facebook, Instagram | C-IN-SP-REOR-AC0142-Solar only-ADVO-META-CONV-ADS-Allen County, IN-Comment Campaign | 9427 | 56743 | 305 | 211 | 3 | 0 | 0 |  | Sydney Wray
Allen County Solar Ordinance | ASM | Facebook, Instagram | C-IN-SP-REOR-AC0142-Solar only-INTV-META-CONV-ADS-Allen County, IN-Allen County Solar Ord - ETT 2 | 9537 | 79134 | 554 | 340 | 15 | 0 | 0 | 0 | Sydney Wray
Purple Sage BESS | CROP | Facebook, Instagram | C-TX-SP-RENE-MC0052-Purple Sage BESS-INTV-META-REAC-ADS-Ground Softening Phase 1 | 75441 | 182087 | 7712 | 8 | 0 | 0 | 0 | Ground Softening Only | Sydney Wray
Purple Sage BESS | CROP | Facebook, Instagram | C-TX-SP-RENE-MC0052-Purple Sage BESS-INTV-META-REAC-ADS-Ground Softening Phase 1 - July | 113020 | 258525 | 6462 | 10 | 0 | 0 | 0 | Ground Softening Only | Sydney Wray
Purple Sage BESS | CROP | Instagram, Facebook | C-TX-SP-RENE-MC0052-Purple Sage BESS-ADVO-META-IMPR-ADS-Purple Sage BESS - GS 3 | 54168 | 114214 | 2347 | 8 | 0 | 0 | 0 | Ground Softening Only | Sydney Wray
Whitewater Solar | [10 empty] | No ads | Sydney Wray
Isabelle Creek Solar | [10 empty] | No ads | Sydney Wray
Massey BESS | [10 empty] | No ads | Sydney Wray
Cobia Solar | [10 empty] | No ads | Sydney Wray
Burr Oak Solar | [10 empty] | No ads | Sydney Wray
Sloopy Solar Energy Center | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar High Priority |  | 195508 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Compass Energy Storage | [10 empty] | No ads
Wood Duck Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar High Priority |  | 97506 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Wood Duck Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 66829 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Sylvan Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 61287 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Mission Clean Energy Solar Project | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 BESS |  | 59195 | [5 empty] | No ads
Washtenaw Solar Energy Center | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 337356 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Taro Solar | [10 empty] | No ads
North Valley Energy Storage | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-BESS High Priority |  | 986555 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Soda Mountain | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-BESS High Priority |  | 679429 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Downstream Solar Energy Center | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 61592 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Downstream Solar Energy Center | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 58968 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Champaign County BESS Ordinance | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-BESS High Priority |  | 475470 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Earthwise Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 341419 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Union Township Solar Ordinance | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 340063 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Lakeside Solar Project | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 255578 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Lakeside Solar Project | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 151816 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Tilton-Caitlin Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-BESS High Priority |  | 127140 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Tilton-Caitlin Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar High Priority |  | 123040 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Kingwood Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 116809 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Grass River Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 Solar |  | 112636 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Grass River Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 64590 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Town of Ulster BESS | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-09.25 BESS |  | 86130 | [5 empty] | YT Ground Softening only (as of 11/10) | Katie Sims
Fiddlehead Solar | CROP | YouTube | N-MS-AR-APOL-AC0453-ADVO-GVID-VIDV-ADS-CROP Ground Softening-Solar Low Priority |  | 58117

## Detailed - SMS
Project | Source | Channel | Campaign Name | SMS Sent | SMS Delivered | SMS Replies | ETT Page Submissions | RSVPs | Attendees | Notes | Owner
Dawn Harvest Solar | ACE | Inlist - ACE Shortcode | INTV-S-WI-S3-ALL-BLT-OT-SIPE-Rock County WI - Core | 11265 | 9412 |  | 46 |  |  |  | Shaniqua Gibson
Hope Ridge Wind | ACE | Inlist - ACE Shortcode | INTV-S-KS-NC-YOU-BLT-OT-SIPE-Hope Ridge Commissioners Hearing | 9 | 5 |  | 0
Halifax County Solar | ACE | Inlist - ACE Shortcode | EVEN-S-VA-NC-NR-OT-SIPE-Halifax County Solar Ordinance | 20 | 11 |  | 0
Jackson County Wind | ACE | Inlist - ACE Shortcode | EVEN-S-IA-NC-YOU-BLT-OT-SIPE-Jackson County Wind Ordinance - Core | 16 | 13 |  | 0
Cass County Solar | ACE | Inlist - ACE Shortcode | EVEN-S-NE-NC-YOU-BLT-OT-SIPE-Cass County Solar Ordinance 7514841049 | 12 | 10 |  | 0
Hope Hull Solar | ACE | Inlist - ACE Shortcode | INTV-S-AL-S3-ALL-BLT-OT-SIPE-Montgomery Solar Project - Core | 7031 | 5768 |  | 26 |  |  |  | Shaniqua Gibson
Rancho Viejo Solar | ACE | Inlist - ACE Shortcode | INTV-S-NM-S3-ALL-BLT-OT-SIPE-Rancho Viejo Solar - Santa Fe County - Core | 2310 | 1890 |  | 10 | 5 | 5 |  | Shaniqua Gibson
Mount Vernon BESS | ACE | Inlist - ACE Shortcode | INTV-S-WA-S3-ALL-BLT-OT-SIPE-Skagit County 8378184253 | 64 | 53 |  | 0
Iron Pine Solar | ACE | Inlist - ACE Shortcode | INTV-S-MN-S3-ALL-BLT-OT-SIPE-Pine County, MN - Core | 7284 | 6424 |  | 18 |  |  |  | Shaniqua Gibson
Yellow Barn Solar | ACE | Inlist - ACE Shortcode | INTV-S-NY-S3-ALL-BLT-OT-SIPE-Yellow Barn Solar sms - Core | 64 | 50 |  | 0 |  |  |  | Shaniqua Gibson
New Frontiers Solar Park | ACE | Inlist - ACE Shortcode | INTV-S-NY-NC-NR-OT-SIPE-New Frontiers Solar Park-Breckinridge County, KY | 4380 | 3545 |  | 13 |  |  |  | Shaniqua Gibson
Frasier Solar | CROP | Inlist - P2P |  | 2044 | [6 empty] | Roma Joshi
Mesa County Solar Moratorium | CROP | Inlist - P2P |  | 7241 | [6 empty] | Roma Joshi
Yavapai County Solar Moratorium | CROP | Inlist - P2P | EVEN-S-AZ-S3-ALL-P2P-RE-APOL-YAVAPAI AZ [YAN LIST] | 235 |  | 570 |  | 24 | 15 |  | Roma Joshi
Mohave County Solar Moratorium | CROP | Inlist - P2P | EVEN-S-AZ-S3-ALL-P2P-RE-APOL-Mohave AZ Solar Moratorium Hearing | 241 |  |  | 6 | 6 |  |  | Roma Joshi
Propel Transmission | ACE | Inlist - P2P |  | 1287 |  |  |  | 2 |  |  | Roma Joshi
Clear Mountain | CROP | Inlist - P2P | ADVO-S-OH-C-ALL-P2P-OT-SIPE-Clermont County Hearing | 566 |  |  |  | 1 |  |  | Roma Joshi
Ochoa Energy BESS | ACE | Inlist - P2P | EVEN-S-TX-C-ALL-P2P-RE-SIPE-KATY-BESS-OSHOA | 3619 |  |  | 20 | 1 | 1 | 1 RSVP and that person attended (Arya Gandavadi) | Roma Joshi
Lexington Solar
Prospect and Janus Solar Project | ACE | Inlist - P2P | EVEN-S-CO-S3-COM-P2P-RE-SIPE-Weld_Solar | 1286 |  |  |  | 1 | 0 |  | Roma Joshi
Town of Babylon BESS Moratorium | CROP | Inlist - P2P | EVEN-S-NY-S3-COM-P2P-RE-SIPE-Babylon_BESS | 525 |  |  |  | 17 | 1 |  | Roma Joshi
Birch Coulee
Coweta County Solar | ACE | Inlist - ACE Shortcode | EVEN-S-GA-NC-ALL-BLT-OT-SIPE-Coweta Solar Ordinance - Core | 39 | 33 |  | 0
Pinal County Solar | CROP | Inlist - P2P | EVEN-S-AZ-NC-ALL-P2P-OT-SIPE-Pinal_Solar | 956 |  |  |  | 5 | 3 |  | Roma Joshi
Bright Leaf & Swift Creek Solar + BESS
Surry County BESS | ACE |  | INTV-S-VA-NC-YOU-BLT-OT-SIPE-Surry County BESS ¦ Ordinance
Paddlefish Solar
Schnebly Coulee Solar | CROP | Inlist - P2P |  | 208 |  |  | 4 | 2 | 2 |  | Roma Joshi
Eastern Cottontail Solar | CROP | Inlist - P2P | EVEN-S-OH-NC-NR-OT-SIPE-Fairlfield_Solar | 388 | 382 |  |  | 0 | 0 |  | Roma Joshi
Sussex County Offshore Wind Project | ACE | Inlist - P2P
Hesperus Solar
Prairie Power Solar Farm
Soul City Solar Project
Libra Solar Project
Greenlink West Transmission Project
Dry Lake East Energy Center
Blue Ridge Solar
Michaux Solar
Grand Junction Solar
Split Rail Solar
Badger Hollow Wind | ACE | Inlist - ACE Shortcode | ADVO-S-WI-S3-ALL-BLT-OT-SIPE-badger hollow | 11319 | 9474 |  | 57
Uplands Wind
Gabriel Solar | ACE |  | ADVO-S-VA-S3-ALL-BLT-OT-SIPE-Prince Edward County TurnOut | 9 | 6 |  | 0
Keystone Wind
Prairie Wolf Wind
Westfield Battery Ordinance
Bolivar Onshore Wind Ordinance
Goshen Onshore Wind Ordinance
Lee Onshore Wind & Solar Ordinance
New York Rapid Act
Surprise BESS Ordinance
Livingston Energy Storage
Hanover BESS
Grass Lake Solar
New Frontiers Solar Park | ACE | Inlist - ACE Shortcode | INTV-S-KY-NC-ALL-BLT-OT-SIPE-Breckinridge County KY Solar Farm | 4380 | 3545 |  | 13
Darden Energy Center
Blue Lake BESS
Allen County Solar Ordinance
Valley Farms Energy Storage
Ironwood Transmission Line
Coweta County Solar | ACE | Inlist - ACE Shortcode | EVEN-S-GA-NC-ALL-BLT-OT-SIPE-Coweta Solar Ordinance Reminder | 39 | 34 |  | 0
Antlers Road Solar | ACE | Inlist - P2P | INTV-S-VA-NC-ALL-P2P-OT-SIPE-Mecklenburg County, VA - Antlers Road Solar | 22 | 22 | 0 | 0 |  |  |  | Shaniqua Gibson
Midwater Energy Storage
Yellow Rosebush | CROP | Inlist - P2P | INTV-S-OR-NC-ALL-P2P-OT-SIPE-Yellow Rosebush Solar - Wasco, OR | 50 | 50 | 2 |  |  |  |  | Shaniqua Gibson
Fort Watt BESS | CROP | Inlist - P2P | INTV-S-TX-NC-ALL-P2P-OT-SIPE-Fort Watt BESS | 170 | 170 | 7 |  |  |  |  | Shaniqua Gibson
Little Prairie Hybrid | ACE | Inlist - P2P | INTV-S-IL-NC-ALL-P2P-OT-SIPE- Little Prairie Hybrid Champaign, IL | 338 | 338 | 33 |  |  |  |  | Shaniqua Gibson
Gibson Solar | CROP | Inlist - P2P | INTV-S-VA-NC-ALL-P2P-OT-SIPE-KingGeorge-GibsonSolar (copy) | 9 | 9 | 1 |  |  |  |  | Shaniqua Gibson
Badger Hollow Wind | ACE | Inlist - ACE Shortcode | INTV-S-WI-S3-ALL-BLT-OT-SIPE-Badger Hollow Public Comments | 11310 | 9432 | 0 | 69 |  |  |  | Shaniqua Gibson
Allen County Solar Ordinance | ACE | Inlist - ACE Shortcode | C-IN-SP-REOR-AC0142-Solar only-INTV-SUP-BLT-SMS-Allen County, IN-June 12 Public Hearing | 173 | 140 | 0 | 5 |  |  |  | Shaniqua Gibson
Rancho Viejo Solar | ACE | Inlist - ACE Shortcode | S-NM-SP-RENE-AC0219-Rancho Viejo Solar and BESS-INTV-SUP-BLT-SMS-Santa Fe County-Aug2025 | 72 | 60 | 0 | 2 | 2 |  |  | Shaniqua Gibson
Whitewater Solar | ACE | Inlist - ACE Shortcode | S-WI-SP-RENE-AC0226-Whitewater Solar-ADVO-YOU-BLT-SMS-Docket Comment-Docket Comment | 11086 | 9167 | 0 | 56 |  |  |  | Josh Walker
Allen County Solar Ordinance | ACE | Inlist - ACE Shortcode | C-IN-SP-REOR-AC0142-Solar only-ADVO-SUP-BLT-SMS-Allen County IN-Aug 8 Hearing | 165 | 129 | 0 | 4 |  |  |  | Shaniqua Gibson
Cobia Solar | ACE | Inlist - ACE Shortcode | S-IN-SP-RENE-AC0260-Cobia Solar-INTV-SUP-BLT-SMS-Decatur County-Aug 6 SMS | 7 | 6 | 0 | 0 |  |  |  | Shaniqua Gibson
Rancho Viejo Solar | ACE | Inlist - ACE Shortcode | S-NM-SP-RENE-AC0219-Rancho Viejo Solar and BESS-INTV-SUP-BLT-SMS-Santa Fe County-RSVP | 60 | 60 | 0 | 0 |  |  |  | Shaniqua Gibson
Tyco Solar | ACE | Inlist - ACE Shortcode | C-NC-SP-RENE-AC0313-Hyco Solar-INTV-SUP-BLT-SMS-Public Hearing-Aug 14 | 36 | 27 | 0 | 0 |  |  |  | Shaniqua Gibson
Massey BESS | ACE | Inlist - ACE Shortcode | S-TX-SP-RENE-AC0215-Massey BESS-RSVP-YOU-BLT-SMS-City of Baytown-Greenlight BESS info session | 119 | 94 | 0 | 0 | 0 |  |  | Josh Walker
Whitewater Solar | ACE | Inlist - ACE Shortcode | C-WI-SP-RENE-AC0202-Whitewater Solar-INTV-SUP-BLT-SMS-Jefferson County, WI-June 25 Open House | 135 | 105 | 0 | 0 | 0
Badger Hollow Wind | ACE | Inlist - ACE Shortcode | S-WI-SP-RENE-AC0081-Badger Hollow Wind-PUBC-ALL-BLT-SMS-Iowa & Grant Counties-Third Comment Period | 11269 | 9385 | 0 | 67 | 0 |  |  | Shaniqua Gibson
Badger Hollow Wind | ACE | Inlist - ACE Shortcode | S-WI-SP-RENE-AC0081-Badger Hollow Wind-PUBC-ALL-BLT-SMS-Iowa | 11184 | 9267 | 0 | 34 | 0 |  |  | Shaniqua Gibson
Claire BESS | ACE | Inlist - ACE Shortcode | C-TX-SP-RENE-AC0527-Claire BESS-INTV-SUP-P2P-P2P-Baytown-RSVP Nov 2025 | 214 | 214 | 1 |  | 0

## Detailed - Emails
Project | Source | Campaign Name | Emails Sent | ETT Page Submissions | RSVPs | Attendees | Notes | Owner | Last Updated
Frasier Solar | ACE |  | 23 |  |  |  |  | Roma Joshi | 2025-11-20 11:57
Mesa County Solar Moratorium | AEJ
Yavapai County Solar Moratorium | ASM
Mohave County Solar Moratorium | CROP |  |  | 44 |  |  |  |  | 2025-11-20 11:57
Propel Transmission
Clear Mountain |  |  |  | 35 |  |  |  |  | 2025-11-20 11:57
Ochoa Energy BESS
Lexington Solar
Prospect and Janus Solar Project
Town of Babylon BESS Moratorium
Dawn Harvest Solar | ACE | INTV-S-WI-S3-ALL-BLT-OT-SIPE-Dawn Harvest Solar Project | 23886 | 25 |  |  |  |  | 2025-11-20 11:57
Dawn Harvest Solar | ACE | ADVO-S-WI-NC-YOU-BLT-OT-DAWN-Dawn Solar | 5029 | 1 |  |  |  |  | 2025-11-20 11:57
Hope Ridge Wind | ACE | NTV-S-KS-NC-YOU-BLT-OT-SIPE-Hope Ridge Wind Commissioner Hearing | 31 | 0 |  |  |  |  | 2025-11-20 11:57
Hope Ridge Wind | ACE | EVEN-S-KS-NC-ALL-BLT-OT-SIPE-Hope Ridge-2 | 31 | 0 |  |  |  |  | 2025-11-20 11:57
Hope Ridge Wind | ACE | EVEN-S-KS-NC-ALL-BLT-OT-SIPE-Dickinson County Hope Ridge Meeting 2 | 30 | 0 |  |  |  |  | 2025-11-20 11:57
Southampton BESS Moratorium
Birch Coulee | ACE | ADVO-S-MN-NC-ALL-BLT-OT-SIPE-Birch Coulee Solar | 12690 | 14 |  |  |  |  | 2025-11-20 11:57
Coweta County Solar | ACE | EVEN-S-GA-NC-NR-OT-SIPE-Coweta Solar Ordinance Reminder | 106 | 0 |  |  |  |  | 2025-11-20 11:57
Coweta County Solar | ACE | EVEN-S-GA-NC-NR-OT-SIPE-Coweta Solar Ordinance | 106 | 0 |  |  |  |  | 2025-11-20 11:57
Pinal County Solar
Jackson County Wind | ACE | EVEN-S-IA-NC-YOU-BLT-OT-SIPE-Jackson County Wind Ordinance | 20 | 0 |  |  |  |  | 2025-11-20 11:57
Halifax County Solar | ACE | EVEN-S-VA-NC-NR-OT-SIPE-Halifax County Solar Ordinance | 30 | 0 |  |  |  |  | 2025-11-20 11:57
Cass County Solar | ACE | INTV-S-NE-NC-YOU-BLT-OT-SIPE-Cass County Solar Ordinance | 12 | 0 |  |  |  |  | 2025-11-20 11:57
Cass County Solar | ACE | INTV-S-NE-NC-YOU-BLT-OT-SIPE- Cass County Solar Ordinance Second Hearing | 12 | 0 |  |  |  |  | 2025-11-20 11:57
Bright Leaf & Swift Creek Solar + BESS
Surry County BESS
Paddlefish Solar
Hope Hull Solar | ACE | EVEN-S-AL-NC-YOU-BLT-OT-SIPE-SR Hope Hull Montgomery | 201 | 0 |  |  |  |  | 2025-11-20 11:57
Eastern Cottontail Solar
Schnebly Coulee Solar
Sussex County Offshore Wind Project
Rancho Viejo Solar | ACE | INTV-S-NM-NC-ALL-BLT-OT-SIPE-Rancho Viejo Solar Sante Fe | 4779 | 9 |  |  |  |  | 2025-11-20 11:57
Hesperus Solar
Prairie Power Solar Farm
Soul City Solar Project
Libra Solar Project
Greenlink West Transmission Project
Dry Lake East Energy Center
Blue Ridge Solar
Michaux Solar
Grand Junction Solar
Split Rail Solar
Badger Hollow Wind | ACE | INTV-S-WI-S3-ALL-BLT-OT-SIPE-Badger Hollow Public Comments | 23929 | 27 |  |  |  |  | 2025-11-20 11:57
Uplands Wind
Mount Vernon BESS | ACE | INTV-S-WA-S3-ALL-BLT-OT-SIPE-Skagit County ETT | 107 | 0 |  |  |  |  | 2025-11-20 11:57
Gabriel Solar | ACE | INTV-S-VA-S3-ALL-BLT-OT-SIPE-Prince Edward County Turnout | 32 | 0 |  |  |  |  | 2025-11-20 11:57
Keystone Wind
Prairie Wolf Wind
Iron Pine Solar | ACE | INTV-S-MN-S3-ALL-BLT-OT-SIPE-Pine County, MN | 7259 | 4 |  |  |  |  | 2025-11-20 11:57
Westfield Battery Ordinance
Bolivar Onshore Wind Ordinance
Goshen Onshore Wind Ordinance
Lee Onshore Wind & Solar Ordinance
New York Rapid Act
Daviess Solar Ordinance
Surprise BESS Ordinance
Livingston Energy Storage
Hanover BESS
Yellow Barn Solar | ACE | INTV-S-NY-S3-ALL-BLT-OT-SIPE-Yellow Barn Solar | 228 | 0 |  |  |  | Shaniqua Gibson | 2025-11-20 11:57
Grass Lake Solar
New Frontiers Solar Park |  | INTV-S-KY-NC-ALL-BLT-OT-SIPE-Breckinridge County KY | 8704 | 4 |  |  |  |  | 2025-11-20 11:57
Darden Energy Center
Blue Lake BESS
Allen County Solar Ordinance
Valley Farms Energy Storage
Ironwood Transmission Line
Gibson Solar | ACE | INTV-S-VA-NC-ALL-BLT-OT-SIPE-GibsonSolar | 19 | 0 |  |  |  | Shaniqua Gibson | 2025-11-20 11:57
Antlers Road Solar | ACE | S-VA-SP-RENE-AC0061-Antlers Road Solar-ADVO-ALL-BLT-EML-Mecklenburg County, VA-ETT | 28 | 0 |  |  |  | Shaniqua Gibson | 2025-11-20 11:57
Midwater Energy Storage
Badger Hollow Wind | ACE | INTV-S-WI-S3-ALL-BLT-OT-SIPE-Badger Hollow Comments | 23799 | 22 |  |  |  | Shaniqua Gibson | 2025-11-20 11:57
Allen County Solar Ordinance | ACE | C-IN-SP-REOR-AC0142-Solar only-INTV-SUP-BLT-EML-Allen CountyIN | 362 | 0 |  |  |  | Shaniqua Gibson | 2025-11-20 11:57
Fort Watt BESS
Whitewater Solar | ACE
Rancho Viejo Solar | ACE | S-NM-SP-RENE-AC0219-Rancho Viejo Solar and BESS-INTV-SUP-BLT-EML-Santa Fe County-Aug2025 | 182 | 0 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Allen County Solar Ordinance | ACE | C-IN-SP-REOR-AC0142-Solar only-ADVO-SUP-BLT-EML-Allen County IN-Aug 8 Hearing | 359 | 0 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Cobia Solar | ACE | S-IN-SP-RENE-AC0260-Cobia Solar-INTV-SUP-BLT-EML-Decatur County-Aug 6 email | 14 | 0 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Rancho Viejo Solar | ACE | S-NM-SP-RENE-AC0219-Rancho Viejo Solar and BESS-INTV-SUP-BLT-EML-Santa Fe County-RSVP | 181 | 0 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Badger Hollow Wind | ACE | S-WI-SP-RENE-AC0081-Badger Hollow Wind-PUBC-ALL-BLT-EML-Iowa & Grant Counties-Third Comment Period | 23771 | 23 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Allen County Solar Ordinance | ACE | C-IN-SP-REOR-AC0142-Solar only-INTV-SUP-BLT-EML-Allen County, IN | 362 | 0 | 0 |  |  | Shaniqua Gibson | 2025-11-20 11:57
Formulas:
Last Updated = IF(AND(ISBLANK([Emails Sent]),ISBLANK([ETT Page Submissions]),ISBLANK([RSVPs])),,LAMBDA(triggers,LAMBDA(x,x)(NOW()))(HSTACK([Emails Sent]:[RSVPs])))

## Detailed - Calls
Project | Source | Channel | Campaign Name | Calls | Calls Answered/Right Number | ETT Page Submissions | RSVPs | Attendees | Notes | Owner
Frasier Solar | ACE | Inlist - ACE Shortcode
Mesa County Solar Moratorium | AEJ | Inlist - P2P | Mesa County, CO call in [YAN List] | 229 | 27 |  | 3
Yavapai County Solar Moratorium | CROP | Inlist - P2P | EVEN-S-AZ-S3-ALL-P2P-RE-APOL-YAVAPAI AZ [YAN LIST] | 485 | 21 |  | 13 |  |  | Roma Joshi
Mohave County Solar Moratorium | CROP | Inlist - P2P | EVEN-S-AZ-S3-ALL-P2P-RE-APOL-Mohave AZ Solar Moratorium Hearing | 244 | 37 | 2 | 3 |  |  | Roma Joshi
Propel Transmission
Hope Hull Solar | ACE |  | Sr-Hope Hull Solar Project | 525 |  |  | 23 |  |  | Rodrigo Escotto
Hope Hull Solar | ACE |  | Sr-Hope Hull Solar Project |  |  |  | 5
Hope Hull Solar | ACE |  | Sr-Hope Hull Solar Project |  |  |  | 50 | 12
Iron Pine Solar | ACE |  |  | 884 | 575 |  | 30 |  |  | Rodrigo Escotto
Flickertail Solar | CROP |  | Flickertail Solar | 680 | 415 |  | 1 |  |  | Rodrigo Escotto
Gabriel Solar | ACE |  | Gabriel Solar | 624 | 288 |  | 1 |  |  | Rodrigo Escotto
Gibson Solar | CROP |  |  | 2324 | 2072 |  | 11 |  |  | Rodrigo Escotto
Goshen Onshore Wind Ordinance | ACE |  | Wind Ordinance | 554 | 321 |  | 7 |  |  | Rodrigo Escotto
Rancho Viejo Solar | ACE |  | Rancho Viejo Solar Project | 660 | 461 |  | 82 |  |  | Jerssay Arredondo
Blue Lake BESS | ASM |  | Blue Lake BESS | 100 | 68 |  | 0 |  |  | Jerssay Arredondo
Antlers Road Solar | CROP | External list - P2P | Antlers Road Solar Project (Round 1) | 2197 | 1602 |  | 0 |  |  | Shaniqua Gibson
Westfield Battery Ordinance | ACE |  | Westfield BESS Ordinance | 665 | 477 |  | 23 |  |  | Rodrigo Escotto
Yellow Rosebush | [9 empty] | Shaniqua Gibson
Fort Watt BESS | CROP | Inlist - P2P | INTV-S-TX-NC-ALL-P2P-OT-SIPE-Fort Watt BESS | 178 | 21 |  |  |  |  | Shaniqua Gibson
Propel Transmission | CROP | Inlist - P2P | Propel Public Hearing - Nassau, NY | 457 | 64 |  |  |  |  | Shaniqua Gibson
Antlers Road Solar | CROP | External list - P2P | Antlers Road Solar Project (Round 2) | 175 | 132 |  | 5 |  |  | Shaniqua Gibson
San Luis Obispo OSW | ACE | Inlist - P2P | INTV-S-CA-S3-COM-P2P-OT-SIPE-SLO County- CA | 757 | 682 | 20 | 9 |  |  | Roma Joshi
Schnebly Coulee Solar | ACE | Inlist - P2P | INTV-S-WA-NC-NR-OT-SIPE-Kittitas_Solar (1_2) | 108 | 19 | 9 | 6 |  |  | Roma Joshi
Rancho Viejo Solar | ACE | Inlist - P2P | EVEN-S-NM-NC-NR-OT-SIPE-Santa Fe_Solar | 690 | 40 |  | 18
Southampton BESS Moratorium | ACE | Inlist - P2P | EVEN-S-NY-S3-COM-P2P-RE-SIPE-Southampton BESS | 0
Prairie Wolf Wind | CROP | Inlist - P2P | RWE Prairie Wolf Open House 02.26 | 25 | 18 |  | 0
Pinal County Solar | CROP | Inlist - P2P | EVEN-S-AZ-NC-ALL-P2P-OT-SIPE-Pinal_Solar | 974 | 86 |  | 2
Ochoa Energy BESS | CROP | Inlist - P2P |  | 0
Cobia Solar | CROP | External list - P2P | Paid Phonebank - Cobia Solar | 1150 | 546 | 6 |  |  | Paid phone bank ETT | Josh Walker
Burr Oak Solar | CROP | External list - P2P | Paid Phonebank - Burr Oak Solar | 5000 | 2555 | 25 | 6 |  | Paid phone bank ETT | Josh Walker
Grifton Solar | CROP | External list - P2P | Paid Phonebank - Grifton Solar | 1285 | 992 | 46 |  |  | Paid phone bank ETT | Josh Walker
Union Township Solar Ordinance | CROP | External list - P2P | Paid Phonebank - Union Township Solar Ordinance | 191 | 160 | 5 |  |  | Paid phone bank ETT | Josh Walker
Paddlefish Solar | CROP | External list - P2P | Paid Phonebank - Paddlefish | 597 | 489 | 11
Juniter Springs Solar + BESS | CROP | External list - P2P | Paid Phonebank - Juniper Springs | 2066 | 1098 | 17 | 6 |  | Paid phone bank ETT | Shaniqua Gibson
Oakham BESS | AEJ | External list - P2P | Paid Phonebank - Oakham BESS | 5129 | 4409 | 44 |  |  | Paid phone bank ETT | Shaniqua Gibson
Hillman Energy Storage | AEJ | External list - P2P | Paid Phonebank - Hillman Energy Storage | 1179 | 1018 | 14 |  |  | Paid phone bank ETT | Shaniqua Gibson
Akron Solar Project | CROP | External list - P2P | Paid Phonebank - Akron Solar Project | 890 | 757 | 10 |  |  | Paid phone bank ETT | Shaniqua Gibson
Cactus Wren BESS | ACE | External list - P2P | Paid Phonebank - Cactus Wren BESS | 314 | 275 | 14 | 1 |  | Paid phone bank ETT | Shaniqua Gibson
New Haven Solar Ordinance | ACE | External list - P2P | Paid Phonebank - New Haven Solar Ordinance | 526 | 492 | 5 |  |  | Paid phone bank ETT | Shaniqua Gibson

## FIPS Data
State Abbr | County Name | FIPS Code | INDEX(FILTER('FIPS Data'!C:C, 'FIPS Data'!A:A=H163, 'FIPS Data'!B:B=D163), 1)
AL | Autauga County | 01001
AL | Baldwin County | 01003
AL | Barbour County | 01005
AL | Bibb County | 01007
AL | Blount County | 01009
AL | Bullock County | 01011
AL | Butler County | 01013
AL | Calhoun County | 01015
AL | Chambers County | 01017
AL | Cherokee County | 01019
AL | Chilton County | 01021
AL | Choctaw County | 01023
AL | Clarke County | 01025
AL | Clay County | 01027
AL | Cleburne County | 01029
AL | Coffee County | 01031
AL | Colbert County | 01033
AL | Conecuh County | 01035
AL | Coosa County | 01037
AL | Covington County | 01039
AL | Crenshaw County | 01041
AL | Cullman County | 01043
AL | Dale County | 01045
AL | Dallas County | 01047
AL | DeKalb County | 01049
AL | Elmore County | 01051
AL | Escambia County | 01053
AL | Etowah County | 01055
AL | Fayette County | 01057
AL | Franklin County | 01059
AL | Geneva County | 01061
AL | Greene County | 01063
AL | Hale County | 01065
AL | Henry County | 01067
AL | Houston County | 01069
AL | Jackson County | 01071
AL | Jefferson County | 01073
AL | Lamar County | 01075
AL | Lauderdale County | 01077
AL | Lawrence County | 01079
AL | Lee County | 01081
AL | Limestone County | 01083
AL | Lowndes County | 01085
AL | Macon County | 01087
AL | Madison County | 01089
AL | Marengo County | 01091
AL | Marion County | 01093
AL | Marshall County | 01095
AL | Mobile County | 01097
AL | Monroe County | 01099
AL | Montgomery County | 01101
AL | Morgan County | 01103
AL | Perry County | 01105
AL | Pickens County | 01107
AL | Pike County | 01109
AL | Randolph County | 01111
AL | Russell County | 01113
AL | St. Clair County | 01115
AL | Shelby County | 01117
AL | Sumter County | 01119
AL | Talladega County | 01121
AL | Tallapoosa County | 01123
AL | Tuscaloosa County | 01125
AL | Walker County | 01127
AL | Washington County | 01129
AL | Wilcox County | 01131
AL | Winston County | 01133
AK | Aleutians East Borough | 02013
AK | Aleutians West Census Area | 02016
AK | Anchorage Municipality | 02020
AK | Bethel Census Area | 02050
AK | Bristol Bay Borough | 02060
AK | Denali Borough | 02068
AK | Dillingham Census Area | 02070
AK | Fairbanks North Star Borough | 02090
AK | Haines Borough | 02100
AK | Hoonah-Angoon Census Area | 02105
AK | Juneau City and Borough | 02110
AK | Kenai Peninsula Borough | 02122
AK | Ketchikan Gateway Borough | 02130
AK | Kodiak Island Borough | 02150
AK | Kusilvak Census Area | 02158
AK | Lake and Peninsula Borough | 02164
AK | Matanuska-Susitna Borough | 02170
AK | Nome Census Area | 02180
AK | North Slope Borough | 02185
AK | Northwest Arctic Borough | 02188
AK | Petersburg Borough | 02195
AK | Prince of Wales-Hyder Census Area | 02198
AK | Sitka City and Borough | 02220
AK | Skagway Municipality | 02230
AK | Southeast Fairbanks Census Area | 02240
AK | Valdez-Cordova Census Area | 02261
AK | Wrangell City and Borough | 02275
AK | Yakutat City and Borough | 02282
AK | Yukon-Koyukuk Census Area | 02290
AZ | Apache County | 04001
AZ | Cochise County | 04003
AZ | Coconino County | 04005
AZ | Gila County | 04007
AZ | Graham County | 04009
AZ | Greenlee County | 04011
AZ | La Paz County | 04012
AZ | Maricopa County | 04013
AZ | Mohave County | 04015
AZ | Navajo County | 04017
AZ | Pima County | 04019
AZ | Pinal County | 04021
AZ | Santa Cruz County | 04023
AZ | Yavapai County | 04025
AZ | Yuma County | 04027
AR | Arkansas County | 05001
AR | Ashley County | 05003
AR | Baxter County | 05005
AR | Benton County | 05007
AR | Boone County | 05009
AR | Bradley County | 05011
AR | Calhoun County | 05013
AR | Carroll County | 05015
AR | Chicot County | 05017
AR | Clark County | 05019
AR | Clay County | 05021
AR | Cleburne County | 05023
AR | Cleveland County | 05025
AR | Columbia County | 05027
AR | Conway County | 05029
AR | Craighead County | 05031
AR | Crawford County | 05033
AR | Crittenden County | 05035
AR | Cross County | 05037
AR | Dallas County | 05039
AR | Desha County | 05041
AR | Drew County | 05043
AR | Faulkner County | 05045
AR | Franklin County | 05047
AR | Fulton County | 05049
AR | Garland County | 05051
AR | Grant County | 05053
AR | Greene County | 05055
AR | Hempstead County | 05057
AR | Hot Spring County | 05059
AR | Howard County | 05061
AR | Independence County | 05063
AR | Izard County | 05065
AR | Jackson County | 05067
AR | Jefferson County | 05069
AR | Johnson County | 05071
AR | Lafayette County | 05073
AR | Lawrence County | 05075
AR | Lee County | 05077
AR | Lincoln County | 05079
AR | Little River County | 05081
AR | Logan County | 05083
AR | Lonoke County | 05085
AR | Madison County | 05087
AR | Marion County | 05089
AR | Miller County | 05091
AR | Mississippi County | 05093
AR | Monroe County | 05095
AR | Montgomery County | 05097
AR | Nevada County | 05099
AR | Newton County | 05101
AR | Ouachita County | 05103
AR | Perry County | 05105
AR | Phillips County | 05107
AR | Pike County | 05109
AR | Poinsett County | 05111
AR | Polk County | 05113
AR | Pope County | 05115
AR | Prairie County | 05117
AR | Pulaski County | 05119
AR | Randolph County | 05121
AR | St. Francis County | 05123
AR | Saline County | 05125
AR | Scott County | 05127
AR | Searcy County | 05129
AR | Sebastian County | 05131
AR | Sevier County | 05133
AR | Sharp County | 05135
AR | Stone County | 05137
AR | Union County | 05139
AR | Van Buren County | 05141
AR | Washington County | 05143
AR | White County | 05145
AR | Woodruff County | 05147
AR | Yell County | 05149
CA | Alameda County | 06001
CA | Alpine County | 06003
CA | Amador County | 06005
CA | Butte County | 06007
CA | Calaveras County | 06009
CA | Colusa County | 06011
CA | Contra Costa County | 06013
CA | Del Norte County | 06015
CA | El Dorado County | 06017
CA | Fresno County | 06019
CA | Glenn County | 06021
CA | Humboldt County | 06023
CA | Imperial County | 06025
CA | Inyo County | 06027
CA | Kern County | 06029
CA | Kings County | 06031
CA | Lake County | 06033
CA | Lassen County | 06035
CA | Los Angeles County | 06037
CA | Madera County | 06039
CA | Marin County | 06041
CA | Mariposa County | 06043
CA | Mendocino County | 06045
CA | Merced County | 06047
CA | Modoc County | 06049
CA | Mono County | 06051
CA | Monterey County | 06053
CA | Napa County | 06055
CA | Nevada County | 06057
CA | Orange County | 06059
CA | Placer County | 06061
CA | Plumas County | 06063
CA | Riverside County | 06065
CA | Sacramento County | 06067
CA | San Benito County | 06069
CA | San Bernardino County | 06071
CA | San Diego County | 06073
CA | San Francisco County | 06075
CA | San Joaquin County | 06077
CA | San Luis Obispo County | 06079
CA | San Mateo County | 06081
CA | Santa Barbara County | 06083
CA | Santa Clara County | 06085
CA | Santa Cruz County | 06087
CA | Shasta County | 06089
CA | Sierra County | 06091
CA | Siskiyou County | 06093
CA | Solano County | 06095
CA | Sonoma County | 06097
CA | Stanislaus County | 06099
CA | Sutter County | 06101
CA | Tehama County | 06103
CA | Trinity County | 06105
CA | Tulare County | 06107
CA | Tuolumne County | 06109
CA | Ventura County | 06111
CA | Yolo County | 06113
CA | Yuba County | 06115
CO | Adams County | 08001
CO | Alamosa County | 08003
CO | Arapahoe County | 08005
CO | Archuleta County | 08007
CO | Baca County | 08009
CO | Bent County | 08011
CO | Boulder County | 08013
CO | Broomfield County | 08014
CO | Chaffee County | 08015
CO | Cheyenne County | 08017
CO | Clear Creek County | 08019
CO | Conejos County | 08021
CO | Costilla County | 08023
CO | Crowley County | 08025
CO | Custer County | 08027
CO | Delta County | 08029
CO | Denver County | 08031
CO | Dolores County | 08033
CO | Douglas County | 08035
CO | Eagle County | 08037
CO | Elbert County | 08039
CO | El Paso County | 08041
CO | Fremont County | 08043
CO | Garfield County | 08045
CO | Gilpin County | 08047
CO | Grand County | 08049
CO | Gunnison County | 08051
CO | Hinsdale County | 08053
CO | Huerfano County | 08055
CO | Jackson County | 08057
CO | Jefferson County | 08059
CO | Kiowa County | 08061
CO | Kit Carson County | 08063
CO | Lake County | 08065
CO | La Plata County | 08067
CO | Larimer County | 08069
CO | Las Animas County | 08071
CO | Lincoln County | 08073
CO | Logan County | 08075
CO | Mesa County | 08077
CO | Mineral County | 08079
CO | Moffat County | 08081
CO | Montezuma County | 08083
CO | Montrose County | 08085
CO | Morgan County | 08087
CO | Otero County | 08089
CO | Ouray County | 08091
CO | Park County | 08093
CO | Phillips County | 08095
CO | Pitkin County | 08097
CO | Prowers County | 08099
CO | Pueblo County | 08101
CO | Rio Blanco County | 08103
CO | Rio Grande County | 08105
CO | Routt County | 08107
CO | Saguache County | 08109
CO | San Juan County | 08111
CO | San Miguel County | 08113
CO | Sedgwick County | 08115
CO | Summit County | 08117
CO | Teller County | 08119
CO | Washington County | 08121
CO | Weld County | 08123
CO | Yuma County | 08125
CT | Fairfield County | 09001
CT | Hartford County | 09003
CT | Litchfield County | 09005
CT | Middlesex County | 09007
CT | New Haven County | 09009
CT | New London County | 09011
CT | Tolland County | 09013
CT | Windham County | 09015
DE | Kent County | 10001
DE | New Castle County | 10003
DE | Sussex County | 10005
DC | District of Columbia | 11001
FL | Alachua County | 12001
FL | Baker County | 12003
FL | Bay County | 12005
FL | Bradford County | 12007
FL | Brevard County | 12009
FL | Broward County | 12011
FL | Calhoun County | 12013
FL | Charlotte County | 12015
FL | Citrus County | 12017
FL | Clay County | 12019
FL | Collier County | 12021
FL | Columbia County | 12023
FL | DeSoto County | 12027
FL | Dixie County | 12029
FL | Duval County | 12031
FL | Escambia County | 12033
FL | Flagler County | 12035
FL | Franklin County | 12037
FL | Gadsden County | 12039
FL | Gilchrist County | 12041
FL | Glades County | 12043
FL | Gulf County | 12045
FL | Hamilton County | 12047
FL | Hardee County | 12049
FL | Hendry County | 12051
FL | Hernando County | 12053
FL | Highlands County | 12055
FL | Hillsborough County | 12057
FL | Holmes County | 12059
FL | Indian River County | 12061
FL | Jackson County | 12063
FL | Jefferson County | 12065
FL | Lafayette County | 12067
FL | Lake County | 12069
FL | Lee County | 12071
FL | Leon County | 12073
FL | Levy County | 12075
FL | Liberty County | 12077
FL | Madison County | 12079
FL | Manatee County | 12081
FL | Marion County | 12083
FL | Martin County | 12085
FL | Miami-Dade County | 12086
FL | Monroe County | 12087
FL | Nassau County | 12089
FL | Okaloosa County | 12091
FL | Okeechobee County | 12093
FL | Orange County | 12095
FL | Osceola County | 12097
FL | Palm Beach County | 12099
FL | Pasco County | 12101
FL | Pinellas County | 12103
FL | Polk County | 12105
FL | Putnam County | 12107
FL | St. Johns County | 12109
FL | St. Lucie County | 12111
FL | Santa Rosa County | 12113
FL | Sarasota County | 12115
FL | Seminole County | 12117
FL | Sumter County | 12119
FL | Suwannee County | 12121
FL | Taylor County | 12123
FL | Union County | 12125
FL | Volusia County | 12127
FL | Wakulla County | 12129
FL | Walton County | 12131
FL | Washington County | 12133
GA | Appling County | 13001
GA | Atkinson County | 13003
GA | Bacon County | 13005
GA | Baker County | 13007
GA | Baldwin County | 13009
GA | Banks County | 13011
GA | Barrow County | 13013
GA | Bartow County | 13015
GA | Ben Hill County | 13017
GA | Berrien County | 13019
GA | Bibb County | 13021
GA | Bleckley County | 13023
GA | Brantley County | 13025
GA | Brooks County | 13027
GA | Bryan County | 13029
GA | Bulloch County | 13031
GA | Burke County | 13033
GA | Butts County | 13035
GA | Calhoun County | 13037
GA | Camden County | 13039
GA | Candler County | 13043
GA | Carroll County | 13045
GA | Catoosa County | 13047
GA | Charlton County | 13049
GA | Chatham County | 13051
GA | Chattahoochee County | 13053
GA | Chattooga County | 13055
GA | Cherokee County | 13057
GA | Clarke County | 13059
GA | Clay County | 13061
GA | Clayton County | 13063
GA | Clinch County | 13065
GA | Cobb County | 13067
GA | Coffee County | 13069
GA | Colquitt County | 13071
GA | Columbia County | 13073
GA | Cook County | 13075
GA | Coweta County | 13077
GA | Crawford County | 13079
GA | Crisp County | 13081
GA | Dade County | 13083
GA | Dawson County | 13085
GA | Decatur County | 13087
GA | DeKalb County | 13089
GA | Dodge County | 13091
GA | Dooly County | 13093
GA | Dougherty County | 13095
GA | Douglas County | 13097
GA | Early County | 13099
GA | Echols County | 13101
GA | Effingham County | 13103
GA | Elbert County | 13105
GA | Emanuel County | 13107
GA | Evans County | 13109
GA | Fannin County | 13111
GA | Fayette County | 13113
GA | Floyd County | 13115
GA | Forsyth County | 13117
GA | Franklin County | 13119
GA | Fulton County | 13121
GA | Gilmer County | 13123
GA | Glascock County | 13125
GA | Glynn County | 13127
GA | Gordon County | 13129
GA | Grady County | 13131
GA | Greene County | 13133
GA | Gwinnett County | 13135
GA | Habersham County | 13137
GA | Hall County | 13139
GA | Hancock County | 13141
GA | Haralson County | 13143
GA | Harris County | 13145
GA | Hart County | 13147
GA | Heard County | 13149
GA | Henry County | 13151
GA | Houston County | 13153
GA | Irwin County | 13155
GA | Jackson County | 13157
GA | Jasper County | 13159
GA | Jeff Davis County | 13161
GA | Jefferson County | 13163
GA | Jenkins County | 13165
GA | Johnson County | 13167
GA | Jones County | 13169
GA | Lamar County | 13171
GA | Lanier County | 13173
GA | Laurens County | 13175
GA | Lee County | 13177
GA | Liberty County | 13179
GA | Lincoln County | 13181
GA | Long County | 13183
GA | Lowndes County | 13185
GA | Lumpkin County | 13187
GA | McDuffie County | 13189
GA | McIntosh County | 13191
GA | Macon County | 13193
GA | Madison County | 13195
GA | Marion County | 13197
GA | Meriwether County | 13199
GA | Miller County | 13201
GA | Mitchell County | 13205
GA | Monroe County | 13207
GA | Montgomery County | 13209
GA | Morgan County | 13211
GA | Murray County | 13213
GA | Muscogee County | 13215
GA | Newton County | 13217
GA | Oconee County | 13219
GA | Oglethorpe County | 13221
GA | Paulding County | 13223
GA | Peach County | 13225
GA | Pickens County | 13227
GA | Pierce County | 13229
GA | Pike County | 13231
GA | Polk County | 13233
GA | Pulaski County | 13235
GA | Putnam County | 13237
GA | Quitman County | 13239
GA | Rabun County | 13241
GA | Randolph County | 13243
GA | Richmond County | 13245
GA | Rockdale County | 13247
GA | Schley County | 13249
GA | Screven County | 13251
GA | Seminole County | 13253
GA | Spalding County | 13255
GA | Stephens County | 13257
GA | Stewart County | 13259
GA | Sumter County | 13261
GA | Talbot County | 13263
GA | Taliaferro County | 13265
GA | Tattnall County | 13267
GA | Taylor County | 13269
GA | Telfair County | 13271
GA | Terrell County | 13273
GA | Thomas County | 13275
GA | Tift County | 13277
GA | Toombs County | 13279
GA | Towns County | 13281
GA | Treutlen County | 13283
GA | Troup County | 13285
GA | Turner County | 13287
GA | Twiggs County | 13289
GA | Union County | 13291
GA | Upson County | 13293
GA | Walker County | 13295
GA | Walton County | 13297
GA | Ware County | 13299
GA | Warren County | 13301
GA | Washington County | 13303
GA | Wayne County | 13305
GA | Webster County | 13307
GA | Wheeler County | 13309
GA | White County | 13311
GA | Whitfield County | 13313
GA | Wilcox County | 13315
GA | Wilkes County | 13317
GA | Wilkinson County | 13319
GA | Worth County | 13321
HI | Hawaii County | 15001
HI | Honolulu County | 15003
HI | Kalawao County | 15005
HI | Kauai County | 15007
HI | Maui County | 15009
ID | Ada County | 16001
ID | Adams County | 16003
ID | Bannock County | 16005
ID | Bear Lake County | 16007
ID | Benewah County | 16009
ID | Bingham County | 16011
ID | Blaine County | 16013
ID | Boise County | 16015
ID | Bonner County | 16017
ID | Bonneville County | 16019
ID | Boundary County | 16021
ID | Butte County | 16023
ID | Camas County | 16025
ID | Canyon County | 16027
ID | Caribou County | 16029
ID | Cassia County | 16031
ID | Clark County | 16033
ID | Clearwater County | 16035
ID | Custer County | 16037
ID | Elmore County | 16039
ID | Franklin County | 16041
ID | Fremont County | 16043
ID | Gem County | 16045
ID | Gooding County | 16047
ID | Idaho County | 16049
ID | Jefferson County | 16051
ID | Jerome County | 16053
ID | Kootenai County | 16055
ID | Latah County | 16057
ID | Lemhi County | 16059
ID | Lewis County | 16061
ID | Lincoln County | 16063
ID | Madison County | 16065
ID | Minidoka County | 16067
ID | Nez Perce County | 16069
ID | Oneida County | 16071
ID | Owyhee County | 16073
ID | Payette County | 16075
ID | Power County | 16077
ID | Shoshone County | 16079
ID | Teton County | 16081
ID | Twin Falls County | 16083
ID | Valley County | 16085
ID | Washington County | 16087
IL | Adams County | 17001
IL | Alexander County | 17003
IL | Bond County | 17005
IL | Boone County | 17007
IL | Brown County | 17009
IL | Bureau County | 17011
IL | Calhoun County | 17013
IL | Carroll County | 17015
IL | Cass County | 17017
IL | Champaign County | 17019
IL | Christian County | 17021
IL | Clark County | 17023
IL | Clay County | 17025
IL | Clinton County | 17027
IL | Coles County | 17029
IL | Cook County | 17031
IL | Crawford County | 17033
IL | Cumberland County | 17035
IL | DeKalb County | 17037
IL | De Witt County | 17039
IL | Douglas County | 17041
IL | DuPage County | 17043
IL | Edgar County | 17045
IL | Edwards County | 17047
IL | Effingham County | 17049
IL | Fayette County | 17051
IL | Ford County | 17053
IL | Franklin County | 17055
IL | Fulton County | 17057
IL | Gallatin County | 17059
IL | Greene County | 17061
IL | Grundy County | 17063
IL | Hamilton County | 17065
IL | Hancock County | 17067
IL | Hardin County | 17069
IL | Henderson County | 17071
IL | Henry County | 17073
IL | Iroquois County | 17075
IL | Jackson County | 17077
IL | Jasper County | 17079
IL | Jefferson County | 17081
IL | Jersey County | 17083
IL | Jo Daviess County | 17085
IL | Johnson County | 17087
IL | Kane County | 17089
IL | Kankakee County | 17091
IL | Kendall County | 17093
IL | Knox County | 17095
IL | Lake County | 17097
IL | LaSalle County | 17099
IL | Lawrence County | 17101
IL | Lee County | 17103
IL | Livingston County | 17105
IL | Logan County | 17107
IL | McDonough County | 17109
IL | McHenry County | 17111
IL | McLean County | 17113
IL | Macon County | 17115
IL | Macoupin County | 17117
IL | Madison County | 17119
IL | Marion County | 17121
IL | Marshall County | 17123
IL | Mason County | 17125
IL | Massac County | 17127
IL | Menard County | 17129
IL | Mercer County | 17131
IL | Monroe County | 17133
IL | Montgomery County | 17135
IL | Morgan County | 17137
IL | Moultrie County | 17139
IL | Ogle County | 17141
IL | Peoria County | 17143
IL | Perry County | 17145
IL | Piatt County | 17147
IL | Pike County | 17149
IL | Pope County | 17151
IL | Pulaski County | 17153
IL | Putnam County | 17155
IL | Randolph County | 17157
IL | Richland County | 17159
IL | Rock Island County | 17161
IL | St. Clair County | 17163
IL | Saline County | 17165
IL | Sangamon County | 17167
IL | Schuyler County | 17169
IL | Scott County | 17171
IL | Shelby County | 17173
IL | Stark County | 17175
IL | Stephenson County | 17177
IL | Tazewell County | 17179
IL | Union County | 17181
IL | Vermilion County | 17183
IL | Wabash County | 17185
IL | Warren County | 17187
IL | Washington County | 17189
IL | Wayne County | 17191
IL | White County | 17193
IL | Whiteside County | 17195
IL | Will County | 17197
IL | Williamson County | 17199
IL | Winnebago County | 17201
IL | Woodford County | 17203
IN | Adams County | 18001
IN | Allen County | 18003
IN | Bartholomew County | 18005
IN | Benton County | 18007
IN | Blackford County | 18009
IN | Boone County | 18011
IN | Brown County | 18013
IN | Carroll County | 18015
IN | Cass County | 18017
IN | Clark County | 18019
IN | Clay County | 18021
IN | Clinton County | 18023
IN | Crawford County | 18025
IN | Daviess County | 18027
IN | Dearborn County | 18029
IN | Decatur County | 18031
IN | DeKalb County | 18033
IN | Delaware County | 18035
IN | Dubois County | 18037
IN | Elkhart County | 18039
IN | Fayette County | 18041
IN | Floyd County | 18043
IN | Fountain County | 18045
IN | Franklin County | 18047
IN | Fulton County | 18049
IN | Gibson County | 18051
IN | Grant County | 18053
IN | Greene County | 18055
IN | Hamilton County | 18057
IN | Hancock County | 18059
IN | Harrison County | 18061
IN | Hendricks County | 18063
IN | Henry County | 18065
IN | Howard County | 18067
IN | Huntington County | 18069
IN | Jackson County | 18071
IN | Jasper County | 18073
IN | Jay County | 18075
IN | Jefferson County | 18077
IN | Jennings County | 18079
IN | Johnson County | 18081
IN | Knox County | 18083
IN | Kosciusko County | 18085
IN | LaGrange County | 18087
IN | Lake County | 18089
IN | LaPorte County | 18091
IN | Lawrence County | 18093
IN | Madison County | 18095
IN | Marion County | 18097
IN | Marshall County | 18099
IN | Martin County | 18101
IN | Miami County | 18103
IN | Monroe County | 18105
IN | Montgomery County | 18107
IN | Morgan County | 18109
IN | Newton County | 18111
IN | Noble County | 18113
IN | Ohio County | 18115
IN | Orange County | 18117
IN | Owen County | 18119
IN | Parke County | 18121
IN | Perry County | 18123
IN | Pike County | 18125
IN | Porter County | 18127
IN | Posey County | 18129
IN | Pulaski County | 18131
IN | Putnam County | 18133
IN | Randolph County | 18135
IN | Ripley County | 18137
IN | Rush County | 18139
IN | St. Joseph County | 18141
IN | Scott County | 18143
IN | Shelby County | 18145
IN | Spencer County | 18147
IN | Starke County | 18149
IN | Steuben County | 18151
IN | Sullivan County | 18153
IN | Switzerland County | 18155
IN | Tippecanoe County | 18157
IN | Tipton County | 18159
IN | Union County | 18161
IN | Vanderburgh County | 18163
IN | Vermillion County | 18165
IN | Vigo County | 18167
IN | Wabash County | 18169
IN | Warren County | 18171
IN | Warrick County | 18173
IN | Washington County | 18175
IN | Wayne County | 18177
IN | Wells County | 18179
IN | White County | 18181
IN | Whitley County | 18183
IA | Adair County | 19001
IA | Adams County | 19003
IA | Allamakee County | 19005
IA | Appanoose County | 19007
IA | Audubon County | 19009
IA | Benton County | 19011
IA | Black Hawk County | 19013
IA | Boone County | 19015
IA | Bremer County | 19017
IA | Buchanan County | 19019
IA | Buena Vista County | 19021
IA | Butler County | 19023
IA | Calhoun County | 19025
IA | Carroll County | 19027
IA | Cass County | 19029
IA | Cedar County | 19031
IA | Cerro Gordo County | 19033
IA | Cherokee County | 19035
IA | Chickasaw County | 19037
IA | Clarke County | 19039
IA | Clay County | 19041
IA | Clayton County | 19043
IA | Clinton County | 19045
IA | Crawford County | 19047
IA | Dallas County | 19049
IA | Davis County | 19051
IA | Decatur County | 19053
IA | Delaware County | 19055
IA | Des Moines County | 19057
IA | Dickinson County | 19059
IA | Dubuque County | 19061
IA | Emmet County | 19063
IA | Fayette County | 19065
IA | Floyd County | 19067
IA | Franklin County | 19069
IA | Fremont County | 19071
IA | Greene County | 19073
IA | Grundy County | 19075
IA | Guthrie County | 19077
IA | Hamilton County | 19079
IA | Hancock County | 19081
IA | Hardin County | 19083
IA | Harrison County | 19085
IA | Henry County | 19087
IA | Howard County | 19089
IA | Humboldt County | 19091
IA | Ida County | 19093
IA | Iowa County | 19095
IA | Jackson County | 19097
IA | Jasper County | 19099
IA | Jefferson County | 19101
IA | Johnson County | 19103
IA | Jones County | 19105
IA | Keokuk County | 19107
IA | Kossuth County | 19109
IA | Lee County | 19111
IA | Linn County | 19113
IA | Louisa County | 19115
IA | Lucas County | 19117
IA | Lyon County | 19119
IA | Madison County | 19121
IA | Mahaska County | 19123
IA | Marion County | 19125
IA | Marshall County | 19127
IA | Mills County | 19129
IA | Mitchell County | 19131
IA | Monona County | 19133
IA | Monroe County | 19135
IA | Montgomery County | 19137
IA | Muscatine County | 19139
IA | O'Brien County | 19141
IA | Osceola County | 19143
IA | Page County | 19145
IA | Palo Alto County | 19147
IA | Plymouth County | 19149
IA | Pocahontas County | 19151
IA | Polk County | 19153
IA | Pottawattamie County | 19155
IA | Poweshiek County | 19157
IA | Ringgold County | 19159
IA | Sac County | 19161
IA | Scott County | 19163
IA | Shelby County | 19165
IA | Sioux County | 19167
IA | Story County | 19169
IA | Tama County | 19171
IA | Taylor County | 19173
IA | Union County | 19175
IA | Van Buren County | 19177
IA | Wapello County | 19179
IA | Warren County | 19181
IA | Washington County | 19183
IA | Wayne County | 19185
IA | Webster County | 19187
IA | Winnebago County | 19189
IA | Winneshiek County | 19191
IA | Woodbury County | 19193
IA | Worth County | 19195
IA | Wright County | 19197
KS | Allen County | 20001
KS | Anderson County | 20003
KS | Atchison County | 20005
KS | Barber County | 20007
KS | Barton County | 20009
KS | Bourbon County | 20011
KS | Brown County | 20013
KS | Butler County | 20015
KS | Chase County | 20017
KS | Chautauqua County | 20019
KS | Cherokee County | 20021
KS | Cheyenne County | 20023
KS | Clark County | 20025
KS | Clay County | 20027
KS | Cloud County | 20029
KS | Coffey County | 20031
KS | Comanche County | 20033
KS | Cowley County | 20035
KS | Crawford County | 20037
KS | Decatur County | 20039
KS | Dickinson County | 20041
KS | Doniphan County | 20043
KS | Douglas County | 20045
KS | Edwards County | 20047
KS | Elk County | 20049
KS | Ellis County | 20051
KS | Ellsworth County | 20053
KS | Finney County | 20055
KS | Ford County | 20057
KS | Franklin County | 20059
KS | Geary County | 20061
KS | Gove County | 20063
KS | Graham County | 20065
KS | Grant County | 20067
KS | Gray County | 20069
KS | Greeley County | 20071
KS | Greenwood County | 20073
KS | Hamilton County | 20075
KS | Harper County | 20077
KS | Harvey County | 20079
KS | Haskell County | 20081
KS | Hodgeman County | 20083
KS | Jackson County | 20085
KS | Jefferson County | 20087
KS | Jewell County | 20089
KS | Johnson County | 20091
KS | Kearny County | 20093
KS | Kingman County | 20095
KS | Kiowa County | 20097
KS | Labette County | 20099
KS | Lane County | 20101
KS | Leavenworth County | 20103
KS | Lincoln County | 20105
KS | Linn County | 20107
KS | Logan County | 20109
KS | Lyon County | 20111
KS | McPherson County | 20113
KS | Marion County | 20115
KS | Marshall County | 20117
KS | Meade County | 20119
KS | Miami County | 20121
KS | Mitchell County | 20123
KS | Montgomery County | 20125
KS | Morris County | 20127
KS | Morton County | 20129
KS | Nemaha County | 20131
KS | Neosho County | 20133
KS | Ness County | 20135
KS | Norton County | 20137
KS | Osage County | 20139
KS | Osborne County | 20141
KS | Ottawa County | 20143
KS | Pawnee County | 20145
KS | Phillips County | 20147
KS | Pottawatomie County | 20149
KS | Pratt County | 20151
KS | Rawlins County | 20153
KS | Reno County | 20155
KS | Republic County | 20157
KS | Rice County | 20159
KS | Riley County | 20161
KS | Rooks County | 20163
KS | Rush County | 20165
KS | Russell County | 20167
KS | Saline County | 20169
KS | Scott County | 20171
KS | Sedgwick County | 20173
KS | Seward County | 20175
KS | Shawnee County | 20177
KS | Sheridan County | 20179
KS | Sherman County | 20181
KS | Smith County | 20183
KS | Stafford County | 20185
KS | Stanton County | 20187
KS | Stevens County | 20189
KS | Sumner County | 20191
KS | Thomas County | 20193
KS | Trego County | 20195
KS | Wabaunsee County | 20197
KS | Wallace County | 20199
KS | Washington County | 20201
KS | Wichita County | 20203
KS | Wilson County | 20205
KS | Woodson County | 20207
KS | Wyandotte County | 20209
KY | Adair County | 21001
KY | Allen County | 21003
KY | Anderson County | 21005
KY | Ballard County | 21007
KY | Barren County | 21009
KY | Bath County | 21011
KY | Bell County | 21013
KY | Boone County | 21015
KY | Bourbon County | 21017
KY | Boyd County | 21019
KY | Boyle County | 21021
KY | Bracken County | 21023
KY | Breathitt County | 21025
KY | Breckinridge County | 21027
KY | Bullitt County | 21029
KY | Butler County | 21031
KY | Caldwell County | 21033
KY | Calloway County | 21035
KY | Campbell County | 21037
KY | Carlisle County | 21039
KY | Carroll County | 21041
KY | Carter County | 21043
KY | Casey County | 21045
KY | Christian County | 21047
KY | Clark County | 21049
KY | Clay County | 21051
KY | Clinton County | 21053
KY | Crittenden County | 21055
KY | Cumberland County | 21057
KY | Daviess County | 21059
KY | Edmonson County | 21061
KY | Elliott County | 21063
KY | Estill County | 21065
KY | Fayette County | 21067
KY | Fleming County | 21069
KY | Floyd County | 21071
KY | Franklin County | 21073
KY | Fulton County | 21075
KY | Gallatin County | 21077
KY | Garrard County | 21079
KY | Grant County | 21081
KY | Graves County | 21083
KY | Grayson County | 21085
KY | Green County | 21087
KY | Greenup County | 21089
KY | Hancock County | 21091
KY | Hardin County | 21093
KY | Harlan County | 21095
KY | Harrison County | 21097
KY | Hart County | 21099
KY | Henderson County | 21101
KY | Henry County | 21103
KY | Hickman County | 21105
KY | Hopkins County | 21107
KY | Jackson County | 21109
KY | Jefferson County | 21111
KY | Jessamine County | 21113
KY | Johnson County | 21115
KY | Kenton County | 21117
KY | Knott County | 21119
KY | Knox County | 21121
KY | Larue County | 21123
KY | Laurel County | 21125
KY | Lawrence County | 21127
KY | Lee County | 21129
KY | Leslie County | 21131
KY | Letcher County | 21133
KY | Lewis County | 21135
KY | Lincoln County | 21137
KY | Livingston County | 21139
KY | Logan County | 21141
KY | Lyon County | 21143
KY | McCracken County | 21145
KY | McCreary County | 21147
KY | McLean County | 21149
KY | Madison County | 21151
KY | Magoffin County | 21153
KY | Marion County | 21155
KY | Marshall County | 21157
KY | Martin County | 21159
KY | Mason County | 21161
KY | Meade County | 21163
KY | Menifee County | 21165
KY | Mercer County | 21167
KY | Metcalfe County | 21169
KY | Monroe County | 21171
KY | Montgomery County | 21173
KY | Morgan County | 21175
KY | Muhlenberg County | 21177
KY | Nelson County | 21179
KY | Nicholas County | 21181
KY | Ohio County | 21183
KY | Oldham County | 21185
KY | Owen County | 21187
KY | Owsley County | 21189
KY | Pendleton County | 21191
KY | Perry County | 21193
KY | Pike County | 21195
KY | Powell County | 21197
KY | Pulaski County | 21199
KY | Robertson County | 21201
KY | Rockcastle County | 21203
KY | Rowan County | 21205
KY | Russell County | 21207
KY | Scott County | 21209
KY | Shelby County | 21211
KY | Simpson County | 21213
KY | Spencer County | 21215
KY | Taylor County | 21217
KY | Todd County | 21219
KY | Trigg County | 21221
KY | Trimble County | 21223
KY | Union County | 21225
KY | Warren County | 21227
KY | Washington County | 21229
KY | Wayne County | 21231
KY | Webster County | 21233
KY | Whitley County | 21235
KY | Wolfe County | 21237
KY | Woodford County | 21239
LA | Acadia Parish | 22001
LA | Allen Parish | 22003
LA | Ascension Parish | 22005
LA | Assumption Parish | 22007
LA | Avoyelles Parish | 22009
LA | Beauregard Parish | 22011
LA | Bienville Parish | 22013
LA | Bossier Parish | 22015
LA | Caddo Parish | 22017
LA | Calcasieu Parish | 22019
LA | Caldwell Parish | 22021
LA | Cameron Parish | 22023
LA | Catahoula Parish | 22025
LA | Claiborne Parish | 22027
LA | Concordia Parish | 22029
LA | De Soto Parish | 22031
LA | East Baton Rouge Parish | 22033
LA | East Carroll Parish | 22035
LA | East Feliciana Parish | 22037
LA | Evangeline Parish | 22039
LA | Franklin Parish | 22041
LA | Grant Parish | 22043
LA | Iberia Parish | 22045
LA | Iberville Parish | 22047
LA | Jackson Parish | 22049
LA | Jefferson Parish | 22051
LA | Jefferson Davis Parish | 22053
LA | Lafayette Parish | 22055
LA | Lafourche Parish | 22057
LA | LaSalle Parish | 22059
LA | Lincoln Parish | 22061
LA | Livingston Parish | 22063
LA | Madison Parish | 22065
LA | Morehouse Parish | 22067
LA | Natchitoches Parish | 22069
LA | Orleans Parish | 22071
LA | Ouachita Parish | 22073
LA | Plaquemines Parish | 22075
LA | Pointe Coupee Parish | 22077
LA | Rapides Parish | 22079
LA | Red River Parish | 22081
LA | Richland Parish | 22083
LA | Sabine Parish | 22085
LA | St. Bernard Parish | 22087
LA | St. Charles Parish | 22089
LA | St. Helena Parish | 22091
LA | St. James Parish | 22093
LA | St. John the Baptist Parish | 22095
LA | St. Landry Parish | 22097
LA | St. Martin Parish | 22099
LA | St. Mary Parish | 22101
LA | St. Tammany Parish | 22103
LA | Tangipahoa Parish | 22105
LA | Tensas Parish | 22107
LA | Terrebonne Parish | 22109
LA | Union Parish | 22111
LA | Vermilion Parish | 22113
LA | Vernon Parish | 22115
LA | Washington Parish | 22117
LA | Webster Parish | 22119
LA | West Baton Rouge Parish | 22121
LA | West Carroll Parish | 22123
LA | West Feliciana Parish | 22125
LA | Winn Parish | 22127
ME | Androscoggin County | 23001
ME | Aroostook County | 23003
ME | Cumberland County | 23005
ME | Franklin County | 23007
ME | Hancock County | 23009
ME | Kennebec County | 23011
ME | Knox County | 23013
ME | Lincoln County | 23015
ME | Oxford County | 23017
ME | Penobscot County | 23019
ME | Piscataquis County | 23021
ME | Sagadahoc County | 23023
ME | Somerset County | 23025
ME | Waldo County | 23027
ME | Washington County | 23029
ME | York County | 23031
MD | Allegany County | 24001
MD | Anne Arundel County | 24003
MD | Baltimore County | 24005
MD | Calvert County | 24009
MD | Caroline County | 24011
MD | Carroll County | 24013
MD | Cecil County | 24015
MD | Charles County | 24017
MD | Dorchester County | 24019
MD | Frederick County | 24021
MD | Garrett County | 24023
MD | Harford County | 24025
MD | Howard County | 24027
MD | Kent County | 24029
MD | Montgomery County | 24031
MD | Prince George's County | 24033
MD | Queen Anne's County | 24035
MD | St. Mary's County | 24037
MD | Somerset County | 24039
MD | Talbot County | 24041
MD | Washington County | 24043
MD | Wicomico County | 24045
MD | Worcester County | 24047
MD | Baltimore city | 24510
MA | Barnstable County | 25001
MA | Berkshire County | 25003
MA | Bristol County | 25005
MA | Dukes County | 25007
MA | Essex County | 25009
MA | Franklin County | 25011
MA | Hampden County | 25013
MA | Hampshire County | 25015
MA | Middlesex County | 25017
MA | Nantucket County | 25019
MA | Norfolk County | 25021
MA | Plymouth County | 25023
MA | Suffolk County | 25025
MA | Worcester County | 25027
MI | Alcona County | 26001
MI | Alger County | 26003
MI | Allegan County | 26005
MI | Alpena County | 26007
MI | Antrim County | 26009
MI | Arenac County | 26011
MI | Baraga County | 26013
MI | Barry County | 26015
MI | Bay County | 26017
MI | Benzie County | 26019
MI | Berrien County | 26021
MI | Branch County | 26023
MI | Calhoun County | 26025
MI | Cass County | 26027
MI | Charlevoix County | 26029
MI | Cheboygan County | 26031
MI | Chippewa County | 26033
MI | Clare County | 26035
MI | Clinton County | 26037
MI | Crawford County | 26039
MI | Delta County | 26041
MI | Dickinson County | 26043
MI | Eaton County | 26045
MI | Emmet County | 26047
MI | Genesee County | 26049
MI | Gladwin County | 26051
MI | Gogebic County | 26053
MI | Grand Traverse County | 26055
MI | Gratiot County | 26057
MI | Hillsdale County | 26059
MI | Houghton County | 26061
MI | Huron County | 26063
MI | Ingham County | 26065
MI | Ionia County | 26067
MI | Iosco County | 26069
MI | Iron County | 26071
MI | Isabella County | 26073
MI | Jackson County | 26075
MI | Kalamazoo County | 26077
MI | Kalkaska County | 26079
MI | Kent County | 26081
MI | Keweenaw County | 26083
MI | Lake County | 26085
MI | Lapeer County | 26087
MI | Leelanau County | 26089
MI | Lenawee County | 26091
MI | Livingston County | 26093
MI | Luce County | 26095
MI | Mackinac County | 26097
MI | Macomb County | 26099
MI | Manistee County | 26101
MI | Marquette County | 26103
MI | Mason County | 26105
MI | Mecosta County | 26107
MI | Menominee County | 26109
MI | Midland County | 26111
MI | Missaukee County | 26113
MI | Monroe County | 26115
MI | Montcalm County | 26117
MI | Montmorency County | 26119
MI | Muskegon County | 26121
MI | Newaygo County | 26123
MI | Oakland County | 26125
MI | Oceana County | 26127
MI | Ogemaw County | 26129
MI | Ontonagon County | 26131
MI | Osceola County | 26133
MI | Oscoda County | 26135
MI | Otsego County | 26137
MI | Ottawa County | 26139
MI | Presque Isle County | 26141
MI | Roscommon County | 26143
MI | Saginaw County | 26145
MI | St. Clair County | 26147
MI | St. Joseph County | 26149
MI | Sanilac County | 26151
MI | Schoolcraft County | 26153
MI | Shiawassee County | 26155
MI | Tuscola County | 26157
MI | Van Buren County | 26159
MI | Washtenaw County | 26161
MI | Wayne County | 26163
MI | Wexford County | 26165
MN | Aitkin County | 27001
MN | Anoka County | 27003
MN | Becker County | 27005
MN | Beltrami County | 27007
MN | Benton County | 27009
MN | Big Stone County | 27011
MN | Blue Earth County | 27013
MN | Brown County | 27015
MN | Carlton County | 27017
MN | Carver County | 27019
MN | Cass County | 27021
MN | Chippewa County | 27023
MN | Chisago County | 27025
MN | Clay County | 27027
MN | Clearwater County | 27029
MN | Cook County | 27031
MN | Cottonwood County | 27033
MN | Crow Wing County | 27035
MN | Dakota County | 27037
MN | Dodge County | 27039
MN | Douglas County | 27041
MN | Faribault County | 27043
MN | Fillmore County | 27045
MN | Freeborn County | 27047
MN | Goodhue County | 27049
MN | Grant County | 27051
MN | Hennepin County | 27053
MN | Houston County | 27055
MN | Hubbard County | 27057
MN | Isanti County | 27059
MN | Itasca County | 27061
MN | Jackson County | 27063
MN | Kanabec County | 27065
MN | Kandiyohi County | 27067
MN | Kittson County | 27069
MN | Koochiching County | 27071
MN | Lac qui Parle County | 27073
MN | Lake County | 27075
MN | Lake of the Woods County | 27077
MN | Le Sueur County | 27079
MN | Lincoln County | 27081
MN | Lyon County | 27083
MN | McLeod County | 27085
MN | Mahnomen County | 27087
MN | Marshall County | 27089
MN | Martin County | 27091
MN | Meeker County | 27093
MN | Mille Lacs County | 27095
MN | Morrison County | 27097
MN | Mower County | 27099
MN | Murray County | 27101
MN | Nicollet County | 27103
MN | Nobles County | 27105
MN | Norman County | 27107
MN | Olmsted County | 27109
MN | Otter Tail County | 27111
MN | Pennington County | 27113
MN | Pine County | 27115
MN | Pipestone County | 27117
MN | Polk County | 27119
MN | Pope County | 27121
MN | Ramsey County | 27123
MN | Red Lake County | 27125
MN | Redwood County | 27127
MN | Renville County | 27129
MN | Rice County | 27131
MN | Rock County | 27133
MN | Roseau County | 27135
MN | St. Louis County | 27137
MN | Scott County | 27139
MN | Sherburne County | 27141
MN | Sibley County | 27143
MN | Stearns County | 27145
MN | Steele County | 27147
MN | Stevens County | 27149
MN | Swift County | 27151
MN | Todd County | 27153
MN | Traverse County | 27155
MN | Wabasha County | 27157
MN | Wadena County | 27159
MN | Waseca County | 27161
MN | Washington County | 27163
MN | Watonwan County | 27165
MN | Wilkin County | 27167
MN | Winona County | 27169
MN | Wright County | 27171
MN | Yellow Medicine County | 27173
MS | Adams County | 28001
MS | Alcorn County | 28003
MS | Amite County | 28005
MS | Attala County | 28007
MS | Benton County | 28009
MS | Bolivar County | 28011
MS | Calhoun County | 28013
MS | Carroll County | 28015
MS | Chickasaw County | 28017
MS | Choctaw County | 28019
MS | Claiborne County | 28021
MS | Clarke County | 28023
MS | Clay County | 28025
MS | Coahoma County | 28027
MS | Copiah County | 28029
MS | Covington County | 28031
MS | DeSoto County | 28033
MS | Forrest County | 28035
MS | Franklin County | 28037
MS | George County | 28039
MS | Greene County | 28041
MS | Grenada County | 28043
MS | Hancock County | 28045
MS | Harrison County | 28047
MS | Hinds County | 28049
MS | Holmes County | 28051
MS | Humphreys County | 28053
MS | Issaquena County | 28055
MS | Itawamba County | 28057
MS | Jackson County | 28059
MS | Jasper County | 28061
MS | Jefferson County | 28063
MS | Jefferson Davis County | 28065
MS | Jones County | 28067
MS | Kemper County | 28069
MS | Lafayette County | 28071
MS | Lamar County | 28073
MS | Lauderdale County | 28075
MS | Lawrence County | 28077
MS | Leake County | 28079
MS | Lee County | 28081
MS | Leflore County | 28083
MS | Lincoln County | 28085
MS | Lowndes County | 28087
MS | Madison County | 28089
MS | Marion County | 28091
MS | Marshall County | 28093
MS | Monroe County | 28095
MS | Montgomery County | 28097
MS | Neshoba County | 28099
MS | Newton County | 28101
MS | Noxubee County | 28103
MS | Oktibbeha County | 28105
MS | Panola County | 28107
MS | Pearl River County | 28109
MS | Perry County | 28111
MS | Pike County | 28113
MS | Pontotoc County | 28115
MS | Prentiss County | 28117
MS | Quitman County | 28119
MS | Rankin County | 28121
MS | Scott County | 28123
MS | Sharkey County | 28125
MS | Simpson County | 28127
MS | Smith County | 28129
MS | Stone County | 28131
MS | Sunflower County | 28133
MS | Tallahatchie County | 28135
MS | Tate County | 28137
MS | Tippah County | 28139
MS | Tishomingo County | 28141
MS | Tunica County | 28143
MS | Union County | 28145
MS | Walthall County | 28147
MS | Warren County | 28149
MS | Washington County | 28151
MS | Wayne County | 28153
MS | Webster County | 28155
MS | Wilkinson County | 28157
MS | Winston County | 28159
MS | Yalobusha County | 28161
MS | Yazoo County | 28163
MO | Adair County | 29001
MO | Andrew County | 29003
MO | Atchison County | 29005
MO | Audrain County | 29007
MO | Barry County | 29009
MO | Barton County | 29011
MO | Bates County | 29013
MO | Benton County | 29015
MO | Bollinger County | 29017
MO | Boone County | 29019
MO | Buchanan County | 29021
MO | Butler County | 29023
MO | Caldwell County | 29025
MO | Callaway County | 29027
MO | Camden County | 29029
MO | Cape Girardeau County | 29031
MO | Carroll County | 29033
MO | Carter County | 29035
MO | Cass County | 29037
MO | Cedar County | 29039
MO | Chariton County | 29041
MO | Christian County | 29043
MO | Clark County | 29045
MO | Clay County | 29047
MO | Clinton County | 29049
MO | Cole County | 29051
MO | Cooper County | 29053
MO | Crawford County | 29055
MO | Dade County | 29057
MO | Dallas County | 29059
MO | Daviess County | 29061
MO | DeKalb County | 29063
MO | Dent County | 29065
MO | Douglas County | 29067
MO | Dunklin County | 29069
MO | Franklin County | 29071
MO | Gasconade County | 29073
MO | Gentry County | 29075
MO | Greene County | 29077
MO | Grundy County | 29079
MO | Harrison County | 29081
MO | Henry County | 29083
MO | Hickory County | 29085
MO | Holt County | 29087
MO | Howard County | 29089
MO | Howell County | 29091
MO | Iron County | 29093
MO | Jackson County | 29095
MO | Jasper County | 29097
MO | Jefferson County | 29099
MO | Johnson County | 29101
MO | Knox County | 29103
MO | Laclede County | 29105
MO | Lafayette County | 29107
MO | Lawrence County | 29109
MO | Lewis County | 29111
MO | Lincoln County | 29113
MO | Linn County | 29115
MO | Livingston County | 29117
MO | McDonald County | 29119
MO | Macon County | 29121
MO | Madison County | 29123
MO | Maries County | 29125
MO | Marion County | 29127
MO | Mercer County | 29129
MO | Miller County | 29131
MO | Mississippi County | 29133
MO | Moniteau County | 29135
MO | Monroe County | 29137
MO | Montgomery County | 29139
MO | Morgan County | 29141
MO | New Madrid County | 29143
MO | Newton County | 29145
MO | Nodaway County | 29147
MO | Oregon County | 29149
MO | Osage County | 29151
MO | Ozark County | 29153
MO | Pemiscot County | 29155
MO | Perry County | 29157
MO | Pettis County | 29159
MO | Phelps County | 29161
MO | Pike County | 29163
MO | Platte County | 29165
MO | Polk County | 29167
MO | Pulaski County | 29169
MO | Putnam County | 29171
MO | Ralls County | 29173
MO | Randolph County | 29175
MO | Ray County | 29177
MO | Reynolds County | 29179
MO | Ripley County | 29181
MO | St. Charles County | 29183
MO | St. Clair County | 29185
MO | Ste. Genevieve County | 29186
MO | St. Francois County | 29187
MO | St. Louis County | 29189
MO | Saline County | 29195
MO | Schuyler County | 29197
MO | Scotland County | 29199
MO | Scott County | 29201
MO | Shannon County | 29203
MO | Shelby County | 29205
MO | Stoddard County | 29207
MO | Stone County | 29209
MO | Sullivan County | 29211
MO | Taney County | 29213
MO | Texas County | 29215
MO | Vernon County | 29217
MO | Warren County | 29219
MO | Washington County | 29221
MO | Wayne County | 29223
MO | Webster County | 29225
MO | Worth County | 29227
MO | Wright County | 29229
MO | St. Louis city | 29510
MT | Beaverhead County | 30001
MT | Big Horn County | 30003
MT | Blaine County | 30005
MT | Broadwater County | 30007
MT | Carbon County | 30009
MT | Carter County | 30011
MT | Cascade County | 30013
MT | Chouteau County | 30015
MT | Custer County | 30017
MT | Daniels County | 30019
MT | Dawson County | 30021
MT | Deer Lodge County | 30023
MT | Fallon County | 30025
MT | Fergus County | 30027
MT | Flathead County | 30029
MT | Gallatin County | 30031
MT | Garfield County | 30033
MT | Glacier County | 30035
MT | Golden Valley County | 30037
MT | Granite County | 30039
MT | Hill County | 30041
MT | Jefferson County | 30043
MT | Judith Basin County | 30045
MT | Lake County | 30047
MT | Lewis and Clark County | 30049
MT | Liberty County | 30051
MT | Lincoln County | 30053
MT | McCone County | 30055
MT | Madison County | 30057
MT | Meagher County | 30059
MT | Mineral County | 30061
MT | Missoula County | 30063
MT | Musselshell County | 30065
MT | Park County | 30067
MT | Petroleum County | 30069
MT | Phillips County | 30071
MT | Pondera County | 30073
MT | Powder River County | 30075
MT | Powell County | 30077
MT | Prairie County | 30079
MT | Ravalli County | 30081
MT | Richland County | 30083
MT | Roosevelt County | 30085
MT | Rosebud County | 30087
MT | Sanders County | 30089
MT | Sheridan County | 30091
MT | Silver Bow County | 30093
MT | Stillwater County | 30095
MT | Sweet Grass County | 30097
MT | Teton County | 30099
MT | Toole County | 30101
MT | Treasure County | 30103
MT | Valley County | 30105
MT | Wheatland County | 30107
MT | Wibaux County | 30109
MT | Yellowstone County | 30111
NE | Adams County | 31001
NE | Antelope County | 31003
NE | Arthur County | 31005
NE | Banner County | 31007
NE | Blaine County | 31009
NE | Boone County | 31011
NE | Box Butte County | 31013
NE | Boyd County | 31015
NE | Brown County | 31017
NE | Buffalo County | 31019
NE | Burt County | 31021
NE | Butler County | 31023
NE | Cass County | 31025
NE | Cedar County | 31027
NE | Chase County | 31029
NE | Cherry County | 31031
NE | Cheyenne County | 31033
NE | Clay County | 31035
NE | Colfax County | 31037
NE | Cuming County | 31039
NE | Custer County | 31041
NE | Dakota County | 31043
NE | Dawes County | 31045
NE | Dawson County | 31047
NE | Deuel County | 31049
NE | Dixon County | 31051
NE | Dodge County | 31053
NE | Douglas County | 31055
NE | Dundy County | 31057
NE | Fillmore County | 31059
NE | Franklin County | 31061
NE | Frontier County | 31063
NE | Furnas County | 31065
NE | Gage County | 31067
NE | Garden County | 31069
NE | Garfield County | 31071
NE | Gosper County | 31073
NE | Grant County | 31075
NE | Greeley County | 31077
NE | Hall County | 31079
NE | Hamilton County | 31081
NE | Harlan County | 31083
NE | Hayes County | 31085
NE | Hitchcock County | 31087
NE | Holt County | 31089
NE | Hooker County | 31091
NE | Howard County | 31093
NE | Jefferson County | 31095
NE | Johnson County | 31097
NE | Kearney County | 31099
NE | Keith County | 31101
NE | Keya Paha County | 31103
NE | Kimball County | 31105
NE | Knox County | 31107
NE | Lancaster County | 31109
NE | Lincoln County | 31111
NE | Logan County | 31113
NE | Loup County | 31115
NE | McPherson County | 31117
NE | Madison County | 31119
NE | Merrick County | 31121
NE | Morrill County | 31123
NE | Nance County | 31125
NE | Nemaha County | 31127
NE | Nuckolls County | 31129
NE | Otoe County | 31131
NE | Pawnee County | 31133
NE | Perkins County | 31135
NE | Phelps County | 31137
NE | Pierce County | 31139
NE | Platte County | 31141
NE | Polk County | 31143
NE | Red Willow County | 31145
NE | Richardson County | 31147
NE | Rock County | 31149
NE | Saline County | 31151
NE | Sarpy County | 31153
NE | Saunders County | 31155
NE | Scotts Bluff County | 31157
NE | Seward County | 31159
NE | Sheridan County | 31161
NE | Sherman County | 31163
NE | Sioux County | 31165
NE | Stanton County | 31167
NE | Thayer County | 31169
NE | Thomas County | 31171
NE | Thurston County | 31173
NE | Valley County | 31175
NE | Washington County | 31177
NE | Wayne County | 31179
NE | Webster County | 31181
NE | Wheeler County | 31183
NE | York County | 31185
NV | Churchill County | 32001
NV | Clark County | 32003
NV | Douglas County | 32005
NV | Elko County | 32007
NV | Esmeralda County | 32009
NV | Eureka County | 32011
NV | Humboldt County | 32013
NV | Lander County | 32015
NV | Lincoln County | 32017
NV | Lyon County | 32019
NV | Mineral County | 32021
NV | Nye County | 32023
NV | Pershing County | 32027
NV | Storey County | 32029
NV | Washoe County | 32031
NV | White Pine County | 32033
NV | Carson City | 32510
NH | Belknap County | 33001
NH | Carroll County | 33003
NH | Cheshire County | 33005
NH | Coos County | 33007
NH | Grafton County | 33009
NH | Hillsborough County | 33011
NH | Merrimack County | 33013
NH | Rockingham County | 33015
NH | Strafford County | 33017
NH | Sullivan County | 33019
NJ | Atlantic County | 34001
NJ | Bergen County | 34003
NJ | Burlington County | 34005
NJ | Camden County | 34007
NJ | Cape May County | 34009
NJ | Cumberland County | 34011
NJ | Essex County | 34013
NJ | Gloucester County | 34015
NJ | Hudson County | 34017
NJ | Hunterdon County | 34019
NJ | Mercer County | 34021
NJ | Middlesex County | 34023
NJ | Monmouth County | 34025
NJ | Morris County | 34027
NJ | Ocean County | 34029
NJ | Passaic County | 34031
NJ | Salem County | 34033
NJ | Somerset County | 34035
NJ | Sussex County | 34037
NJ | Union County | 34039
NJ | Warren County | 34041
NM | Bernalillo County | 35001
NM | Catron County | 35003
NM | Chaves County | 35005
NM | Cibola County | 35006
NM | Colfax County | 35007
NM | Curry County | 35009
NM | De Baca County | 35011
NM | Doña Ana County | 35013
NM | Eddy County | 35015
NM | Grant County | 35017
NM | Guadalupe County | 35019
NM | Harding County | 35021
NM | Hidalgo County | 35023
NM | Lea County | 35025
NM | Lincoln County | 35027
NM | Los Alamos County | 35028
NM | Luna County | 35029
NM | McKinley County | 35031
NM | Mora County | 35033
NM | Otero County | 35035
NM | Quay County | 35037
NM | Rio Arriba County | 35039
NM | Roosevelt County | 35041
NM | Sandoval County | 35043
NM | San Juan County | 35045
NM | San Miguel County | 35047
NM | Santa Fe County | 35049
NM | Sierra County | 35051
NM | Socorro County | 35053
NM | Taos County | 35055
NM | Torrance County | 35057
NM | Union County | 35059
NM | Valencia County | 35061
NY | Albany County | 36001
NY | Allegany County | 36003
NY | Bronx County | 36005
NY | Broome County | 36007
NY | Cattaraugus County | 36009
NY | Cayuga County | 36011
NY | Chautauqua County | 36013
NY | Chemung County | 36015
NY | Chenango County | 36017
NY | Clinton County | 36019
NY | Columbia County | 36021
NY | Cortland County | 36023
NY | Delaware County | 36025
NY | Dutchess County | 36027
NY | Erie County | 36029
NY | Essex County | 36031
NY | Franklin County | 36033
NY | Fulton County | 36035
NY | Genesee County | 36037
NY | Greene County | 36039
NY | Hamilton County | 36041
NY | Herkimer County | 36043
NY | Jefferson County | 36045
NY | Kings County | 36047
NY | Lewis County | 36049
NY | Livingston County | 36051
NY | Madison County | 36053
NY | Monroe County | 36055
NY | Montgomery County | 36057
NY | Nassau County | 36059
NY | New York County | 36061
NY | Niagara County | 36063
NY | Oneida County | 36065
NY | Onondaga County | 36067
NY | Ontario County | 36069
NY | Orange County | 36071
NY | Orleans County | 36073
NY | Oswego County | 36075
NY | Otsego County | 36077
NY | Putnam County | 36079
NY | Queens County | 36081
NY | Rensselaer County | 36083
NY | Richmond County | 36085
NY | Rockland County | 36087
NY | St. Lawrence County | 36089
NY | Saratoga County | 36091
NY | Schenectady County | 36093
NY | Schoharie County | 36095
NY | Schuyler County | 36097
NY | Seneca County | 36099
NY | Steuben County | 36101
NY | Suffolk County | 36103
NY | Sullivan County | 36105
NY | Tioga County | 36107
NY | Tompkins County | 36109
NY | Ulster County | 36111
NY | Warren County | 36113
NY | Washington County | 36115
NY | Wayne County | 36117
NY | Westchester County | 36119
NY | Wyoming County | 36121
NY | Yates County | 36123
NC | Alamance County | 37001
NC | Alexander County | 37003
NC | Alleghany County | 37005
NC | Anson County | 37007
NC | Ashe County | 37009
NC | Avery County | 37011
NC | Beaufort County | 37013
NC | Bertie County | 37015
NC | Bladen County | 37017
NC | Brunswick County | 37019
NC | Buncombe County | 37021
NC | Burke County | 37023
NC | Cabarrus County | 37025
NC | Caldwell County | 37027
NC | Camden County | 37029
NC | Carteret County | 37031
NC | Caswell County | 37033
NC | Catawba County | 37035
NC | Chatham County | 37037
NC | Cherokee County | 37039
NC | Chowan County | 37041
NC | Clay County | 37043
NC | Cleveland County | 37045
NC | Columbus County | 37047
NC | Craven County | 37049
NC | Cumberland County | 37051
NC | Currituck County | 37053
NC | Dare County | 37055
NC | Davidson County | 37057
NC | Davie County | 37059
NC | Duplin County | 37061
NC | Durham County | 37063
NC | Edgecombe County | 37065
NC | Forsyth County | 37067
NC | Franklin County | 37069
NC | Gaston County | 37071
NC | Gates County | 37073
NC | Graham County | 37075
NC | Granville County | 37077
NC | Greene County | 37079
NC | Guilford County | 37081
NC | Halifax County | 37083
NC | Harnett County | 37085
NC | Haywood County | 37087
NC | Henderson County | 37089
NC | Hertford County | 37091
NC | Hoke County | 37093
NC | Hyde County | 37095
NC | Iredell County | 37097
NC | Jackson County | 37099
NC | Johnston County | 37101
NC | Jones County | 37103
NC | Lee County | 37105
NC | Lenoir County | 37107
NC | Lincoln County | 37109
NC | McDowell County | 37111
NC | Macon County | 37113
NC | Madison County | 37115
NC | Martin County | 37117
NC | Mecklenburg County | 37119
NC | Mitchell County | 37121
NC | Montgomery County | 37123
NC | Moore County | 37125
NC | Nash County | 37127
NC | New Hanover County | 37129
NC | Northampton County | 37131
NC | Onslow County | 37133
NC | Orange County | 37135
NC | Pamlico County | 37137
NC | Pasquotank County | 37139
NC | Pender County | 37141
NC | Perquimans County | 37143
NC | Person County | 37145
NC | Pitt County | 37147
NC | Polk County | 37149
NC | Randolph County | 37151
NC | Richmond County | 37153
NC | Robeson County | 37155
NC | Rockingham County | 37157
NC | Rowan County | 37159
NC | Rutherford County | 37161
NC | Sampson County | 37163
NC | Scotland County | 37165
NC | Stanly County | 37167
NC | Stokes County | 37169
NC | Surry County | 37171
NC | Swain County | 37173
NC | Transylvania County | 37175
NC | Tyrrell County | 37177
NC | Union County | 37179
NC | Vance County | 37181
NC | Wake County | 37183
NC | Warren County | 37185
NC | Washington County | 37187
NC | Watauga County | 37189
NC | Wayne County | 37191
NC | Wilkes County | 37193
NC | Wilson County | 37195
NC | Yadkin County | 37197
NC | Yancey County | 37199
ND | Adams County | 38001
ND | Barnes County | 38003
ND | Benson County | 38005
ND | Billings County | 38007
ND | Bottineau County | 38009
ND | Bowman County | 38011
ND | Burke County | 38013
ND | Burleigh County | 38015
ND | Cass County | 38017
ND | Cavalier County | 38019
ND | Dickey County | 38021
ND | Divide County | 38023
ND | Dunn County | 38025
ND | Eddy County | 38027
ND | Emmons County | 38029
ND | Foster County | 38031
ND | Golden Valley County | 38033
ND | Grand Forks County | 38035
ND | Grant County | 38037
ND | Griggs County | 38039
ND | Hettinger County | 38041
ND | Kidder County | 38043
ND | LaMoure County | 38045
ND | Logan County | 38047
ND | McHenry County | 38049
ND | McIntosh County | 38051
ND | McKenzie County | 38053
ND | McLean County | 38055
ND | Mercer County | 38057
ND | Morton County | 38059
ND | Mountrail County | 38061
ND | Nelson County | 38063
ND | Oliver County | 38065
ND | Pembina County | 38067
ND | Pierce County | 38069
ND | Ramsey County | 38071
ND | Ransom County | 38073
ND | Renville County | 38075
ND | Richland County | 38077
ND | Rolette County | 38079
ND | Sargent County | 38081
ND | Sheridan County | 38083
ND | Sioux County | 38085
ND | Slope County | 38087
ND | Stark County | 38089
ND | Steele County | 38091
ND | Stutsman County | 38093
ND | Towner County | 38095
ND | Traill County | 38097
ND | Walsh County | 38099
ND | Ward County | 38101
ND | Wells County | 38103
ND | Williams County | 38105
OH | Adams County | 39001
OH | Allen County | 39003
OH | Ashland County | 39005
OH | Ashtabula County | 39007
OH | Athens County | 39009
OH | Auglaize County | 39011
OH | Belmont County | 39013
OH | Brown County | 39015
OH | Butler County | 39017
OH | Carroll County | 39019
OH | Champaign County | 39021
OH | Clark County | 39023
OH | Clermont County | 39025
OH | Clinton County | 39027
OH | Columbiana County | 39029
OH | Coshocton County | 39031
OH | Crawford County | 39033
OH | Cuyahoga County | 39035
OH | Darke County | 39037
OH | Defiance County | 39039
OH | Delaware County | 39041
OH | Erie County | 39043
OH | Fairfield County | 39045
OH | Fayette County | 39047
OH | Franklin County | 39049
OH | Fulton County | 39051
OH | Gallia County | 39053
OH | Geauga County | 39055
OH | Greene County | 39057
OH | Guernsey County | 39059
OH | Hamilton County | 39061
OH | Hancock County | 39063
OH | Hardin County | 39065
OH | Harrison County | 39067
OH | Henry County | 39069
OH | Highland County | 39071
OH | Hocking County | 39073
OH | Holmes County | 39075
OH | Huron County | 39077
OH | Jackson County | 39079
OH | Jefferson County | 39081
OH | Knox County | 39083
OH | Lake County | 39085
OH | Lawrence County | 39087
OH | Licking County | 39089
OH | Logan County | 39091
OH | Lorain County | 39093
OH | Lucas County | 39095
OH | Madison County | 39097
OH | Mahoning County | 39099
OH | Marion County | 39101
OH | Medina County | 39103
OH | Meigs County | 39105
OH | Mercer County | 39107
OH | Miami County | 39109
OH | Monroe County | 39111
OH | Montgomery County | 39113
OH | Morgan County | 39115
OH | Morrow County | 39117
OH | Muskingum County | 39119
OH | Noble County | 39121
OH | Ottawa County | 39123
OH | Paulding County | 39125
OH | Perry County | 39127
OH | Pickaway County | 39129
OH | Pike County | 39131
OH | Portage County | 39133
OH | Preble County | 39135
OH | Putnam County | 39137
OH | Richland County | 39139
OH | Ross County | 39141
OH | Sandusky County | 39143
OH | Scioto County | 39145
OH | Seneca County | 39147
OH | Shelby County | 39149
OH | Stark County | 39151
OH | Summit County | 39153
OH | Trumbull County | 39155
OH | Tuscarawas County | 39157
OH | Union County | 39159
OH | Van Wert County | 39161
OH | Vinton County | 39163
OH | Warren County | 39165
OH | Washington County | 39167
OH | Wayne County | 39169
OH | Williams County | 39171
OH | Wood County | 39173
OH | Wyandot County | 39175
OK | Adair County | 40001
OK | Alfalfa County | 40003
OK | Atoka County | 40005
OK | Beaver County | 40007
OK | Beckham County | 40009
OK | Blaine County | 40011
OK | Bryan County | 40013
OK | Caddo County | 40015
OK | Canadian County | 40017
OK | Carter County | 40019
OK | Cherokee County | 40021
OK | Choctaw County | 40023
OK | Cimarron County | 40025
OK | Cleveland County | 40027
OK | Coal County | 40029
OK | Comanche County | 40031
OK | Cotton County | 40033
OK | Craig County | 40035
OK | Creek County | 40037
OK | Custer County | 40039
OK | Delaware County | 40041
OK | Dewey County | 40043
OK | Ellis County | 40045
OK | Garfield County | 40047
OK | Garvin County | 40049
OK | Grady County | 40051
OK | Grant County | 40053
OK | Greer County | 40055
OK | Harmon County | 40057
OK | Harper County | 40059
OK | Haskell County | 40061
OK | Hughes County | 40063
OK | Jackson County | 40065
OK | Jefferson County | 40067
OK | Johnston County | 40069
OK | Kay County | 40071
OK | Kingfisher County | 40073
OK | Kiowa County | 40075
OK | Latimer County | 40077
OK | Le Flore County | 40079
OK | Lincoln County | 40081
OK | Logan County | 40083
OK | Love County | 40085
OK | McClain County | 40087
OK | McCurtain County | 40089
OK | McIntosh County | 40091
OK | Major County | 40093
OK | Marshall County | 40095
OK | Mayes County | 40097
OK | Murray County | 40099
OK | Muskogee County | 40101
OK | Noble County | 40103
OK | Nowata County | 40105
OK | Okfuskee County | 40107
OK | Oklahoma County | 40109
OK | Okmulgee County | 40111
OK | Osage County | 40113
OK | Ottawa County | 40115
OK | Pawnee County | 40117
OK | Payne County | 40119
OK | Pittsburg County | 40121
OK | Pontotoc County | 40123
OK | Pottawatomie County | 40125
OK | Pushmataha County | 40127
OK | Roger Mills County | 40129
OK | Rogers County | 40131
OK | Seminole County | 40133
OK | Sequoyah County | 40135
OK | Stephens County | 40137
OK | Texas County | 40139
OK | Tillman County | 40141
OK | Tulsa County | 40143
OK | Wagoner County | 40145
OK | Washington County | 40147
OK | Washita County | 40149
OK | Woods County | 40151
OK | Woodward County | 40153
OR | Baker County | 41001
OR | Benton County | 41003
OR | Clackamas County | 41005
OR | Clatsop County | 41007
OR | Columbia County | 41009
OR | Coos County | 41011
OR | Crook County | 41013
OR | Curry County | 41015
OR | Deschutes County | 41017
OR | Douglas County | 41019
OR | Gilliam County | 41021
OR | Grant County | 41023
OR | Harney County | 41025
OR | Hood River County | 41027
OR | Jackson County | 41029
OR | Jefferson County | 41031
OR | Josephine County | 41033
OR | Klamath County | 41035
OR | Lake County | 41037
OR | Lane County | 41039
OR | Lincoln County | 41041
OR | Linn County | 41043
OR | Malheur County | 41045
OR | Marion County | 41047
OR | Morrow County | 41049
OR | Multnomah County | 41051
OR | Polk County | 41053
OR | Sherman County | 41055
OR | Tillamook County | 41057
OR | Umatilla County | 41059
OR | Union County | 41061
OR | Wallowa County | 41063
OR | Wasco County | 41065
OR | Washington County | 41067
OR | Wheeler County | 41069
OR | Yamhill County | 41071
PA | Adams County | 42001
PA | Allegheny County | 42003
PA | Armstrong County | 42005
PA | Beaver County | 42007
PA | Bedford County | 42009
PA | Berks County | 42011
PA | Blair County | 42013
PA | Bradford County | 42015
PA | Bucks County | 42017
PA | Butler County | 42019
PA | Cambria County | 42021
PA | Cameron County | 42023
PA | Carbon County | 42025
PA | Centre County | 42027
PA | Chester County | 42029
PA | Clarion County | 42031
PA | Clearfield County | 42033
PA | Clinton County | 42035
PA | Columbia County | 42037
PA | Crawford County | 42039
PA | Cumberland County | 42041
PA | Dauphin County | 42043
PA | Delaware County | 42045
PA | Elk County | 42047
PA | Erie County | 42049
PA | Fayette County | 42051
PA | Forest County | 42053
PA | Franklin County | 42055
PA | Fulton County | 42057
PA | Greene County | 42059
PA | Huntingdon County | 42061
PA | Indiana County | 42063
PA | Jefferson County | 42065
PA | Juniata County | 42067
PA | Lackawanna County | 42069
PA | Lancaster County | 42071
PA | Lawrence County | 42073
PA | Lebanon County | 42075
PA | Lehigh County | 42077
PA | Luzerne County | 42079
PA | Lycoming County | 42081
PA | McKean County | 42083
PA | Mercer County | 42085
PA | Mifflin County | 42087
PA | Monroe County | 42089
PA | Montgomery County | 42091
PA | Montour County | 42093
PA | Northampton County | 42095
PA | Northumberland County | 42097
PA | Perry County | 42099
PA | Philadelphia County | 42101
PA | Pike County | 42103
PA | Potter County | 42105
PA | Schuylkill County | 42107
PA | Snyder County | 42109
PA | Somerset County | 42111
PA | Sullivan County | 42113
PA | Susquehanna County | 42115
PA | Tioga County | 42117
PA | Union County | 42119
PA | Venango County | 42121
PA | Warren County | 42123
PA | Washington County | 42125
PA | Wayne County | 42127
PA | Westmoreland County | 42129
PA | Wyoming County | 42131
PA | York County | 42133
RI | Bristol County | 44001
RI | Kent County | 44003
RI | Newport County | 44005
RI | Providence County | 44007
RI | Washington County | 44009
SC | Abbeville County | 45001
SC | Aiken County | 45003
SC | Allendale County | 45005
SC | Anderson County | 45007
SC | Bamberg County | 45009
SC | Barnwell County | 45011
SC | Beaufort County | 45013
SC | Berkeley County | 45015
SC | Calhoun County | 45017
SC | Charleston County | 45019
SC | Cherokee County | 45021
SC | Chester County | 45023
SC | Chesterfield County | 45025
SC | Clarendon County | 45027
SC | Colleton County | 45029
SC | Darlington County | 45031
SC | Dillon County | 45033
SC | Dorchester County | 45035
SC | Edgefield County | 45037
SC | Fairfield County | 45039
SC | Florence County | 45041
SC | Georgetown County | 45043
SC | Greenville County | 45045
SC | Greenwood County | 45047
SC | Hampton County | 45049
SC | Horry County | 45051
SC | Jasper County | 45053
SC | Kershaw County | 45055
SC | Lancaster County | 45057
SC | Laurens County | 45059
SC | Lee County | 45061
SC | Lexington County | 45063
SC | McCormick County | 45065
SC | Marion County | 45067
SC | Marlboro County | 45069
SC | Newberry County | 45071
SC | Oconee County | 45073
SC | Orangeburg County | 45075
SC | Pickens County | 45077
SC | Richland County | 45079
SC | Saluda County | 45081
SC | Spartanburg County | 45083
SC | Sumter County | 45085
SC | Union County | 45087
SC | Williamsburg County | 45089
SC | York County | 45091
SD | Aurora County | 46003
SD | Beadle County | 46005
SD | Bennett County | 46007
SD | Bon Homme County | 46009
SD | Brookings County | 46011
SD | Brown County | 46013
SD | Brule County | 46015
SD | Buffalo County | 46017
SD | Butte County | 46019
SD | Campbell County | 46021
SD | Charles Mix County | 46023
SD | Clark County | 46025
SD | Clay County | 46027
SD | Codington County | 46029
SD | Corson County | 46031
SD | Custer County | 46033
SD | Davison County | 46035
SD | Day County | 46037
SD | Deuel County | 46039
SD | Dewey County | 46041
SD | Douglas County | 46043
SD | Edmunds County | 46045
SD | Fall River County | 46047
SD | Faulk County | 46049
SD | Grant County | 46051
SD | Gregory County | 46053
SD | Haakon County | 46055
SD | Hamlin County | 46057
SD | Hand County | 46059
SD | Hanson County | 46061
SD | Harding County | 46063
SD | Hughes County | 46065
SD | Hutchinson County | 46067
SD | Hyde County | 46069
SD | Jackson County | 46071
SD | Jerauld County | 46073
SD | Jones County | 46075
SD | Kingsbury County | 46077
SD | Lake County | 46079
SD | Lawrence County | 46081
SD | Lincoln County | 46083
SD | Lyman County | 46085
SD | McCook County | 46087
SD | McPherson County | 46089
SD | Marshall County | 46091
SD | Meade County | 46093
SD | Mellette County | 46095
SD | Miner County | 46097
SD | Minnehaha County | 46099
SD | Moody County | 46101
SD | Oglala Lakota County | 46102
SD | Pennington County | 46103
SD | Perkins County | 46105
SD | Potter County | 46107
SD | Roberts County | 46109
SD | Sanborn County | 46111
SD | Spink County | 46115
SD | Stanley County | 46117
SD | Sully County | 46119
SD | Todd County | 46121
SD | Tripp County | 46123
SD | Turner County | 46125
SD | Union County | 46127
SD | Walworth County | 46129
SD | Yankton County | 46135
SD | Ziebach County | 46137
TN | Anderson County | 47001
TN | Bedford County | 47003
TN | Benton County | 47005
TN | Bledsoe County | 47007
TN | Blount County | 47009
TN | Bradley County | 47011
TN | Campbell County | 47013
TN | Cannon County | 47015
TN | Carroll County | 47017
TN | Carter County | 47019
TN | Cheatham County | 47021
TN | Chester County | 47023
TN | Claiborne County | 47025
TN | Clay County | 47027
TN | Cocke County | 47029
TN | Coffee County | 47031
TN | Crockett County | 47033
TN | Cumberland County | 47035
TN | Davidson County | 47037
TN | Decatur County | 47039
TN | DeKalb County | 47041
TN | Dickson County | 47043
TN | Dyer County | 47045
TN | Fayette County | 47047
TN | Fentress County | 47049
TN | Franklin County | 47051
TN | Gibson County | 47053
TN | Giles County | 47055
TN | Grainger County | 47057
TN | Greene County | 47059
TN | Grundy County | 47061
TN | Hamblen County | 47063
TN | Hamilton County | 47065
TN | Hancock County | 47067
TN | Hardeman County | 47069
TN | Hardin County | 47071
TN | Hawkins County | 47073
TN | Haywood County | 47075
TN | Henderson County | 47077
TN | Henry County | 47079
TN | Hickman County | 47081
TN | Houston County | 47083
TN | Humphreys County | 47085
TN | Jackson County | 47087
TN | Jefferson County | 47089
TN | Johnson County | 47091
TN | Knox County | 47093
TN | Lake County | 47095
TN | Lauderdale County | 47097
TN | Lawrence County | 47099
TN | Lewis County | 47101
TN | Lincoln County | 47103
TN | Loudon County | 47105
TN | McMinn County | 47107
TN | McNairy County | 47109
TN | Macon County | 47111
TN | Madison County | 47113
TN | Marion County | 47115
TN | Marshall County | 47117
TN | Maury County | 47119
TN | Meigs County | 47121
TN | Monroe County | 47123
TN | Montgomery County | 47125
TN | Moore County | 47127
TN | Morgan County | 47129
TN | Obion County | 47131
TN | Overton County | 47133
TN | Perry County | 47135
TN | Pickett County | 47137
TN | Polk County | 47139
TN | Putnam County | 47141
TN | Rhea County | 47143
TN | Roane County | 47145
TN | Robertson County | 47147
TN | Rutherford County | 47149
TN | Scott County | 47151
TN | Sequatchie County | 47153
TN | Sevier County | 47155
TN | Shelby County | 47157
TN | Smith County | 47159
TN | Stewart County | 47161
TN | Sullivan County | 47163
TN | Sumner County | 47165
TN | Tipton County | 47167
TN | Trousdale County | 47169
TN | Unicoi County | 47171
TN | Union County | 47173
TN | Van Buren County | 47175
TN | Warren County | 47177
TN | Washington County | 47179
TN | Wayne County | 47181
TN | Weakley County | 47183
TN | White County | 47185
TN | Williamson County | 47187
TN | Wilson County | 47189
TX | Anderson County | 48001
TX | Andrews County | 48003
TX | Angelina County | 48005
TX | Aransas County | 48007
TX | Archer County | 48009
TX | Armstrong County | 48011
TX | Atascosa County | 48013
TX | Austin County | 48015
TX | Bailey County | 48017
TX | Bandera County | 48019
TX | Bastrop County | 48021
TX | Baylor County | 48023
TX | Bee County | 48025
TX | Bell County | 48027
TX | Bexar County | 48029
TX | Blanco County | 48031
TX | Borden County | 48033
TX | Bosque County | 48035
TX | Bowie County | 48037
TX | Brazoria County | 48039
TX | Brazos County | 48041
TX | Brewster County | 48043
TX | Briscoe County | 48045
TX | Brooks County | 48047
TX | Brown County | 48049
TX | Burleson County | 48051
TX | Burnet County | 48053
TX | Caldwell County | 48055
TX | Calhoun County | 48057
TX | Callahan County | 48059
TX | Cameron County | 48061
TX | Camp County | 48063
TX | Carson County | 48065
TX | Cass County | 48067
TX | Castro County | 48069
TX | Chambers County | 48071
TX | Cherokee County | 48073
TX | Childress County | 48075
TX | Clay County | 48077
TX | Cochran County | 48079
TX | Coke County | 48081
TX | Coleman County | 48083
TX | Collin County | 48085
TX | Collingsworth County | 48087
TX | Colorado County | 48089
TX | Comal County | 48091
TX | Comanche County | 48093
TX | Concho County | 48095
TX | Cooke County | 48097
TX | Coryell County | 48099
TX | Cottle County | 48101
TX | Crane County | 48103
TX | Crockett County | 48105
TX | Crosby County | 48107
TX | Culberson County | 48109
TX | Dallam County | 48111
TX | Dallas County | 48113
TX | Dawson County | 48115
TX | Deaf Smith County | 48117
TX | Delta County | 48119
TX | Denton County | 48121
TX | DeWitt County | 48123
TX | Dickens County | 48125
TX | Dimmit County | 48127
TX | Donley County | 48129
TX | Duval County | 48131
TX | Eastland County | 48133
TX | Ector County | 48135
TX | Edwards County | 48137
TX | Ellis County | 48139
TX | El Paso County | 48141
TX | Erath County | 48143
TX | Falls County | 48145
TX | Fannin County | 48147
TX | Fayette County | 48149
TX | Fisher County | 48151
TX | Floyd County | 48153
TX | Foard County | 48155
TX | Fort Bend County | 48157
TX | Franklin County | 48159
TX | Freestone County | 48161
TX | Frio County | 48163
TX | Gaines County | 48165
TX | Galveston County | 48167
TX | Garza County | 48169
TX | Gillespie County | 48171
TX | Glasscock County | 48173
TX | Goliad County | 48175
TX | Gonzales County | 48177
TX | Gray County | 48179
TX | Grayson County | 48181
TX | Gregg County | 48183
TX | Grimes County | 48185
TX | Guadalupe County | 48187
TX | Hale County | 48189
TX | Hall County | 48191
TX | Hamilton County | 48193
TX | Hansford County | 48195
TX | Hardeman County | 48197
TX | Hardin County | 48199
TX | Harris County | 48201
TX | Harrison County | 48203
TX | Hartley County | 48205
TX | Haskell County | 48207
TX | Hays County | 48209
TX | Hemphill County | 48211
TX | Henderson County | 48213
TX | Hidalgo County | 48215
TX | Hill County | 48217
TX | Hockley County | 48219
TX | Hood County | 48221
TX | Hopkins County | 48223
TX | Houston County | 48225
TX | Howard County | 48227
TX | Hudspeth County | 48229
TX | Hunt County | 48231
TX | Hutchinson County | 48233
TX | Irion County | 48235
TX | Jack County | 48237
TX | Jackson County | 48239
TX | Jasper County | 48241
TX | Jeff Davis County | 48243
TX | Jefferson County | 48245
TX | Jim Hogg County | 48247
TX | Jim Wells County | 48249
TX | Johnson County | 48251
TX | Jones County | 48253
TX | Karnes County | 48255
TX | Kaufman County | 48257
TX | Kendall County | 48259
TX | Kenedy County | 48261
TX | Kent County | 48263
TX | Kerr County | 48265
TX | Kimble County | 48267
TX | King County | 48269
TX | Kinney County | 48271
TX | Kleberg County | 48273
TX | Knox County | 48275
TX | Lamar County | 48277
TX | Lamb County | 48279
TX | Lampasas County | 48281
TX | La Salle County | 48283
TX | Lavaca County | 48285
TX | Lee County | 48287
TX | Leon County | 48289
TX | Liberty County | 48291
TX | Limestone County | 48293
TX | Lipscomb County | 48295
TX | Live Oak County | 48297
TX | Llano County | 48299
TX | Loving County | 48301
TX | Lubbock County | 48303
TX | Lynn County | 48305
TX | McCulloch County | 48307
TX | McLennan County | 48309
TX | McMullen County | 48311
TX | Madison County | 48313
TX | Marion County | 48315
TX | Martin County | 48317
TX | Mason County | 48319
TX | Matagorda County | 48321
TX | Maverick County | 48323
TX | Medina County | 48325
TX | Menard County | 48327
TX | Midland County | 48329
TX | Milam County | 48331
TX | Mills County | 48333
TX | Mitchell County | 48335
TX | Montague County | 48337
TX | Montgomery County | 48339
TX | Moore County | 48341
TX | Morris County | 48343
TX | Motley County | 48345
TX | Nacogdoches County | 48347
TX | Navarro County | 48349
TX | Newton County | 48351
TX | Nolan County | 48353
TX | Nueces County | 48355
TX | Ochiltree County | 48357
TX | Oldham County | 48359
TX | Orange County | 48361
TX | Palo Pinto County | 48363
TX | Panola County | 48365
TX | Parker County | 48367
TX | Parmer County | 48369
TX | Pecos County | 48371
TX | Polk County | 48373
TX | Potter County | 48375
TX | Presidio County | 48377
TX | Rains County | 48379
TX | Randall County | 48381
TX | Reagan County | 48383
TX | Real County | 48385
TX | Red River County | 48387
TX | Reeves County | 48389
TX | Refugio County | 48391
TX | Roberts County | 48393
TX | Robertson County | 48395
TX | Rockwall County | 48397
TX | Runnels County | 48399
TX | Rusk County | 48401
TX | Sabine County | 48403
TX | San Augustine County | 48405
TX | San Jacinto County | 48407
TX | San Patricio County | 48409
TX | San Saba County | 48411
TX | Schleicher County | 48413
TX | Scurry County | 48415
TX | Shackelford County | 48417
TX | Shelby County | 48419
TX | Sherman County | 48421
TX | Smith County | 48423
TX | Somervell County | 48425
TX | Starr County | 48427
TX | Stephens County | 48429
TX | Sterling County | 48431
TX | Stonewall County | 48433
TX | Sutton County | 48435
TX | Swisher County | 48437
TX | Tarrant County | 48439
TX | Taylor County | 48441
TX | Terrell County | 48443
TX | Terry County | 48445
TX | Throckmorton County | 48447
TX | Titus County | 48449
TX | Tom Green County | 48451
TX | Travis County | 48453
TX | Trinity County | 48455
TX | Tyler County | 48457
TX | Upshur County | 48459
TX | Upton County | 48461
TX | Uvalde County | 48463
TX | Val Verde County | 48465
TX | Van Zandt County | 48467
TX | Victoria County | 48469
TX | Walker County | 48471
TX | Waller County | 48473
TX | Ward County | 48475
TX | Washington County | 48477
TX | Webb County | 48479
TX | Wharton County | 48481
TX | Wheeler County | 48483
TX | Wichita County | 48485
TX | Wilbarger County | 48487
TX | Willacy County | 48489
TX | Williamson County | 48491
TX | Wilson County | 48493
TX | Winkler County | 48495
TX | Wise County | 48497
TX | Wood County | 48499
TX | Yoakum County | 48501
TX | Young County | 48503
TX | Zapata County | 48505
TX | Zavala County | 48507
UT | Beaver County | 49001
UT | Box Elder County | 49003
UT | Cache County | 49005
UT | Carbon County | 49007
UT | Daggett County | 49009
UT | Davis County | 49011
UT | Duchesne County | 49013
UT | Emery County | 49015
UT | Garfield County | 49017
UT | Grand County | 49019
UT | Iron County | 49021
UT | Juab County | 49023
UT | Kane County | 49025
UT | Millard County | 49027
UT | Morgan County | 49029
UT | Piute County | 49031
UT | Rich County | 49033
UT | Salt Lake County | 49035
UT | San Juan County | 49037
UT | Sanpete County | 49039
UT | Sevier County | 49041
UT | Summit County | 49043
UT | Tooele County | 49045
UT | Uintah County | 49047
UT | Utah County | 49049
UT | Wasatch County | 49051
UT | Washington County | 49053
UT | Wayne County | 49055
UT | Weber County | 49057
VT | Addison County | 50001
VT | Bennington County | 50003
VT | Caledonia County | 50005
VT | Chittenden County | 50007
VT | Essex County | 50009
VT | Franklin County | 50011
VT | Grand Isle County | 50013
VT | Lamoille County | 50015
VT | Orange County | 50017
VT | Orleans County | 50019
VT | Rutland County | 50021
VT | Washington County | 50023
VT | Windham County | 50025
VT | Windsor County | 50027
VA | Accomack County | 51001
VA | Albemarle County | 51003
VA | Alleghany County | 51005
VA | Amelia County | 51007
VA | Amherst County | 51009
VA | Appomattox County | 51011
VA | Arlington County | 51013
VA | Augusta County | 51015
VA | Bath County | 51017
VA | Bedford County | 51019
VA | Bland County | 51021
VA | Botetourt County | 51023
VA | Brunswick County | 51025
VA | Buchanan County | 51027
VA | Buckingham County | 51029
VA | Campbell County | 51031
VA | Caroline County | 51033
VA | Carroll County | 51035
VA | Charles City County | 51036
VA | Charlotte County | 51037
VA | Chesterfield County | 51041
VA | Clarke County | 51043
VA | Craig County | 51045
VA | Culpeper County | 51047
VA | Cumberland County | 51049
VA | Dickenson County | 51051
VA | Dinwiddie County | 51053
VA | Essex County | 51057
VA | Fairfax County | 51059
VA | Fauquier County | 51061
VA | Floyd County | 51063
VA | Fluvanna County | 51065
VA | Franklin County | 51067
VA | Frederick County | 51069
VA | Giles County | 51071
VA | Gloucester County | 51073
VA | Goochland County | 51075
VA | Grayson County | 51077
VA | Greene County | 51079
VA | Greensville County | 51081
VA | Halifax County | 51083
VA | Hanover County | 51085
VA | Henrico County | 51087
VA | Henry County | 51089
VA | Highland County | 51091
VA | Isle of Wight County | 51093
VA | James City County | 51095
VA | King and Queen County | 51097
VA | King George County | 51099
VA | King William County | 51101
VA | Lancaster County | 51103
VA | Lee County | 51105
VA | Loudoun County | 51107
VA | Louisa County | 51109
VA | Lunenburg County | 51111
VA | Madison County | 51113
VA | Mathews County | 51115
VA | Mecklenburg County | 51117
VA | Middlesex County | 51119
VA | Montgomery County | 51121
VA | Nelson County | 51125
VA | New Kent County | 51127
VA | Northampton County | 51131
VA | Northumberland County | 51133
VA | Nottoway County | 51135
VA | Orange County | 51137
VA | Page County | 51139
VA | Patrick County | 51141
VA | Pittsylvania County | 51143
VA | Powhatan County | 51145
VA | Prince Edward County | 51147
VA | Prince George County | 51149
VA | Prince William County | 51153
VA | Pulaski County | 51155
VA | Rappahannock County | 51157
VA | Richmond County | 51159
VA | Roanoke County | 51161
VA | Rockbridge County | 51163
VA | Rockingham County | 51165
VA | Russell County | 51167
VA | Scott County | 51169
VA | Shenandoah County | 51171
VA | Smyth County | 51173
VA | Southampton County | 51175
VA | Spotsylvania County | 51177
VA | Stafford County | 51179
VA | Surry County | 51181
VA | Sussex County | 51183
VA | Tazewell County | 51185
VA | Warren County | 51187
VA | Washington County | 51191
VA | Westmoreland County | 51193
VA | Wise County | 51195
VA | Wythe County | 51197
VA | York County | 51199
VA | Alexandria city | 51510
VA | Bristol city | 51520
VA | Buena Vista city | 51530
VA | Charlottesville city | 51540
VA | Chesapeake city | 51550
VA | Colonial Heights city | 51570
VA | Covington city | 51580
VA | Danville city | 51590
VA | Emporia city | 51595
VA | Fairfax city | 51600
VA | Falls Church city | 51610
VA | Franklin city | 51620
VA | Fredericksburg city | 51630
VA | Galax city | 51640
VA | Hampton city | 51650
VA | Harrisonburg city | 51660
VA | Hopewell city | 51670
VA | Lexington city | 51678
VA | Lynchburg city | 51680
VA | Manassas city | 51683
VA | Manassas Park city | 51685
VA | Martinsville city | 51690
VA | Newport News city | 51700
VA | Norfolk city | 51710
VA | Norton city | 51720
VA | Petersburg city | 51730
VA | Poquoson city | 51735
VA | Portsmouth city | 51740
VA | Radford city | 51750
VA | Richmond city | 51760
VA | Roanoke city | 51770
VA | Salem city | 51775
VA | Staunton city | 51790
VA | Suffolk city | 51800
VA | Virginia Beach city | 51810
VA | Waynesboro city | 51820
VA | Williamsburg city | 51830
VA | Winchester city | 51840
WA | Adams County | 53001
WA | Asotin County | 53003
WA | Benton County | 53005
WA | Chelan County | 53007
WA | Clallam County | 53009
WA | Clark County | 53011
WA | Columbia County | 53013
WA | Cowlitz County | 53015
WA | Douglas County | 53017
WA | Ferry County | 53019
WA | Franklin County | 53021
WA | Garfield County | 53023
WA | Grant County | 53025
WA | Grays Harbor County | 53027
WA | Island County | 53029
WA | Jefferson County | 53031
WA | King County | 53033
WA | Kitsap County | 53035
WA | Kittitas County | 53037
WA | Klickitat County | 53039
WA | Lewis County | 53041
WA | Lincoln County | 53043
WA | Mason County | 53045
WA | Okanogan County | 53047
WA | Pacific County | 53049
WA | Pend Oreille County | 53051
WA | Pierce County | 53053
WA | San Juan County | 53055
WA | Skagit County | 53057
WA | Skamania County | 53059
WA | Snohomish County | 53061
WA | Spokane County | 53063
WA | Stevens County | 53065
WA | Thurston County | 53067
WA | Wahkiakum County | 53069
WA | Walla Walla County | 53071
WA | Whatcom County | 53073
WA | Whitman County | 53075
WA | Yakima County | 53077
WV | Barbour County | 54001
WV | Berkeley County | 54003
WV | Boone County | 54005
WV | Braxton County | 54007
WV | Brooke County | 54009
WV | Cabell County | 54011
WV | Calhoun County | 54013
WV | Clay County | 54015
WV | Doddridge County | 54017
WV | Fayette County | 54019
WV | Gilmer County | 54021
WV | Grant County | 54023
WV | Greenbrier County | 54025
WV | Hampshire County | 54027
WV | Hancock County | 54029
WV | Hardy County | 54031
WV | Harrison County | 54033
WV | Jackson County | 54035
WV | Jefferson County | 54037
WV | Kanawha County | 54039
WV | Lewis County | 54041
WV | Lincoln County | 54043
WV | Logan County | 54045
WV | McDowell County | 54047
WV | Marion County | 54049
WV | Marshall County | 54051
WV | Mason County | 54053
WV | Mercer County | 54055
WV | Mineral County | 54057
WV | Mingo County | 54059
WV | Monongalia County | 54061
WV | Monroe County | 54063
WV | Morgan County | 54065
WV | Nicholas County | 54067
WV | Ohio County | 54069
WV | Pendleton County | 54071
WV | Pleasants County | 54073
WV | Pocahontas County | 54075
WV | Preston County | 54077
WV | Putnam County | 54079
WV | Raleigh County | 54081
WV | Randolph County | 54083
WV | Ritchie County | 54085
WV | Roane County | 54087
WV | Summers County | 54089
WV | Taylor County | 54091
WV | Tucker County | 54093
WV | Tyler County | 54095
WV | Upshur County | 54097
WV | Wayne County | 54099
WV | Webster County | 54101
WV | Wetzel County | 54103
WV | Wirt County | 54105
WV | Wood County | 54107
WV | Wyoming County | 54109
WI | Adams County | 55001
WI | Ashland County | 55003
WI | Barron County | 55005
WI | Bayfield County | 55007
WI | Brown County | 55009
WI | Buffalo County | 55011
WI | Burnett County | 55013
WI | Calumet County | 55015
WI | Chippewa County | 55017
WI | Clark County | 55019
WI | Columbia County | 55021
WI | Crawford County | 55023
WI | Dane County | 55025
WI | Dodge County | 55027
WI | Door County | 55029
WI | Douglas County | 55031
WI | Dunn County | 55033
WI | Eau Claire County | 55035
WI | Florence County | 55037
WI | Fond du Lac County | 55039
WI | Forest County | 55041
WI | Grant County | 55043
WI | Green County | 55045
WI | Green Lake County | 55047
WI | Iowa County | 55049
WI | Iron County | 55051
WI | Jackson County | 55053
WI | Jefferson County | 55055
WI | Juneau County | 55057
WI | Kenosha County | 55059
WI | Kewaunee County | 55061
WI | La Crosse County | 55063
WI | Lafayette County | 55065
WI | Langlade County | 55067
WI | Lincoln County | 55069
WI | Manitowoc County | 55071
WI | Marathon County | 55073
WI | Marinette County | 55075
WI | Marquette County | 55077
WI | Menominee County | 55078
WI | Milwaukee County | 55079
WI | Monroe County | 55081
WI | Oconto County | 55083
WI | Oneida County | 55085
WI | Outagamie County | 55087
WI | Ozaukee County | 55089
WI | Pepin County | 55091
WI | Pierce County | 55093
WI | Polk County | 55095
WI | Portage County | 55097
WI | Price County | 55099
WI | Racine County | 55101
WI | Richland County | 55103
WI | Rock County | 55105
WI | Rusk County | 55107
WI | St. Croix County | 55109
WI | Sauk County | 55111
WI | Sawyer County | 55113
WI | Shawano County | 55115
WI | Sheboygan County | 55117
WI | Taylor County | 55119
WI | Trempealeau County | 55121
WI | Vernon County | 55123
WI | Vilas County | 55125
WI | Walworth County | 55127
WI | Washburn County | 55129
WI | Washington County | 55131
WI | Waukesha County | 55133
WI | Waupaca County | 55135
WI | Waushara County | 55137
WI | Winnebago County | 55139
WI | Wood County | 55141
WY | Albany County | 56001
WY | Big Horn County | 56003
WY | Campbell County | 56005
WY | Carbon County | 56007
WY | Converse County | 56009
WY | Crook County | 56011
WY | Fremont County | 56013
WY | Goshen County | 56015
WY | Hot Springs County | 56017
WY | Johnson County | 56019
WY | Laramie County | 56021
WY | Lincoln County | 56023
WY | Natrona County | 56025
WY | Niobrara County | 56027
WY | Park County | 56029
WY | Platte County | 56031
WY | Sheridan County | 56033
WY | Sublette County | 56035
WY | Sweetwater County | 56037
WY | Teton County | 56039
WY | Uinta County | 56041
WY | Washakie County | 56043
WY | Weston County | 56045
PR | Adjuntas Municipio | 72001
PR | Aguada Municipio | 72003
PR | Aguadilla Municipio | 72005
PR | Aguas Buenas Municipio | 72007
PR | Aibonito Municipio | 72009
PR | Añasco Municipio | 72011
PR | Arecibo Municipio | 72013
PR | Arroyo Municipio | 72015
PR | Barceloneta Municipio | 72017
PR | Barranquitas Municipio | 72019
PR | Bayamón Municipio | 72021
PR | Cabo Rojo Municipio | 72023
PR | Caguas Municipio | 72025
PR | Camuy Municipio | 72027
PR | Canóvanas Municipio | 72029
PR | Carolina Municipio | 72031
PR | Cataño Municipio | 72033
PR | Cayey Municipio | 72035
PR | Ceiba Municipio | 72037
PR | Ciales Municipio | 72039
PR | Cidra Municipio | 72041
PR | Coamo Municipio | 72043
PR | Comerío Municipio | 72045
PR | Corozal Municipio | 72047
PR | Culebra Municipio | 72049
PR | Dorado Municipio | 72051
PR | Fajardo Municipio | 72053
PR | Florida Municipio | 72054
PR | Guánica Municipio | 72055
PR | Guayama Municipio | 72057
PR | Guayanilla Municipio | 72059
PR | Guaynabo Municipio | 72061
PR | Gurabo Municipio | 72063
PR | Hatillo Municipio | 72065
PR | Hormigueros Municipio | 72067
PR | Humacao Municipio | 72069
PR | Isabela Municipio | 72071
PR | Jayuya Municipio | 72073
PR | Juana Díaz Municipio | 72075
PR | Juncos Municipio | 72077
PR | Lajas Municipio | 72079
PR | Lares Municipio | 72081
PR | Las Marías Municipio | 72083
PR | Las Piedras Municipio | 72085
PR | Loíza Municipio | 72087
PR | Luquillo Municipio | 72089
PR | Manatí Municipio | 72091
PR | Maricao Municipio | 72093
PR | Maunabo Municipio | 72095
PR | Mayagüez Municipio | 72097
PR | Moca Municipio | 72099
PR | Morovis Municipio | 72101
PR | Naguabo Municipio | 72103
PR | Naranjito Municipio | 72105
PR | Orocovis Municipio | 72107
PR | Patillas Municipio | 72109
PR | Peñuelas Municipio | 72111
PR | Ponce Municipio | 72113
PR | Quebradillas Municipio | 72115
PR | Rincón Municipio | 72117
PR | Río Grande Municipio | 72119
PR | Sabana Grande Municipio | 72121
PR | Salinas Municipio | 72123
PR | San Germán Municipio | 72125
PR | San Juan Municipio | 72127
PR | San Lorenzo Municipio | 72129
PR | San Sebastián Municipio | 72131
PR | Santa Isabel Municipio | 72133
PR | Toa Alta Municipio | 72135
PR | Toa Baja Municipio | 72137
PR | Trujillo Alto Municipio | 72139
PR | Utuado Municipio | 72141
PR | Vega Alta Municipio | 72143
PR | Vega Baja Municipio | 72145
PR | Vieques Municipio | 72147
PR | Villalba Municipio | 72149
PR | Yabucoa Municipio | 72151
PR | Yauco Municipio | 72153

## Detailed - RSVPs (hidden)
Project | Source | Channel | Campaign Name | Page Clicks | ETT Page Submissions | RSVPs | Attendees | Notes | Owner
Frasier Solar | ACE | Engaging Networks
Mesa County Solar Moratorium | AEJ | Mobilize
Yavapai County Solar Moratorium | ASM
Mohave County Solar Moratorium | CROP
Propel Transmission
Clear Mountain
Ochoa Energy BESS
Lexington Solar
Prospect and Janus Solar Project
Town of Babylon BESS Moratorium
Dawn Harvest Solar
Hope Ridge Wind
Southampton BESS Moratorium
Birch Coulee
Coweta County Solar
Pinal County Solar
Jackson County Wind
Halifax County Solar
Cass County Solar
Bright Leaf & Swift Creek Solar + BESS
Surry County BESS
Paddlefish Solar
Hope Hull Solar
Eastern Cottontail Solar
Schnebly Coulee Solar
Sussex County Offshore Wind Project
Rancho Viejo Solar
Hesperus Solar
Prairie Power Solar Farm
Soul City Solar Project
Libra Solar Project
Greenlink West Transmission Project
Dry Lake East Energy Center
Blue Ridge Solar
Michaux Solar
Grand Junction Solar
Split Rail Solar
Badger Hollow Wind
Uplands Wind
Mount Vernon BESS
Gabriel Solar
Keystone Wind
Prairie Wolf Wind
Iron Pine Solar
Westfield Battery Ordinance
Bolivar Onshore Wind Ordinance
Goshen Onshore Wind Ordinance
Lee Onshore Wind & Solar Ordinance
New York Rapid Act
Daviess Solar Ordinance
Surprise BESS Ordinance
Livingston Energy Storage
Hanover BESS
Yellow Barn Solar
Grass Lake Solar
New Frontiers Solar Park
Darden Energy Center
Blue Lake BESS
Allen County Solar Ordinance
Valley Farms Energy Storage
Ironwood Transmission Line

## Josh number check (hidden)
Project | ACE Impressions | ACE Reach | ACE Social Clicks | CROP Reach | CROP Impressions | CROP Social Clicks | AEJ Reach | AEJ Impressions | AEJ Social Clicks | Total Reach | Total Impressions | Total Emails Sent | Total Peer to Peer SMS/Calls Sent | Email Clicks | SMS Clicks | Totals Clicks to Page | Total Comment Submissions (ETT page) | Total RSVPs (Petition page) | Total Attendees | Notes
Frasier Solar, Knox Co, OH | 0 | 0 | 0 | 29789 | 177541 | 0 | 0 | 0 | 0 | 29789 | 177541 | 25442 | 2044 | 50 |  | 2400 | 327 | 33 |  | Other platforms?
Mesa County, CO | 0 | 0 | 0 | 48566 | 266354 | 686 | 25581 | 138465 | 0 | 74147 | 404819 | 0 | 7241 | 0 |  | 700 | 0 | 0 |  | Other platforms?
Yavapai County, AZ | 0 | 0 | 0 | 19345 | 44987 | 500 | 33422 | 198582 | 0 | 52767 | 243569 | 0 | 7241 | 0 |  | 577 | 0 | 0 |  | Other platforms?
Mohave County, AZ | 0 | 0 | 0 | 0 | 0 | 0 | 23887 | 156574 | 0 | 23887 | 156574 | 0 | 246 | 0 |  | 0 | 0 | 29 |  | Other platforms?
Propel Transmission, NY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1287 | 0 |  | 0 | 0 | 2 |  | Other platforms?
Clear Mountain, Clermont OH | 0 | 0 | 0 | 114881 | 460260 | 2921 | 60033 | 347708 | 0 | 174914 | 807968 | 0 | 573 | 0 |  | 687 | 0 | 0 |  | Other platforms?
Ochoa Energy BESS, Katy, TX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3619 | 0 |  | 0 | 20 | 0 |  | Other platforms?
Fayette County (Lexington) KY Solar | 0 | 0 | 0 | 104124 | 641006 | 6814 | 106267 | 479426 | 6857 | 210391 | 1120432 | 0 | 0 | 0 |  | 8163 | 0 | 4 |  | Other platforms?
Prospect & Janus, Weld County CO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1281 | 0 |  | 0 | 0 | 1 | 1 | Other platforms?
Babylon BESS, Suffolk Co NY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9974 | 0 |  | 0 | 0 | 17 | 1 | Other platforms?
Dawn Harvest Solar, Rock Co, WI | 251994 | 110497 | 5098 | 238444 | 606669 | 14269 | 0 | 0 | 0 | 348941 | 858663 | 5029 | 2760 | 2 | 236 | 19695 | 6 | 7
Hope Ridge Wind, Dickinson Co NE | 305340 | 23728 | 1823 | 3532 | 36604 | 89 | 0 | 0 | 0 | 27260 | 341944 | 92 | 25 | 0 | 1 | 90 | 0 | 18
Southampton BESS, Suffolk Co, NY | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 |  | 0 | 8 | 0 |  | Other platforms?
Birch Coulee Solar, Renville CO, MN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12690 | 0 | 26 | 0 | 26 | 14 | 0 |  | 14 of 18 public comments driven by ACE. All from email blast
Coweta County, GA Solar | 0 | 0 | 0 | 12264 | 217744 | 670 | 0 | 0 | 0 | 12264 | 217744 | 212 | 78 | 0 | 8 | 678 | 0 | 5
Pinal County, AZ Solar | 0 | 0 | 0 | 35966 | 490801 | 2476 | 0 | 0 | 0 | 35966 | 490801 | 0 | 0 | 0 | 0 | 2476 | 0 | 11 |  | Other platforms?
Jackson County, IA Wind | 0 | 0 | 0 | 1361 | 11535 | 27 | 0 | 0 | 0 | 1361 | 11535 | 20 | 16 | 0 | 1 | 28 | 0 | 0
Halifax County, VA Wind | 0 | 0 | 0 | 1137 | 9881 | 28 | 0 | 0 | 0 | 1137 | 9881 | 30 | 20 | 0 | 2 | 26 | 0 | 0
Cass County, NE Solar | 0 | 0 | 0 | 1184 | 10497 | 27 | 0 | 0 | 0 | 1184 | 10497 | 12 | 12 | 0 | 0 | 27 | 0 | 0
Paddlefish Solar, Wells & Huntington Co, IN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SR Hope Hull Solar, Montgomery, AL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 362 | 341 | 1 | 2 | 105 | 0 | 2 |  | Other platforms?